Final Report

End line Survey for Banking on Change Project for Carryover groups

Submitted to:

CARE Kenya

BY:

Davina and Qualispess Consultancy

Cell Phone: +254 723 471 371

Email: infodavina@gmail.com

November, 2015

ACKNOWLEDGEMENTS

Davina and Qualispess Consultancy Team wishes to thank the CARE Kenya BoC staff and the entire CARE Kenya fraternity for giving us the opportunity to conduct this final evaluation which was a follow-up to baseline study undertaken at the beginning of the project. Davina and Qualispess relay their heartfelt gratitude specifically to the programme manager Mr. Francis Mburu, M&E Coordinator Mr. Ayub Were and the entire BoC Kenya family for the relentless support in planning, supporting and coordinating logistics during field work.

The team is greatly indebted to all stakeholders of the Financial Inclusion Sector who participated in the survey by providing relevant information or referral during fieldwork.  The supervisors and all the field enumerators who diligently collected data and provided primary information that forms the content of this final evaluation are specially acknowledged for the good work. The team gives special recognition to Naveed Somani, the Monitoring, Evaluation and Learning Officer, Banking on Change Plan UK for the continuous technical support and guidance he has accorded the exercise in all the critical stages.

# TABLE OF CONTENT

ACKNOWLEDGEMENTS	ii

TABLE OF CONTENT	iii

LIST OF FIGURES	v

LIST OF ACRONYMS	vi

EXECUTIVE SUMMARY	vii

SECTION 1.0: INTRODUCTION	1

1.1 Background of VSLA	1

1.2 CARE Kenya	1

1.3 Banking on Change (BoC) Project	1

SECTION 3: EVALUATION METHODOLOGY	3

3.1 Project Area	3

3.2 Study Design	3

Study design	4

3.3 Study population and sampling	4

3.4 Training research assistants and FGD facilitators	5

3.5 Data collection	6

3.6 Data Quality Assurance	7

3.7 Data Entry and Analysis	7

SECTION 4: RESULTS PART I: DESCRIPTIVE STATISTICS ON THE HOUSEHOLD	9

4.1 Progress Poverty Index (PPI) score	9

4.2 Educational and literacy attainments	9

4.3 Main occupation	9

4.4Household-decision making	10

4.5Housing	11

4.5.1 Housing ownership and materials	11

4.5.2 Sources of energy	11

4.5.3 Type of toilet	12

4.6 Assets	12

4.7 Leadership roles in VSLA	14

4.8 Copying mechanisms	14

4.9 Food Security and Agriculture	15

3.10 Food consumption	15

ECTION 5: RESULTS PART II: DESCRIPTIVE STATISTICS ON THE VSLA MEMBERS	17

5.1 Gender/Sex Composition	17

5.2 Child rights	17

5.3 Income generation activities	17

5.4 Control over own resources	19

5.5 Access to financial services	21

5.6 Factors to consider before taking a loan	24

5.7 Proportion correctly identifying correct loan deal	24

5.8Investments and Household Support	25

5.8.1 Asset acquisition/purchase	25

5.8.2 Cost of housing and house improvement	26

5.8.3 Type of improvements	27

5.9 Education (on themselves/ other household members)	28

5.10  Medical expenses and access to health services	29

5.11 Clothing	29

5.12 Household events	30

5.13 Financial Literacy and Business Skills	31

5.13.1 Business skills	31

5.13.3 Factors of business set and elements of setting price	32

5.14 Financial Anxiety & Self Esteem	32

5.14.1 Financial anxiety	32

5.14.2 Self-image	33

5.15 Participation & Social Position	34

5.15.1 Participation	34

5.15.2 Social Position	35

SECTION 6: ASSESSMENT OF BOC PROGRESS	37

SECTION 7: CONCLUSION AND RECOMMENDATION	38

7.1 Conclusion	38

7.2 Recommendation	38

REFERENCE	39

ANNEXES	39

Annex 1:  HH Survey tool	39

Annex 2: FGD guide	39

Annex 3: ToR	40

LIST OF TABLES

Table a. Sampling distribution	5

Table 1. Distribution of the Carryover members by educational and literacy attainments	9

Table 2. Distribution of the VSLA members by occupation	10

Table 3. Mean score core decision areas by groups	11

Table 4. Distribution of the VSLA members by house ownership and materials	11

Table 7. Distribution of the groups by toilet facility	12

Table 8. Distribution of the VSLA members by type of assets purchased	13

Table 9. Distribution of groups by household food security and agricultural indicators	15

Table 10. Distribution of groups by food consumption pattern	15

Table 11. Distribution of carryover groups by child right issues	17

Table 12. Distribution of carryover groups by main occupation of VSLA member	18

Table 13. Distribution of carryover groups by proportion engaging in business and revenue based activities	19

Table 14. Distribution of carryover groups by loan contracted and source	21

Table 15. Distribution of carryover groups by saving tools	23

Table 16. Distribution of groups by use of loans	23

Table 17. Distribution of carryover groups by factors to consider when taking a loan	24

18. Distribution of carryover groups by proportion correctly identifying a good loan facility	25

Table 19. Distribution of carryover groups by asset acquired in the last 12 months	25

Table 20. Distribution of carryover groups by education expanses	28

Table 21. Distribution of carryover groups by medical expanses	29

Table 22. Distribution of carryover groups by financial literacy and business skills	31

Table 23. Distribution of carryover groups by elements of setting price and factors in business set up	32

Table 24. Distribution of carryover groups carryover groups by self esteem	33

Table 25. Distribution of the carryover groups by participation	34

Table 26. Distribution of the carryover groups by social position	36

Table 27 Summary of project progress	37

# LIST OF FIGURES

Figure a. Key reasons for non-response	5

Figure 1. Distribution of the groups by type of decision maker	10

Figure 2. Distribution of the groups by proportions purchasing assets	13

Figure 3. Distribution of the groups by VSLA involvement	14

Figure 4. Distribution of the groups by financial ability	14

Figure 5 Distribution of groups by control over financial resources	20

Figure 6 Distribution of groups by average loan amount acquired	22

Figure 7 Distribution of groups by cost of housing and house improvement loan amount acquired	27

Figure 8 Distribution of groups by type of house improvement	27

Table 9. Average money spent on self-education and education of others	28

Figure 10. Distribution of groups by average amount spent in medical expenses	29

Figure 11 Distribution of groups by average amount spent in clothing	30

Figure 12. Proportion spending money on special events	30

Figure 13. Distribution of the groups by financial anxiety	33

Figure 14 Level of communalities for key elements of self esteem	34

# LIST OF ACRONYMS

AFC			Agricultural Finance Corporation

APPR			Annual Participatory Programme Review

BBK			Barclays Bank of Kenya

BOC 			Banking on Change

CBOs			Community Based Organizations

CBT			Community Based Trainers

COSALO		Community Savings and Loan

COSAMO		Community Savings Mobilization GS&L Project

DMT			Deposit Taking Microfinance

ECDE			Early Childhood Development and Education

FDS-K			Financial Sector Deepening–Kenya

FGD			Focus Group Discussion

GoK			Government of Kenya

GS&L 			Group Savings and Loan

IGA			Income Generating Activity

KCB 			Kenya Commercial Bank

KII			Key Informant Interviews

KIIs			Key Informant Interviews

K-Rep			Kenya Rural Enterprise Programme

KUAP			Kisumu Urban Apostolate Programme

KWFT			Kenya Women Finance Trust

MDG			Millennium Development Goal

MFIs			Micro Finance Institutions

NGOs			Non-Governmental Organizations

NHIF			National Hospital Insurance Fund

ROSCAs		Rotating Savings and Credit Association

SACCO			Savings and Credit Cooperative Society

SPM 			Selection, Planning and Management

SPSS			Statistical Package for Social Scientists

WED			Women Enterprise Development

VSLA			Village Savings and Loans Association

CRS			Catholic Relief Services

VICOBA		Village community bank program (VICOBA)

# EXECUTIVE SUMMARY

Over the last two decades microfinance institutions have been a major positive force in providing millions of poor people with access to credit. However, rural areas receive less coverage by microfinance institutions because the costs of delivery are high and the demand for loans large enough leading to low profit.. Consequently, few rural poor have access to savings or other financial services that can help them increase their financial security and improve their lives. But very poor people tend to be much more comfortable investing what they already own than increasing their level of liability by taking out a loan. This logic is central to understanding the vital contribution to household livelihood security made by VSLA programmes.

Banking on Change Kenya Phase 2 focused on wealth creation, working with existing group members trained to provide increased and deeper financial education as well as new training in enterprise development and business management.

The End line evaluation assessed the extent to which Banking on Change met its overall vision of improving the quality of life for poor people by providing a range of training, supporting the establishment of income generating activities, and by linking some savings groups to the formal financial sector. The impact indicators focus on social and economic factors at different engagement levels. The evaluation was designed to collect both primary and secondary data using household questionnaire, review of project and related documents, as well as focus group discussions. Both qualitative and quantitative data analysis procedures were adopted. The findings of the evaluation indicate general progress in overall project performance. There were however different degrees of progress, impact and effectiveness in the specific components. The significant success achieved in meeting the fundamental development targets indicates relevance of the project design.

The proportion of carryover members who ever attended school increased from 89.9% at baseline to 96% at end line, denoting a 6% increase. On highest level of education achieved, more members were reported to have attained primary, secondary and college/university levels by 0.2%, 6.2% and 2.8% respectively since baseline. In overall, there was increment in educational attainments for carryover group members in all the levels of education indicating continuous efforts of members to improve their educational status.

There has been a tremendous shift in occupation, since many members who didn’t have occupation at baseline have become engaged in some occupation at end line. In overall, there’s increased engagement in income generating activities among carryover members as demonstrated by reduced proportion of members with no occupation (by 26%), increased proportion of members involved in agriculture (by 34.1%), fishing (by 2.7%), working on own farm (by 1.9%), employment both in formal(by 0.8%) and informal sectors(by 3.6%).

Most decisions were jointly (self and spouse) made at 43.6% with slight improvement since baseline by 3.6%. The role of the saving group member in decision making improved significantly from 30.1% to 43.4% at end line. Generally there’s increased involvement of the VSLA member in household decision making on financial expenses allocation either as individual or and through consultation with the spouse.

Change in quality of housing improved as households with iron sheet roofs increased from 87.1% to 95.6% and households with cement floors increased from 31.4% to 36% at end line. Moreover, there was increased ownership of housing by 12% among the carryover members. There is improvement in sanitation facilities and environment for carryover members as demonstrated by increase in number of households using covered pit latrines from 34.6% at baseline to 48.8% at end line; decrease in those using uncovered pit latrines from 59.1% at baseline to 45.6% at end line and decrease in those without latrines by 1%).

There is improvement in use of various sources of energy for lighting and cooking amongst significant proportions of the carryover members since baseline. Kerosene lantern, solar electricity and wire electricity were the widely used sources of energy for lighting with registered increases at 51.9%, 15.6% and 2.2% respectively since baseline. Wood, charcoal and kerosene were variedly used as sources of energy for cooking with registered minimal increases at 0.44%, 1.3% and 1% respectively since baseline.

There was a significant percentage increase (10.1%) in the number of carryover VSLA members who bought at least one asset in the last one year at the time of the baseline compared to the end line. Generally, the average number of assets owned increased during the project life. Of greater importance were the productive assets comprising of the livestock and agricultural tools/materials/equipment which increased among the carryover members. Increased access to productive assets had enabled VSLA participants to benefit from numerous business opportunities bringing in increased income from diversified sources.

There was significant decline in proportion of households who reported “no difficulty” to cope with financial difficulties by 5.5% margin. Further, majority of the members indicated their households were “somehow able” to cope at 72.2% at end line presenting a 16.2% increase since baseline. Importantly, households that had a lot of problems to cope with bills and daily consumer requirements declined significantly by 10.4% margin among the carryover members. The final evaluation showed that carryover VSLA members recorded significant improvements in food production during the last year of production. Key indicators of increased agricultural productivity included increase in proportion of households by 20.2% who produced enough harvests during the previous harvest season to cover the food need of their household members until the current harvest; increase in percentage of households who considered their year’s harvest as good by 21.5% and significant decrease in households who reported their harvest to have been bad by 32.6%. About 49.9% of the Carryover members reported changes in quantity and quality of meals in the households. Further households missing meals had significantly reduced from 30% to 18.2% at end line.

The findings revealed that 41.0% of carryover groups were engaged in crop production reflecting 17.9% increase since baseline. A reasonable proportion also engaged in self-employment although at a decreased rate of 7.5% compared to baseline. In overall, BoC participants have increased their entrepreneurial activities as witnessed by increased number of members engaging in income generation activities, increased number of households increasing their business funding and increased number of VSLA members reporting increased profits. About 67.5% contracted loans although this result was statistically not different from the baseline findings. Further results on sources of loans revealed that self-help group was the most dominant source of loans with 84.5% of carryover reporting having contracted a loan from this source in the last 12 months. This compared favourably with those who received loans from the same source since baseline translating to a 37.2% increase. The results further showed that the average loan amount contracted in the past one year was Ksh. 11,681.3 against Kshs. 6,913.9 at baseline. Generally  this  outcome  reveal  significant  increase  in  amounts  of loan contracted which is a pointer to increased loan repayment capacity among the members and  increased confidence  in the VSLA as a reliable source of financial services especially credit to its members.

Analysis of the saving tools revealed that more carryover members are now saving with the VSLA/Self- help group (56.6%) at end line than it was at baseline (28.6%). The other important avenues for saving were the private and government banks which registered increments at 6.5% and 1.1% since baseline respectively. When the respondents were asked whether they knew what constituted a good loan deal, fewer carryover members selected loan two (40.6%) denoting a 10.3% decrease since baseline. The carryover participants have increased their entrepreneurial activities as demonstrated by increased number of members engaging in income generation activities (15.5%), increased number of households increasing their business funding (16.3%) and increased number of VSLA members reporting increased profits (62.6%)

There’s improvement in contribution made by carryover members towards payment of housing rent and improvement of their housing. The average monthly rent increased from Kshs.3000 at baseline to Ksh. 4905 at final evaluation and increased contribution was made towards housing improvement from Kshs. 15,331 at baseline to Kshs. 29, 343 at final evaluation. The evaluation revealed a decrease in members’ expenditure on medical bills for self and other family members, although the members reporting not able to access medical services had decreased from 38.8% to 24.3% at end line. There is evidence of increased investment in clothing among the carryover members based on t-test, which is largely attributable to increased economic empowerment arising from their participation in saving groups. The average yearly expenditure on clothes for self among carryover members had increased to Kshs. 20,407 against Kshs. 14,506 at baseline. Likewise the average annual expenditures on clothing for other household members had improved to Kshs. 24,110 against Kshs. 11,839 at baseline.

The findings focusing on record keeping revealed that 40.8% of the carryover members kept records against 43.2% at baseline recording a 2.4 % decrease. More VSLA members were knowledgeable now about the elements they should consider while setting prices for their goods as shown by the increased proportions of respondents since baseline who mentioned cost of raw material (1.6%); transportation (7.2%), my time (1.65%) and market price (7.1%). In overall more VSLA members have increased knowledge in price setting for commodities and setting up of businesses than at baseline.

Just as was at baseline, carryover group members recorded relatively higher mean scores for household level indicators that touched on relationship with the spouse. Decreased changes were reported for “my spouse shows me respect” (at a mean of 3.53) and “my spouse values my role in the household” (at a mean of 3.56) by 0.28 and 0.25 since baseline respectively.

In conclusion, the evaluation portray mixed results with incremental performance and changes noted on several indicators including food production, investment and entrepreneurial activities, joint and member participation in decision making, purchase of assets, expenditure on special events and self-image. Low performance however was noted on keeping of business records, financial anxiety and civil society participation.

There’s increased engagement in income generating activities among carryover members as demonstrated by reduced proportion of members with no occupation, increased number of households increasing their business funding and increased number of members reporting increased profits, increased proportion of members involved in entrepreneurial activities including agriculture and fishing and employment both in formal and informal sectors. Moreover, members have increased knowledge in price setting for commodities and setting up of businesses than at baseline.

Generally there’s increased involvement of the carryover members in household decision making on financial expenses allocation either as individual or and through consultation with the spouse. There was increment in proportion of carryover members who reported improvements in coping mechanisms with financial difficulties, bills and daily consumer requirements.

More carryover members bought at least one asset in the last one year at the time of the baseline compared to the end line. The average number of assets owned increased during the project life. There’s improvement in contribution made by carryover members towards payment of housing rent and improvement of their housing.

The carryover members recorded significant improvements in food production as demonstrated by increase in proportion of households who produced enough harvests during the previous harvest season to cover the food need of their household members until the current harvest; increase in percentage of households who considered their year’s harvest as good and significant decrease in households who reported their harvest to have been bad.

Increase in uptake and utilization of financial services has been reported among the carryover members as shown by more members accessing credit from saving groups; substantial increase in average loan amount contracted in the last one year. Analysis of the saving tools revealed that more carryover members are now saving with the VSLA/Self- help group at end line than it was at baseline.

Based on the foregoing discussions, this evaluation makes the following recommendations: The evaluation noted capacity gaps in the management and running of some saving groups thereby resulting to issues of default, mismanagement and misunderstanding among the membership. Future interventions should put more emphasis in strengthening governance and management structures of the VSLA groups. Quality monitoring and mentoring should be reinforced to guarantee sustained operations of the groups beyond project period; Agriculture has stood out as a key livelihood activity for most of the VSLA members because of its viability in the rural settings where the smallholder farmers reside. The VSLA is already providing finances for agricultural investment, what is missing however is quality agricultural extension support so as to achieve increased production and productivity. Strengthened linkages with relevant Government departments, agencies and private sector players will be crucial in achieving this objective; and Although VSLA had become reliable sources of financial services to the members, they were not panacea to all the financial needs of the members. Linkage to formal financial services remains a major requirement and need which should be escalated to reach more groups.

# SECTION 1.0: INTRODUCTION

## 1.1 Background of VSLA

Over the last two decades microfinance institutions have been a major positive force in providing millions of poor people with access to credit. However, rural areas receive less coverage by microfinance institutions because the costs of delivery are high and the demand for loans large enough to turn a profit is low. Consequently, few rural poor have access to savings or other financial services that can help them increase their financial security and improve their lives. But very poor people tend to be much more comfortable investing what they already own than increasing their level of liability by taking out a loan. This logic is central to understanding the vital contribution to household livelihood security made by VSLA programmes.

## 1.2 CARE Kenya

CARE International in Kenya (CIK) is a development and humanitarian organization with a goal to reduce poverty at the household level, and to provide relief in emergencies. CIK has been operational in Kenya since 1968. We currently carry out major initiatives in Refugee and Emergency Operations, Health, Livelihoods, Water and Sanitation and in HIV/AIDS. We are one of the lead agencies under the United Nations High Commission for Refugees (UNHCR) and the World Food Programme (WFP), for water and hygiene, food distribution and basic education in Dagahaley camp, one of three such camps in Dadaab, along the Kenya-Somalia border.

CARE also carries out significant activities in livelihoods (group savings and loans, water and sanitation), civil society organizational strengthening, and environmental services. Our main office is in Nairobi, and our priority regions are Nyanza Province (with a sub-office in Kisumu and projects in Siaya, Kisii and Nyamira), Kibera in Nairobi, North Eastern Province (sub-offices in Garissa, Dadaab and Takaba) and Marsabit and Embu in Eastern Province. CARE Kenya has been implementing group savings and loan methodology since the year 2004 in different parts of the country. The activities have yielded significant results and have contributed to tremendous improvement in livelihood conditions of the targeted communities and households.

## 1.3 Banking on Change (BoC) Project

Banking on Change, a partnership between Barclays, CARE UK and Plan UK was established in 2009. Originally it set out to deliver a savings-led microfinance programme with the aim of improving the financial inclusion of people in 11 countries across Africa, Asia and South America. Using a savings led microfinance methodology, Banking on Change mobilized individuals into savings groups so they could save regularly, and in turn borrow small amounts at a fair rate of interest agreed by group members.

In phase 1, Banking on Change established over 21,000 new groups who have accrued over $6.5m in savings and loaned out over $5m. Nearly 500 groups have been formally linked to group accounts in branches of Barclays in Uganda, Ghana, Tanzania or Kenya.

Barclays renewed its commitment to the partnership through an additional three year investment in a second phase of Banking on Change (2013-2015). In phase 2 the partnership has used the same savings led microfinance methodology established in phase 1 as a springboard for implementing a more focused, in-depth, programme targeted at young people in seven countries (Egypt, Ghana, India, Kenya, Tanzania, Uganda and Zambia). The specific aims are:

- Support young people in setting up 10,000 youth savings groups.

- To provide an expanded range of in-depth financial literacy, employability and entrepreneurship skills training to over 330,000 beneficiaries, of whom 75% will be under 35.

- To support the establishment of around 41,000 income-generating activities and small businesses that will be sustained over the course of the programme.

- To link over one-third of Banking on Change savings groups in Africa (approx 5,000) to Formal Financial Institutions, including Barclays. A proportion of individual group members will also be linked to personal bank accounts.

The country programme for Kenya contains the following elements:

- Phase 2 focused on wealth creation, working with existing group members trained to provide increased and deeper financial education as well as new training in enterprise development and business management.  It was also to form youth savings groups providing youth with the skills necessary for greater financial, marketing and enterprise understanding. This would enhance self-reliance and improve the ability of beneficiaries to start and sustain income generating activities or seek employment. All levels of training were to be delivered.

- The project intended to reach 80,823 direct beneficiaries, 4,490 groups, of which 2,652 were to be new youth groups.  About 33,073 beneficiaries would be carried over from Phase 1, of whom 39% were to be aged between 10 and 35. 75% of all beneficiaries (60,784) were to be under 35.

Of these original targets, the programme at January 2015 was on target to reach 33,073 carry over beneficiaries. At the time of final evaluation 132% of carry-overs are under 35 years.

# SECTION 3: EVALUATION METHODOLOGY

## 3.1 Project Area

The carryover endline evaluation covered 7 sub-Counties including Homa Bay, Ndhiwa, Kisumu East, Kisumu West, Embu East, Embu West and Mbeere North. The area coverage for Embu County is 2,818 Km2. Homa bay and Ndhiwa are located within Homa Bay County in the former Nyanza Province. The area coverage is 3,183.3 Km2. Kisumu West and Kisumu East is located in Kisumu County. The area coverage is 2, 085.9 Km2. Nyalenda is located within Kisumu East District which lies within longitude 34o 10’E and 35o 20’E and latitude 0o 20’S and 0o 50’S, occupying 557.7 Km2 including Kisumu City.

Other than Nyalenda slums, BoC phase 2 coverage area included Shauri Yako and Dallas informal settlements. Shauri Yako which is the biggest slum in Homabay town is an epitome of poor conditions of living characterized by limited access to piped water and electricity. The area's black cotton soil easily collapses making construction of latrines difficult and very expensive, for the few who would be in position to construct latrines. Inadequate sanitation therefore is a major cause of poor health within the slum. On the other hand Dallas is one of the main slums within Embu town with significant socioeconomic and environmental challenges. Dallas is a cosmopolitan community consisting of many tribes from across the Mt. Kenya region.

## 3.2 Study Design

The overall study design adopted the pre-and post experimental design with a cross-sectional, concurrent mixed methods approaches applied at baseline and final evaluation. One cohort of carryover groups was surveyed at baseline (pre-test) and at final evaluation (post-test). Pre-experimental design made it possible for the evaluation process to establish change brought about by the BOC interventions. Concurrent mixed methods approach entailed both quantitative and qualitative survey methods being applied at the same time. The latter approach was necessary to assess internal and external validity of the results. It also allowed for assessment of the BoC intervention attributions.

## Study design

## 3.3 Study population and sampling

The study population included all groups reached by the Project representing households within Embu East, Embu West, Embu North, Mbeere South, Mbeere North, Kisumu West, Kisumu North, Ndhiwa and Homabay sub-Counties.

For quantitative study, a sample size of 682 members from carry over groups was interviewed.  These sample sizes were arrived at during the baseline for each cohort using the following formula.

The specifications are as follows:

| n | = | Required minimum sample size of VSLA members per survey round. |
| --- | --- | --- |
| d | = | The design effect, which is related to the fact that we used a two stage-cluster sampling; d is a function of the intra-cluster correlation. In other words, the more the outcomes of the sampling unit per-cluster are homogeneous, the more important “d” should be. In general d is equal to 2 for similar type of surveys. |
| P1 | = | The estimated level of an indicator measured as a proportion at the time of the first survey. For instance if the indicator we wished to measure is “the proportion of women making key decisions at household level” P1 was this indicator and we should have found the value of P1 from previous studies (like Demographic and Health studies, for instance). However, because this data was not available, we considered P1 as 50%, value that provided the largest sample size. |
| P2 | = | The expected level of the indicator at some future date such that the quantity (P2 - P1) was the size of the magnitude of change desired. P2 was considered at 60%. |
| Zα | = | The z-score corresponding to the degree of confidence with which it is desired to be able to conclude that an observed change of size (P2 - P1) would not have occurred by chance (α - the level of statistical significance). Z-score was considered at 1.96. |
| Zβ | = | The z-score corresponding to the degree of confidence with which it is desired to be certain of detecting a change of size (P2 - P1) if it actually occurred (β - statistical power). Generally β was considered as 80% power. |

The final sample size was also corrected for expected non response and lost in follow-up (members dropping out of the groups from baseline to final survey).  Generally we assumed a non-response rate of 5% and attrition rate of 10%.

During the implementation of the survey the study participants consisted of all Carry-Over members from phase 1 who continued with the programme into phase 2, and who took part in the Carryover Baseline Household Survey.  For the carryover groups’ survey, 682 members sampled at baseline were targeted out of which 511 were reached as indicated below:

#### Table a. Sampling distribution

|  | Planned Sample Size at Baseline | Actual Sample Size at Baseline | Drop out/Non response rate at Baseline | Actual Sample Size at End line | Drop out/Non response at End line |
| --- | --- | --- | --- | --- | --- |
| Carryover members | 721 | 682 | 39 | 511 | 171 |

The non-response rate among the carryover group members stood at 25% with about 171 members not able to participate in the exercise. The reasons for the drop-out/non-response rate are highlighted in the figure below.

##### Figure a. Key reasons for non-response

## 3.4 Training research assistants and FGD facilitators

All data collection team were trained in a central area for easy management of the exercise. The team was recruited from the communities within study sites. The team comprised of enumerators, FGD facilitators and Supervisors. The suitable supervisors, FGD facilitators and enumerators for the evaluation were identified and recruited by the project manager in consultation with the consultants. The selection was done on the basis of their academic qualifications, previous experience in research/evaluation and their ability to be courteous, to follow instructions precisely and accurately, and capability to establish good rapport with respondents as well as fluency in the use of local languages.  The data collectors were taken through a 3 day intensive orientation session by the consultants in which research team were exposed to the concepts; the survey instruments and data collection methods. Specifically, the team was trained on how to ask the questions and complete the instruments accurately. They also reviewed and familiarized themselves with the tools.

## 3.5 Data collection

All aspects of data collection, entry, and analysis for both the YSLA and Carryover End line Household Surveys were implemented. The Country Office compiled a list of members to be surveyed that specifies the contact and location details of respondents. All the 682 members interviewed at baseline were targeted. The survey included members who had dropped out from the baseline provided they were still located in the same community and agreed to participate. A detailed one hour long survey was administered to all members in both cohorts. The survey was administered using the same tool for the Baseline Household Survey. Additional questions establishing any changes with regards to the member’s participation in the programme, as well as further questions to help attribute change from responses given in the baseline, were added to the survey. All survey interviews were conducted face-to-face at the member household’s premises. Information was collected through interviews as well as direct observation in respondents’ households. The questionnaire included, Full contact details on the members including GPS coordinates, Socio-Demographic Profile of VSLA Member and Household, Access to Financial Services, Housing and Household Assets, Member Investments and Expenses, Consumption and Agricultural Production, Civil society, political participation and child rights and Self-image and social position.  In addition to these socio-economic modules the end line survey instrument included a poverty-measurement scorecard following the PPI® approach. During data collection, regular updates on the survey progress were sent to the Evaluation Team. Amongst others, the updates specified the number of interviews completed and households not reached as well as reasons for not reaching all households. Follow up data collection required field teams to conduct up to two revisits of households that were not available at the first visit.

FGD Criteria

FGD participants’ selection criteria were set as follows: Men aged 16-24; Women aged 16-24; Men aged 24+; and Women aged 24+.  And group sizes were between 8 and 12 members for every focus group discussion session. To ensure members who satisfy the sampling criteria were sufficiently proximate to one another to take part in the FGDs, the end line HH survey groups was split into two or three distinct geographical areas, which include sufficient members of the right age and gender to participate (at least) in the four FGDs outlined above in each area.

Sampling was done prior to the end line household survey, with members who have been selected informed during the HH survey. A list of reserve members of the same size and satisfying the same criteria as the original sample was prepared in case members in the original sample could not participate. Focus Group Discussions was complete within two weeks of final HH survey data collection.

The discussion lasted between 45 minutes and 1.5 hours, and was administered by trained facilitator and record takers aided by digital recorder. The transcription was done later by trained transcribers. The profile sheet was completed by all members and verified before the groups dispersed.

The FGD interview guide was based on the guided format to assess core issues of the project against some selected key HH survey indicators. The facilitators used the interview guide provided by the Global M&E officer at UK office. The general structure of the interview guide included the following sections: Introductory Questions; Household Profile; Member Profile; Access to financial services; Income generating activities; Investment, expenses and consumption; Closing questions.

## 3.6 Data Quality Assurance

Data quality assurance included an actual pre-test to provide them with a hands-on experience of the task, followed by reporting back and discussion session. The pre-test enhanced the workability of the tools by practically assessing their reliability, time taken for administration, logical sequence of questions, clear wording, and accuracy in translations. The training session enabled participants to master the tools and gain confidence in articulating the specific issues that the baseline survey sought to address. The team was enlightened about research ethics and enumeration skills. Supervisors were provided with extra orientation on data quality management skills. Several protocols were developed to ensure that quality mechanisms were put in place and strictly followed. Internal quality checks were observed and implemented by the team leader, support contractors and enumerators. In addition the following were taken into account: daily monitoring using monitoring tools prepared for the entire exercise; daily reporting by the supervisors and support consultants on the process; and daily target reporting and review of every filled questionnaire.

## 3.7 Data Entry and Analysis

Quantitative data was entered into CS PRO 5.0 data form installed in six computers. Analysis was with the help of SPSS version 19.0 based on descriptive statistics which included proportions and means. Test for proportional differences and percent change since baseline was performed to report change for each indicator on focus. Quantitative data was summarized using descriptive statistics in SPSS and excel packages. Critical review involved in depth classification and extraction of relevant information to report as part of documentary report.

Z-test was used to determine significant difference between two proportions for each indicator at baseline and final. Two conditions guided the procedure to ensure effectiveness. These were:

- A random sample of each of the population groups to be compared.

- Categorical data (Pre-determined  HH questionnaire satisfied this condition)

Null Hypothesis

H0: p1 - p2 = 0, where p1 is the proportion from the first population (baseline) and p2 the proportion from the second (Final). This inferential statistics has been indicated by clearly marking the significant areas with * (which means two proportion paired between baseline and final are significantly different at p<0.05.

For variables where dependent variables were measured at the ordinal level Wilcoxon W test was performed to determine the significant difference that could be attributable to BoC intervention.

Qualitative Analysis adopted the styles of Framework analysis for Focus Group Discussions. One key advantage with this framework analysis is that although it uses a thematic approach, it allows themes to develop both from the research questions and from the narratives of research participants. The process of data analysis began during the data collection, by skilfully facilitating the discussion and generating rich data from the interviews and FGDs, complementing them with the observational notes and typing the recorded information.

This stage was followed by familiarization with the data, which was achieved by listening to voice records, reading the transcripts in their entirety several times and reading the observational notes taken during interview and/or FGDs and summary notes written immediately after the interview and/or FGDs. The aim was to immerse in the details and get a sense of the interview as a whole before breaking it into parts. During this process major themes began to emerge. The next stage involved identifying a thematic framework, by writing memos in the margin of the text in the form of short phrases, ideas or concepts arising from the texts and beginning to develop categories. At this stage descriptive statements were formed and an analysis carried out on the data under the questioning route. The third stage, indexing, comprised sifting the data, highlighting and sorting out quotes and making comparisons both within and between cases. The fourth stage, charting, involved lifting the quotes from their original context and re-arranging them under the newly-developed appropriate thematic content.

# SECTION 4: RESULTS PART I: DESCRIPTIVE STATISTICS ON THE HOUSEHOLD

## 4.1 Progress Poverty Index (PPI) score

The final evaluation established the average PPI score for Carryover members to be 51.12. From the PPI look-up tables for 2005, the likelihood of appearing below the poverty line of $2.50/day was 44.4% at final.  Baseline information for this indicator was however missing.

## 4.2 Educational and literacy attainments

The final evaluation assessed the beneficiaries educational and literacy attainments. A comparison was made to establish educational variations that may have emerged during the three year project period among the carryover groups. The proportion of members who ever attended school increased from 89.9% at baseline to 96% at end line, denoting a 6% increase. On highest level of education achieved, more members were reported to have attained primary, secondary and college/university levels by 0.2%, 6.2% and 2.8% respectively since baseline. In overall, there was increment in educational attainments for carryover group members in all the levels of education indicating continuous efforts of members to improve their educational status. On literacy level however, there was a decline which somewhat contradicted the later status.

#### Table 1. Distribution of the Carryover members by educational and literacy attainments

| Characteristics | Evaluation |
| --- | --- |
|  | Baseline (n=682) | End line (n=511) |
| School Attendance | 89.9 | 96.0 |
| Highest Level of Education |  |  |
| Primary | 62.9 | 63.1 |
| Secondary | 21.8 | 28.0 |
| College/University | 5.1 | 7.9 |
| Literacy | 84.5 | 78.8 |

## 4.3 Main occupation

There has been a tremendous shift in occupation, since many members who didn’t have occupation at baseline have become engaged in some occupation at end line. “Agricultural worker” and “no occupation” registered the most significant increase at 34.1% and 26% respectively since baseline. In overall, there’s increased engagement in income generating activities among carryover members as demonstrated by reduced proportion of members with no occupation (by 26%), increased proportion of members involved in agriculture (by 34.1%), fishing (by 2.7%), works on own farm (1.9%), employment both in formal(by 0.8%) and informal sectors(by 3.6%). The increased involvement in gainful economic activities have been likely influenced by the Project’s interventions which emphasized on business training as well as saving and loaning activities which provided  members with financial services they needed as capital for investment.

#### Table 2. Distribution of the VSLA members by occupation

| Occupation type | Evaluation |
| --- | --- |
|  | Baseline (n=682) | End line (n=511) |
| Student/Pre-School | .1 | 0.2 |
| Domestic Work (House Work) | 2.9 | 0.4 |
| Retired | 3.7 | 0.8 |
| No Occupation* | 30.6 | 4.6 |
| Works On Own Farm | .3 | 2.2 |
| Agricultural Worker* | 10.9 | 45.0 |
| Animal Husbandry | .3 | 0.2 |
| Milk Producer, | .1 | 0.0 |
| Pastoralist | .1 | 12.2 |
| Fishing | 1.5 | 4.2 |
| Employee (Formal Sector | 7.2 | 8.0 |
| Employee (Informal Sector), | 4.4 | 8.0 |
| Casual Labour, | 6.7 | 4.2 |
| Self-Employed/Business Owner | 17.4 | 17.2 |
| Petty Trade | 3.1 | 2.0 |
| Making Handicrafts | 1.2 | 0.6 |
| Providing Services/Repairs | 3.5 | 2.4 |

* p<0.05 based on z-test for proportional differences

## 4.4Household-decision making

The evaluation sought to know who in the household decides on the financial expenses allocation.

Apparently for carryover groups decisions are made jointly (me and spouse) at 43.6% with slight improvement since baseline by 3.6%. The role of the saving group member in decision making improved significantly from 30.1% to 43.4% at end line. Generally there’s increased involvement of the carryover member in household decision making on financial expenses allocation either as individual or and through consultation with the spouse.

##### Figure 1. Distribution of the groups by type of decision maker

Key decision areas included children schooling, health care, food, housing/ house repair, acquisition of new land and household equipment. The overall contributions to these five critical decision areas had however not improved since baseline.  Although the member’s role in decision making had improved, they may have not gained enough power overtime to influence critical decisions on key household matters.

#### Table 3. Mean score core decision areas by groups

| Decision making item | Baseline (n=682) | End line (n=511) |
| --- | --- | --- |
| Household children’s schooling | 3.28 | 3.08 |
| Health of household members | 3.50 | 3.25 |
| Food for household members | 3.50 | 3.39 |
| Housing; house repair, acquisition of new land. | 3.24 | 3.11 |
| Household equipment | 3.26 | 3.21 |

## 4.5Housing

### 4.5.1 Housing ownership and materials

Change in quality of housing improved as households with iron sheet roofs increased from 87.1% to 95.6% and households with cement floors increased from 31.4% to 36% at end line. Moreover, there was increased ownership of housing by 12% among the carryover members. Although the proportion of those who rented houses increased from 50.5% to 87.5% at end line, there was improvement in a number of indicators of quality housing for the members, an indication of improvement in socio-economic status of the project beneficiaries. Increased incomes from business activities of the members were used to improve their housing.

#### Table 4. Distribution of the VSLA members by house ownership and materials

| Indicator | Evaluation |
| --- | --- |
|  | Baseline (n=682) | End line (n=511) |
| Ownership type |  |  |
| Household member owned | 84 | 92.0 |
| Rented* | 50.5 | 87.5 |
| Material for house roofing |  |  |
| Material |  |  |
| Cement | 0.7 | 0.1 |
| Tiles/Asbestos | 09.9 | 0.4 |
| Iron Sheets | 87.1 | 95.6 |
| Grass | - | 2.2 |
| Material for house floor |  |  |
| Ceramic tile | 0.6 | 0.1 |
| Wood | 1.0 | 0.2 |
| Cement | 31.4 | 36.0 |
| Sand | 5.9 | 2.0 |
| Soil | 56.2 | 60.0 |

* p<0.05 based on z-test for proportional differences

### 4.5.2 Sources of energy

There is improvement in use of various sources of energy for lighting and cooking amongst significant proportions of the carryover members since baseline. Kerosene lantern, solar electricity and wire electricity were the widely used sources of energy for lighting with registered increases at 51.9%, 15.6% and 2.2% respectively since baseline. Wood, charcoal and kerosene were variedly used as sources of energy for cooking with registered minimal increases at 0.44%, 1.3% and 1% respectively since baseline.

Table 6. Distribution of the VASLA members by source of energy

|  | Evaluation |
| --- | --- |
| Indicator | Baseline (n=682) | End line (n=511) |
| Source of energy for lighting |  |  |
| Wire Electricity | 10.0 | 12.2 |
| Generator Electricity | 1.2 | 0.8 |
| Solar Electricity* | 8.8 | 24.4 |
| Candle | 1.2 | 1.0 |
| Wood | 1.0 | 1.2 |
| Kerosene Lantern | 4.5 | 56.4 |
| Source of energy for cooking |  |  |
| Wood | 85.04 | 84.6 |
| Charcoal | 11.9 | 13.2 |
| Kerosene | 0.6 | 1.6 |
| Gas | 0.4 | 0.6 |
| Electricity | 0.1 | 0.0 |

* p<0.05 based on z-test for proportional differences

### 4.5.3 Type of toilet

Households using covered pit latrines rose from 34.6% at baseline to 48.8% at end line and those using uncovered pit latrines reduced from 59.1% at baseline to 45.6% at end line. Furthermore those without latrines decreased by 1%.  Generally, most of the carryover members had toilets constructed using tin material during baseline and final evaluation. The evaluation further established that no significant change occurred on use of other materials in toilet construction except cement blocks which registered a 3.8% increase. The results show significant improvement in latrine coverage among the carryover VSLA members which could be attributed to improved economic empowerment and participation in group based financial inclusion activities. The increased usage of latrine is likely to be associated with improvements in socio-economic status of the carryover.

#### Table 7. Distribution of the groups by toilet facility

| Indicator | Evaluation |
| --- | --- |
|  | Baseline (n=682) | End line (n=511) |
| Type of toilet |  |  |
| Flush Toilet | 1.0 | 1.6 |
| Covered Pit Latrine* | 34.6 | 48.8 |
| Uncover Pit Latrine | 59.1 | 45.6 |
| Composting Toilet | 0.9 | 0.6 |
| No Facility/Bush | 3.8 | 2.8 |
| Proportion sharing toilet | - | 45.9 |
| Material for toilet |  |  |
| Modern. Burnt Face Brick | 3.5 | 4.0 |
| Cement Blocks | 7.2 | 11.0 |
| Traditional Burnt Bricks | 2.0 | 3.0 |
| Stone | 8.9 | 9.0 |
| Wood/Mud | 2.5 | 3.0 |
| Tin Material | 69.6 | 69.0 |

* p<0.05 based on z-test for proportional differences

## 4.6 Assets

There was a significant increase (by 10.1%) in the number of carryover members who bought at least one asset in the last one year at the time of the baseline compared to the end line. Overall, the average number of assets owned by households increased. Of greater importance was the purchase of productive assets comprising of the livestock and agricultural tools/materials/equipment which increased among carryover groups. Purchase of more productive assets increased members’ capacity to earn more income.  Acquisition of other assets such as means of transport, electronics, household furniture, mobile phones and kitchen were also increased at end line compared with baseline. Land acquisition however remained constant among the carryover members. The average land ownership for carryover at end line was 3 acres denoting a 0.93 acre increase in land ownership since baseline.

##### Figure 2. Distribution of the groups by proportions purchasing assets

Livestock purchase minimally increased by 1.0%; acquisition of means of transport increased with a minimal margin of 1.5%; and electronic purchases increased minimally by 1.2%. There was however significant increase in the purchase of agricultural tools/materials equipment by 6.5% and kitchen ware by 6.1%. Household furniture also recorded a slight increase in proportions by 6.0%. Mobile phone acquisition increased by 2.7%. Increased access to productive assets had enabled VSLA participants to benefit from numerous business opportunities bringing in increased income from diversified sources.

#### Table 8. Distribution of the VSLA members by type of assets purchased

|  | Evaluation |
| --- | --- |
| Asset type | Baseline (n=370) | Final (n=330) |
| Livestock | 50.0 | 51.0 |
| Means Of Transportation | 7.6 | 9.1 |
| Electronics | 17.8 | 19.0 |
| Agricultural Tools/Materials And Equipment | 20.5 | 27.0 |
| Land | 3.2 | 3.2 |
| Jewellery | 7.6 | 4.0 |
| Household Furniture | 31.9 | 37.6 |
| Mobile Phone | 27.3 | 30.0 |
| Kitchen Ware | 54.1 | 60.1 |

* p<0.05 based on z-test for proportional differences

## 4.7 Leadership roles in VSLA

The evaluation results showed that involvement of carryover members in leadership roles in the saving groups had declined by 14.4% since baseline. This could be explained by the fact that leadership positions in VSLA are rotational and members can only serve for a period of time.

##### Figure 3. Distribution of the groups by VSLA involvement

## 4.8 Copying mechanisms

The evaluation assessed the ability of households to cope with ordinary bills and daily consumer items in the past 30 days. There was significant decline in proportion of households who reported “no difficulty” to cope by 5.5% margin. Further, majority of the members indicated their households were “somehow able” to cope at 72.2% presenting a 16.2% increase since baseline. Importantly, households that had a lot of problems to cope with bills and daily consumer requirements declined significantly by 10.4% (z-test>0, p<0.05) margin among the carryover members. This demonstrated improvement in livelihood stability among the carryover members largely attributable to project interventions.

##### Figure 4. Distribution of the groups by financial ability

## 4.9 Food Security and Agriculture

The final evaluation showed that carryover members recorded significant improvements in food production during the last one year of production. Key indicators of increased production included significant increase by 20.2% of households who reported adequate production during the previous harvest season to cover the food need of their household members until the current harvest; significant increase in percentage of households who considered their year’s harvest as good by 21.5% and significant decrease in households who reported their harvest to have been bad by 32.6%. The carryover members who received low harvest mentioned drought and flooding as the main causes of poor harvest.

#### Table 9. Distribution of groups by household food security and agricultural indicators

| Indicator | Evaluation |
| --- | --- |
|  | Baseline (n=682) | End line (n=511) |
| Adequate production in the last season* | 28.2 | 48.4 |
| Perception on harvest |  |  |
| Good* | 18.6 | 40.1 |
| Average | 23.9 | 34.9 |
| Bad | 57.3 | 24.7 |
| Reason for bad harvest |  |  |
| Drought | 8.3 | 59 |
| Flooding | 14.36 | 30 |
| Locust | - | 2 |
| Other | - | - |

* p<0.05 based on z-test for proportional differences

## 3.10 Food consumption

Members served diverse meals during the day before the special event. The composition of the meals served included milk, cereals, meals, poultry fish, vegetable, fruits and beans. Groundnuts were minimally consumed. In normal day milk, cereals and vegetables were widely consumed; the other foods were not consumed as much but were still widely embraced. Such foods included meat, fruits, beans and groundnuts across the groups. This pattern could be attributed to high cost of proteins and vegetables and therefore many households resorted to low cost food categories. About 49.9% of the Carryover members reported changes in quantity and quality of meals in the households. Further households missing meals had significantly reduced from 30% to 18.2% at end line. The improvement in household food consumption was likely contributed to by increased food production.

#### Table 10. Distribution of groups by food consumption pattern

|  | Evaluation |
| --- | --- |
| Food groups | Baseline (n=682) | End line (n=511) |
| Composition of meals during special days |  |  |
| Milk | 73.9 | 67.7 |
| Cereal (corn, millet, sorghum, rice, etc.) | 95.7 | 66.7 |
| Meat, poultry, fish | 47.8 | 66.7 |
| Vegetables | 65.2 | 100 |
| Fruits | 34.8 | 50 |
| Beans | 78.3 | 8.3 |
| Groundnuts | 26.1 | 33.3 |
| Food during normal days |  |  |
| Composition of meals |  |  |
| Milk | 74.5 | 71.7 |
| Cereal (corn, millet, sorghum, rice, etc.) | 81.2 | 86.8 |
| Meat, poultry, fish | 29.0 | 23.8 |
| Vegetables | 84.1 | 86.3 |
| Fruits | 34.1 | 24.4 |
| Beans | 34.1 | 45.1 |
| Groundnuts | 48.4 | 23.0 |
| Proportion missing a meal | 30.0 | 18.2 |

* p<0.05 based on z-test for proportional differences

# ECTION 5: RESULTS PART II: DESCRIPTIVE STATISTICS ON THE VSLA MEMBERS

## 5.1 Gender/Sex Composition

The assessment of carryover membership revealed that the majority were women compared to men.  Female members were reported at 89.0% accounting for a 16.4% increase since baseline. Male members were 11.0% at final compared to 27.4% at baseline.

## 5.2 Child rights

Majority of the carryover members were aware of child rights, 94.6% of them reported to be aware of child rights. When specific rights issues were assessed, the most widely known right issues were “right to education, health and food”. The members who knew these 3 right issues together with “right to be heard” significantly increased at end line by 19.6%, 10.8%, 2.6% and 15.8%  respectively. Other right issues did not record significant proportions among these groups. The number of VSLA members discussing child rights significantly decreased by 12.1%. This implies that the members may have ignored issues of child rights since the project did not put a lot of emphasis on it.

#### Table 11. Distribution of carryover groups by child right issues

| Indicator | Evaluation |
| --- | --- |
|  | Baseline (n=682) | End line (n=511) |
| VSLA member awareness on child right | 97.1 | 94.6 |
| Specific children rights VSLA member |  |  |
| Right To Education* | 40.46 | 60.1 |
| Health* | 40.75 | 51.6 |
| Food | 37.5 | 40.1 |
| Protection | 23.3 | 221 |
| To Be Heard* | 3.8 | 19.6 |
| To An Identity | 2.6 | 3.1 |
| Association | 1.23 | 2.1 |
| Participation | 1.1 | 1.1 |
| To Play | 6.47 | 7.1 |
| Proportion VSLA member discussing child right in the last 12 months | 70.8 | 58.7 |

* p<0.05 based on z-test for proportional differences

## 5.3 Income generation activities

Most discussants indicated they had some businesses before joining saving groups, although a number of them were not doing so well. The main business activities they engaged in included farming, selling of clothes and groceries. Prior to joining saving groups, members relied on their wages and salaries from their employment as a start-up capital. However by joining the groups, they got small loans to strengthen their business activities; they also have acquired business management skills through SPM and Financial education training. Through interactions, some members also acquired new skills and business ideas from their counterparts. All these support have contributed to business improvements thereby resulting to improved incomes.

Yes, since I joined the group and because I can borrow money from the group to boost my business so I have seen improvement because the income that I now get, the interest that I get from the shop has really gone up because of the loan that I get to boost the business. (R12, a female member of Kolunje teachers)

When I started my business, I had lots of management challenges but when I joined the BoC group, we got some related trainings and right now I can comfortably manage my business.( R4, a male member of Tujenge group)

The findings revealed that majority of carryover members (41.0%) were engaged in crop production reflecting a 17.9% increase since baseline. A reasonable proportion also engaged in self employment although at a decreased rate of 7.5% compared to baseline. About 7.5% of carryover members were engaged in petty trade.

#### Table 12. Distribution of carryover groups by main occupation of VSLA member

|  | Evaluation |
| --- | --- |
| Main Occupation | Baseline (n=682) | End line (n=511) |
| Student* | 0.6 | 13.1 |
| Domestic Work | 1.8 | 1.9 |
| Retired | 0.7 | 0.2 |
| No Occupation | 4.5 | 8.5 |
| Crop Production* | 27.1 | 41.0 |
| Agricultural Worker | 16.3 | 1.5 |
| Animal Husbandry | 0.1 | 0.0 |
| Dairy Farmer | 0 | 0.6 |
| Pastoralist | 0.1 | - |
| Fishing | 0.4 | - |
| Employee (Formal Sector) | 4.4 | 3.5 |
| Employee (Informal Sector) | 1.5 | 2.3 |
| Casual Labour | 3.4 | 4.4 |
| Works In Family Business | 6.5 | 0.8 |
| Self-Employed | 19.4 | 13.5 |
| Petty Trade | 7.3 | 7.5 |
| Making Handicrafts | 0.6 | 0.2 |
| Providing Services/Repairs | 1.8 | 0.8 |

* p<0.05 based on z-test for proportional differences

The final evaluation revealed that the proportion engaging in small business was 53%. A 15.5% decrease among those engaging in smaller businesses was recorded among these groups. On income generation activities, more members were engaged in commercial based activities as reported by 56% against 42% at baseline. Similarly more members were involved in the agricultural production as indicated by 22% at end line against 19.7%.  On food processing, there was minimal improvement among the members since baseline. Members were asked whether they had invested additional income into their IGAs in the last 12 months, 58% members affirmed they did compared to 41% at baseline. The carryover members who increased their profits in the last 12 months increased tremendously from 34.8% to 97.4%. In overall, BoC participants have increased their entrepreneurial activities as demonstrated by increased number of members engaging in income generation activities, increased number of households increasing their business funding and increased number of VSLA members reporting increased profits. The results are largely attributable to the project’s support in enterprise development training and coaching in IGAs.

#### Table 13. Distribution of carryover groups by proportion engaging in business and revenue based activities

| Indicator |  |  |
| --- | --- | --- |
|  | Baseline (n=682) | End line (n=511) |
| Proportion engaging in small business | 68.9 | 53.4 |
| Revenue based activities |  |  |
| Commercial* | 42.82 | 56.0 |
| Agri Production | 19.71 | 22.0 |
| Food Processing | 1.95 | 2.1 |
| Manufacture/Services | 35.04 | - |
| Proportion investing additional money* | 41.78 | 58.0 |
| Proportion realizing profit in the last 12 months* | 34.8 | 97.4 |

* p<0.05 based on z-test for proportional differences

Due to increased access to financial services provided by the saving groups, VSLA participants have used these resources to acquire new and or expand existing investments. The key investments options pursued by the members have revolved around acquisition of assets and enhancement of income generation activities. The evident importance of IGAs and the opportunities provided by the market for IGA participation is an important indicator of the potential relevance of promoting enterprise training which the project has emphasized over the years. The assets acquired, some productive some non-productive have all contributed to the wellbeing of the VSLA member’s household.

## 5.4 Control over own resources

The final evaluation revealed that 60% of carryover members reported to have control over their own IGA resources while 59.4% indicated to control produce from the field. These results revealed no significant difference since baseline (within 5% confidence interval). However, there appeared to be a decreasing trend among the carryover for both IGA and field resources control. These results show some decreased level of power in control of resources generated from investments and suggest the possibility of collective decision making at household level.

##### Figure 5 Distribution of groups by control over financial resources

Qualitative outcome from FGD participants also established that participation in BoC saving groups has been beneficial to individual members in diverse ways. Individuals have increased access to income which they freely use to meet their financial needs including making journeys, building own house. In addition, they now use the loans for restocking (cows, sheep and goats, poultry) and expansion of businesses. The groups have provided members with a place to save and peace of mind as they know that they have a source for emergency funds and loan funds should they require it. On employment creation, the saving groups have provided some members with capital to initiate their own businesses, thereby abandoning being a casual labourer.

Members of the carryover groups across the regions of the project area reported that their households had positively changed due to their participation in saving groups. As a result of increased access to basic financial services provided by the saving groups, the participants are able to meet their various household needs including paying school fees and buy educational requirements for their children, buy food, clothing, meet medical expenses and improve housing. Due to increased income streams at households, men and women now share financial responsibilities as women step in to support in meeting other household needs. Business investments created using loans from the VSLA are bringing in additional income which has greatly enhanced the household economy.

## 5.5 Access to financial services

About 67.5% contracted loans, although the result was statistically not different from the baseline finding. Further results on sources of loans revealed that self-help group was the most dominant source of loans with 84.5% reporting having contracted a loan from this source in the last 12 months. This compared favourably with those who received loans from the same source since baseline translating to a 37.2% increase. Other sources of loan recorded insignificant proportion. Members have benefited from the credit services offered by the VSLAs (self-help groups) and the majority, particularly women, have appreciated the opportunity to save and loan, have generally been satisfied with the security of their money, appreciate the incentive their VSLA offers to accumulate money in affordable amounts and the opportunity to get lump-sum pay outs with profits at the end of the cycle for consumption or investment. The flexible interest rates which ultimately contribute to building up the fund have made the VSLA more attractive than other sources of credit.

#### Table 14. Distribution of carryover groups by loan contracted and source

|  | Evaluation |
| --- | --- |
| Indicator | Baseline (n=682) | End line (n=511) |
| Proportion contracting any loan | 74.8 | 67.5 |
| Source of Loan (n=1159) |  |  |
| Private Bank | 1.97 | 3.9 |
| Private Bank | 0.51 | 1.5 |
| Money-Lender/ Shop Keeper | 0 | 0.9 |
| Self-Help Group* | 46.52 | 83.7 |
| Family/ Friend/ Neighbour | 0.34 | 0..3 |
| Micro-Finance Institution | 2.45 | 4.2 |
| Whole-Sale/ Crop Buyer | 0.34 | 0.0 |
| Whole-Sale/ Crop Buyer | 0 | 0.0 |

* p<0.05 based on z-test for proportional differences

The results further showed that the average loan amount contracted in the past one year was Ksh. 11,681.3 against Kshs. 6,913.9 per member at baseline. Generally  this  outcome  reveal  significant  increase  in  amounts  of loan contracted which is a pointer to increased loan repayment capacity among the members and  increased confidence  in the VSLA as a reliable source of financial services especially credit to its members.

##### Figure 6 Distribution of groups by average loan amount acquired

According to the FGD discussants through participation in BoC savings groups, their lives together with their households have tremendously changed. With access to small loans members are to pay school fees for their children, acquire household furniture, buy farm inputs such as certified seeds and fertilizers to maximize their farming activities, others reported meeting their hospital bills with ease unlike in the past. Apart from meeting household needs, loans have been used to acquire more stock so as to expand existing businesses.

Moreover groups have helped build cohesion among the members, sharing of information and ideas have also been a social benefit of such groups. By accessing small loans from the groups, some members have managed to meet most of their household needs such that they no longer have to depend on others for assistance.

The changes that have been reported at household levels are largely attributable to the BoC project according to majority of the FGD discussants. Because of fear of formal financial institutions due to their high interest rates and inflexible repayment terms, the project participants indicated that their GS&L groups were the main source of loans since the terms were friendly to the members. Through the project, GS&L groups have filled the gap by providing members with credit they would otherwise not have access to. The savings and loans activities give members economic options they often lack and enable them to afford health care, take their children to school and put food on the table.

Analysis of the saving tools revealed that more carryover members are now saving with the VSLA/Self- help group (56.6%) at end line than it was at baseline (28.6%). The other important avenues for saving were the private and government banks which registered increments at 6.5% and 1.1% since baseline respectively. These results reveal that saving with both private and government banks is gradually gaining popularity as the project supported groups to be linked to formal financial institutions.

#### Table 15. Distribution of carryover groups by saving tools

|  | Evaluation |
| --- | --- |
| Loan item | Baseline (n=682) | End line (n=511) |
| Savings tools |  |  |
| Private bank | 3.65 | 10.2 |
| Government bank | 5.2 | 6.3 |
| Micro finance institution | 0.85 | 0.9 |
| VSLA/Self Help* | 28.6 | 56.6 |
| ROSCA | 0.5 | 0.1 |
| Sacco | 0.65 | 0.71 |
| Keep with relative/family | 0.15 | 0.1 |
| In the house, | 4 | 0.0 |
| Farmer association | 0.05 | 0.0 |
| Cooperative | 0.2 | 0.1 |
| Keep with local traders | 0.65 | 0.1 |

* p<0.05 based on z-test for proportional differences

In terms of use of loans the evaluation revealed a similar pattern as was at baseline where school fees, livestock purchase and agri-input /seed were the most dominant uses of contracted loans. Use of loans to pay school fees increased by 6.3%, livestock purchase remained at higher proportion although had decreased by 8.2% since baseline. Agri input /seed registered a 7.0 % increase among the members. Other uses of loan were not significant.

#### Table 16. Distribution of groups by use of loans

|  | Evaluation |
| --- | --- |
| Use of loan | Baseline (n=682) | End line (n=511) |
| Housing | 3.9 | 2.9 |
| Livestock | 48.1 | 39.9 |
| Business Capital (IGA) | 2.17 | 5.6 |
| Bought Land/Farm | 0.52 | 0.5 |
| Bought Utensils/Furniture | 1.86 | 0.5 |
| Children’s School Fees | 18.3 | 24.9 |
| Bought Food | 4 | 1.7 |
| Medical Expenses | 1.87 | 1.6 |
| Clothing | 0.69 | 0.6 |
| Funeral | 1.13 | 0.0 |
| Agri. Input/Seed* | 3.9 | 10.9 |

* p<0.05 based on z-test for proportional differences

FGD findings revealed that there are indications that participation in BoC has provided members with opportunities to diversify livelihoods and income generation strategies from loans offered through the saving groups. Members have used loans from the GS&L groups to undertake or expand their current income generating activities as they now have the lump sums to do so. Some members have bought more stock for their kiosks while others have used group loans to pay school tuition fees, buy food and clothes for family members and themselves, lease larger pieces of land for farming and purchase of seeds and fertilizers for planting. Apart from diversifying income generation activities, the groups have diversified livelihoods as members have used social funds for emergencies.

## 5.6 Factors to consider before taking a loan

The final evaluation revealed that majority of carryover members considered the cost/interest rate at 50%, when to pay the loan at 42% and how to pay at 62.9% when taking loans. Other factors were insignificant. No significant change was noted on the factors at end line in comparison with the baseline values.

#### Table 17. Distribution of carryover groups by factors to consider when taking a loan

|  | Evaluation |
| --- | --- |
| Loan Item | Baseline (n=682) | End line (n=511) |
| The Cost/Interest Rate | 49.8 | 50.0 |
| When Do I Need To Pay | 43.3 | 42.0 |
| How Will I Pay | 62.9 | 59.0 |
| What Will Happen If I Don’t Pay | 11.6 | 11.0 |
| Administrative Procedures | 4.5 | 3.7 |
| Collateral | 4.3 | 3.8 |
| Reputation of the Lender | 3.1 | 10.0 |
| Length of the Grace Period | 15.3 | 20 |

* p<0.05 based on z-test for proportional differences

## 5.7 Proportion correctly identifying correct loan deal

When the respondents were asked whether they knew what constituted a good loan deal, fewer carryover members selected loan two (40.6%) denoting a 10.3% decrease since baseline. Members’ understanding of some aspects of financial education was still low as exhibited by decrease in understanding of what constitute a good loan.

#### 18. Distribution of carryover groups by proportion correctly identifying a good loan facility

| Indicator | Evaluation |
| --- | --- |
| Loan Item | Baseline (n=682) | End line (n=511) |
| Loan One | 34.8 | 38.0 |
| Loan Two* | 50.4 | 40.6 |
| Don’t Know | 14.7 | 20.6 |

* p<0.05 based on z-test for proportional differences

## 5.8Investments and Household Support

### 5.8.1 Asset acquisition/purchase

More carryover members acquired assets at end line (64.4%) as compared to baseline period (54.3%) reflecting a 10.1% increase. The most widely purchased assets were kitchen ware, livestock, household furniture, mobile phones and agricultural tools/materials. Purchase of mobile phones increased by 2.7%; Acquisition of means of transport had no significant change; Purchase of electronic increased by 1.2%; Purchase of agricultural tools increased by 2.3%; Land purchase increased by 1.0%; and a slight increase of 2.4% was recorded for household furniture purchase.

#### Table 19. Distribution of carryover groups by asset acquired in the last 12 months

|  | Evaluation |
| --- | --- |
| Indicator | Carryover (n=370) | Final N=322 |
| Purchase of asset in the last | 54.3 | 64.4 |
| Asset purchased in the last 12 months |  |  |
| Livestock | 50.0 | 51.0 |
| Means of Transportation | 7.6 | 9.1 |
| Electronics | 17.8 | 19.0 |
| Agricultural Tools/Materials And Equipment | 20.5 | 27.0 |
| Land | 3.2 | 3.2 |
| Jewellery | 7.6 | 4.0 |
| Household Furniture | 31.9 | 37.6 |
| Mobile Phone | 27.3 | 30.0 |
| Kitchen Ware | 54.1 | 60.1 |

Through interactions with other members of the community, the saving group members have managed to convince many people including friends, relatives and neighbours to join the saving groups. In most cases the benefits of savings groups was shared with non-members through open talks. Some members convinced their spouses to join so that they would benefit together as a family.  The most influencing part however has been the investments undertaken by the members which have been very compelling and attractive to the non-members. Acquisition of physical assets and improvement of housing by the group participants were some of the benefits that easily attracted non-members who would eventually enquire how they could become members of a savings group. The big pay out at the end of the cycle (during share out) to group members was equally exciting to non-members.

The Carryover groups trained under BoC programme have gained easy access to basic financial services including savings, insurance (social fund) and loans. Participants of the BoC saving groups attribute most of the economic success to these groups since they not only benefit from the financial services but also knowledge and information sharing amongst the members. Through social interactions and exchange of ideas, some members have learnt new farming technologies from their colleagues. Moreover the accumulated savings received at share out at the end of the cycle has been beneficial to members in starting up new businesses, expanding existing businesses and acquiring of useful houseful assets.

### 5.8.2 Cost of housing and house improvement

The final evaluation revealed that significant contributions were being made by carryover members towards payment of housing rent and improvement of their housing. On average, the monthly rent for most of the YSLA members had increased from Kshs.3000 at baseline to Ksh. 4905 at final evaluation. On average the monthly rent for most of the carryover members had increased from Kshs.1365 at baseline to Kshs. 2054 at end line. In terms of personal contribution towards housing rent, the carryover members contributed Kshs. 1671 at end line against Kshs. 1104 during baseline. There is increased investment in housing as showed by increased contribution towards housing improvement from Kshs. 15,331 at baseline to Kshs. 29, 343 at final evaluation. The results demonstrate increased expenditure in payment of rent and improvement of housing by the carryover members as well as their increasing role in meeting household needs.

##### Figure 7 Distribution of groups by cost of housing and house improvement loan amount acquired

### 5.8.3 Type of improvements

The main household improvements were made on roof, floor, wall, toilet and additional room. Carryover groups had 37.1% of the members who improved their roofs against 34.34% since baseline. Again 23.0 % improved floor against 20% since baseline.  About 18% improved wall against 15.62% at baseline, while 11.0% had additional rooms against 15.62% at baseline against 6.9% at baseline. Increased financial resources available to members through saving groups enabled them to improve their housing and living conditions in general.

##### Figure 8 Distribution of groups by type of house improvement

## 5.9 Education (on themselves/ other household members)

More carryover members spent money on their own education at end line (77%) compared to 67.4 % at baseline. There was however no significant change among those who spent money on other household members’ education. More investments were being made on education for self than other members of households as demonstrated by these results. Average money spent on self education was kshs 48,648 against kshs 25,767 since baseline. Concerning other members’ education the carryover members spent kshs 39, 3316 against 21,737 at baseline.

##### Table 9. Average money spent on self-education and education of others

When the nature of education related expenditure was considered, the bulk of expenditure went to school fee, books and uniforms. Among the carryover, significant proportion of the members purchasing books, paying school fees and purchasing school uniforms increased by 7.9%, 16.2 and 23.45% respectively. Increased investments in education were indication that the incomes of the members had improved.

#### Table 20. Distribution of carryover groups by education expanses

|  | Evaluation |
| --- | --- |
| Education expense item | Baseline (n=682) | End line (n=511) |
| Proportion making expenses on self education* | 40.2 | 67.4 |
| Proportion making expenses on education of other people | 79.9 | 77.0 |
| Type of expenses |  |  |
| School Fees* | 18.75 | 35.0 |
| Uniforms* | 17.55 | 41.0 |
| Books | 10.1 | 18.0 |
| Transport | 1.4 | 5.7 |
| School Kit | 1.35 | 2.0 |
| Accommodation | 0.9 | 0.0 |

* p<0.05 based on z-test for proportional differences

## 5.10  Medical expenses and access to health services

The evaluation revealed a decrease in members’ expenditure on medical bills for self and other family members, although the members reporting not able to access medical services had decreased from 38.8% to 24.3% at end line. A 3% decrease was noted on medical expenses for self while 8.4% decrease was reported among those members spending money on health care for other family members.

#### Table 21. Distribution of carryover groups by medical expanses

|  | Evaluation |
| --- | --- |
| Indicator | Baseline (n=682) | End line (n=511) |
| Proportion making personal medical expenses | 71.7 | 69.3 |
| Proportion making medical expenses on other people | 77.4 | 68.6 |
| Members not able to access medical services* | 38.8 | 24.3 |

More financial resources were spent on other family members’ medical expenses by carryover groups at Kshs. 23,205 against Kshs. 10,325 at baseline. Significant decreases were further realized on the medical expenditures for self with carryover spending averagely Kshs 18,786 against Kshs 52,123 at baseline.

These results reveal  that heavy  expenditure  on  health bills significantly  reduced  for  both self  and other  family members among carryover  members. This could be attributed to improved health status of the members as a result of increased access to food and increased adoption of appropriate health seeking behaviour.

##### Figure 10. Distribution of groups by average amount spent in medical expenses

## 5.11 Clothing

The evaluation established that the average yearly expenditure on clothes for self among carryover members had increased to Kshs. 20,407 against Kshs. 14,506 at baseline. Likewise the average annual expenditures on clothing for other household members had improved to Kshs. 24,110 against Kshs. 11,839 at baseline. There is evidence of increased investment in clothing among the carryover members based on t-test, which is largely attributable to increased economic empowerment arising from their participation in saving groups.

##### Figure 11 Distribution of groups by average amount spent in clothing

## 5.12 Household events

The evaluation established that 72.4 % of carryover members against 71.1% spent money on special events registering a slight increase since baseline (1.7%).The results revealed increased expenditures on special events since baseline.

##### Figure 12. Proportion spending money on special events

## 5.13 Financial Literacy and Business Skills

### 5.13.1 Business skills

The final evaluation assessed the level of adoption of business skills acquired by VSLA members since the baseline. The findings focusing on record keeping revealed that 40.8% of the carryover members kept records against 43.2% at baseline recording a 2.4 % decrease. The most widely kept records were sales (39.0%), income (31.5%) and expenditures (25.0%). Incremental changes were noted for sales, income and expenditures records at 6.1%, 6.9% and 0.3% respectively. These results show improvements in adoption of good business management practices acquired through business trainings provided by the BoC project.  The final evaluation further revealed that carryover groups registered decreasing trend in having written budgets for their businesses. About 32.2% of carryover groups kept a written budget against 44.1 % at baseline, representing an 11.9% decrease.

#### Table 22. Distribution of carryover groups by financial literacy and business skills

|  | Evaluation |
| --- | --- |
| Indicator | Baseline (n=682) | End line (n=511) |
| VSLA members keeping record | 43.2 | 40.8 |
| Type of record |  |  |
| Sales | 32.9 | 39.0 |
| Goods/Raw Materials | 12.8 | 12.1 |
| Income | 24.65 | 31.5 |
| Expenditures | 24.7 | 25.0 |
| Frequency of record keeping |  |  |
| Daily | 49.7 | 42.7 |
| Weekly | 35.9 | 37.3 |
| Monthly | 9.9 | 13.6 |
| Proportion with a written budget | 44.1 | 32.2 |

* p<0.05 based on z-test for proportional differences

Saving group members reported changes in the way they manage their businesses now compared to how they used to do it before BoC Project came. The positive changes are largely attributable to business management training offered by the project which incorporated such aspects as Selection, Planning and Management (SPM) and Financial Education training which equipped the participants with requisite skills and knowledge on how to start, run and manage small businesses. The group members also gained knowledge on how to keep records, do financial plans and budgets; all these have helped members do their business activities successfully. Access to credit and saving services courtesy of saving groups has equally been useful in providing crucial financial services to entrepreneurs thereby making their businesses to flourish.

### 5.13.3 Factors of business set and elements of setting price

More carryover members are knowledgeable now about the elements they should consider while setting prices for their goods as shown by the increased proportions of respondents since baseline who mentioned cost of raw material (1.6%) transportation (7.2%) my time (1.65%) and market price (7.1%). With regard to factors to consider before engaging in business increased numbers were noted on the investments you have to make to start and run business (0.9%), area offering the same service or good (3.6%); availability of credit (0.3%); my skill/passion (0.1%). In overall more carryover members have increased knowledge in price setting for commodities and setting up of businesses than at baseline.

#### Table 23. Distribution of carryover groups by elements of setting price and factors in business set up

|  | Evaluation |
| --- | --- |
| Indicator | Baseline (n=682) | End line (n=511) |
| Elements of setting price |  |  |
| Cost of raw material | 11.4 | 13.0 |
| Transportation | 10.8 | 18.0 |
| Paid labor | 5.6 | 5.0 |
| My time/labor | 8.35 | 10.0 |
| Market price* | 13.86 | 21.0 |
| Factors for business set up |  |  |
| Investments you have to make to start and run your business | 18.1 | 19.0 |
| How many people want to buy Your service/ good | 22.7 | 23.1 |
| Area offer the same service/ good | 15.4 | 19.0 |
| How much money you can earn through that business | 21.8 | 20.7 |
| Availability of credit | 4.8 | 5.1 |
| Having enough friends/relatives that can help you to run the business | 3.2 | 2.1 |
| My skill/passion | 8.9 | 9.0 |
| Knowing someone who has been successful with the same business | 5.0 | 4.2 |

* p<0.05 based on z-test for proportional differences

## 5.14 Financial Anxiety & Self Esteem

### 5.14.1 Financial anxiety

The results show that members who constantly got worried about money increased by 5.1% for carryover groups. Similarly those that frequently got worried about finances increased by 4% for carryover. On the contrary, members who rarely and never worried about money decreased since baseline. The increased financial anxiety among the carryover members could be attributable to increased financial demands on the members occasioned by their expanding roles in their households and community.

##### Figure 13. Distribution of the groups by financial anxiety

### 5.14.2 Self-image

Seven indicators were used to asses self image of carryover members both at baseline and final evaluation. The average mean score for carryover groups at final evaluation was 3.23.  Further, all the mean scores were higher than the 2.5 expected average score, and thus carryover reported 14.6 % higher than  the minimum expected mean score. However, based on Wilcoxon W test, all the self image indicators registered significant increase at final evaluation except for the spouse influence. The results are attributable to the project’s interventions which economically empowered the members thus enhancing their self-image and esteem.

#### Table 24. Distribution of carryover groups carryover groups by self esteem

|  | Evaluation |  |
| --- | --- | --- |
| Self Image Indicators | End line (n=511) | Baseline (n=682) | Wilcoxon W |
| I can resolve problems on my own | 2.75 | 3.27 | 245773.5* |
| If somebody opposes me, usually I can find a way to get what I want | 2.81 | 3.20 | 255298.5* |
| I always find some way to deal with problems that confront me | 3.19 | 3.31 | 255872.0* |
| I can influence my spouse’s decision making | 4.55 | 4.61 | 285102.0 |
| I can take action to improve my life | 3.26 | 3.58 | 251846.0* |
| I can influence important decisions in my community | 2.88 | 3.27 | 251846.0* |
| I am confident to speak in community meetings | 3.09 | 3.35 | 270563.0* |

* p<0.05 based on Wilcoxon W effect size

In order to establish the real source of decrease on average mean scores for self image indicators, principal axis factoring was performed to generate expected communalities (variance explained) for each indicator. The entire indicator items were subjected to one factor output and result revealed specific sources of decrease. Carryover groups registered improvements on key items defining self image. All the indicators recorded a positive variance increase except for ability to take action to improve life. This  decrease  may have  been pulled by the dependency  on spouse  decision  making verdict given  that the item is influencing spouse decision which recorded insignificant variance and explained by self-esteem factor.

##### Figure 14 Level of communalities for key elements of self esteem

## 5.15 Participation & Social Position

### 5.15.1 Participation

Membership to any community based associations, network, political party or religious association had reduced since baseline among the carryover members by 7.7%. However incremental changes were reported on membership in political party (1.1%), religious association (0.2%) and young mothers club by 49.7% since baseline. The voting pattern (in terms who voted and who determined the voting pattern) remained within the same proportions as was at baseline.  Interestingly, members planning to run for a civic post in 2017 general election significantly increased among the carryover by 49.1% respectively, denoting increased interests in political activity. Moreover, carryover members participating in conflict resolution increased by 21.2% since baseline.

#### Table 25. Distribution of the carryover groups by participation

|  | Evaluation |
| --- | --- |
| Indicator | Baseline (n=682) | End line (n=511) |
| Membership of any community based associations | 41.5 | 33.8 |
| Association type |  |  |
| Political Party | 0.6 | 1.7 |
| Religious | 25.8 | 26.0 |
| Farmer Association | 9.1 | 5.8 |
| School Association | 2.6 | 1.2 |
| Health Club | 1.5 | 1.22 |
| Young Mother Club | 12.3 | 62.0 |
| Member who voted 2013 | 94.1 | 94.0 |
| Who determine the voting pattern |  |  |
| Myself | 96.9 | 94.3 |
| My Spouse | 0.9 | 2.1 |
| Village Chief | 0.5 | 0.0 |
| The Party | 0.5 | 1.3 |
| Members planning to run for civic post in 2017* | 10.4 | 42.5 |
| Members expressing opinion on public | 51.0 | 46.8 |
| Community conflict resolution | 39.6 | 60.8 |

* p<0.05 based on z-test for proportional differences

At group level, the programme has enhanced members’ experience and knowledge of leadership structures and most of the leaders reported that self-confidence is increasing among members and new leaders are emerging for future roles. Ordinary members showed high level of confidence and self-esteem during the interactions with the evaluation team. Saving group participants have reported significant changes in their households’ members’ wellbeing, assets ownership and the businesses they manage and run.

Participation in the saving group has had a wide range of benefits to members including sharing and exchanging of new ideas. It is a source of unity among members. Saving groups have encouraged self-reliance and participation in income generation activities among members. One of the objectives of BoC programme is to create self-reliance through income generation activities. There are indications that the programme is achieving this objective. As opposed to attitudes before the BoC groups, individuals are discussing how best to initiate group and develop group or individual income generating activities and some are already doing so. Members are now engaging in beneficial work as opposed to being idle as they used to be before; others have become more focused and hardworking to pursue their financial plans.

### 5.15.2 Social Position

The evaluation measured members’ perception on their social position in the community based on five selected indicators of change. Just as was at baseline, carryover group members recorded relatively higher mean scores for household level indicators that touched on relationship with the spouse. The members reported that “my spouse shows me respect” (at a mean of 3.53) and “my spouse values my role in the household” (at a mean of 3.56) with some significant decrease.

#### Table 26. Distribution of the carryover groups by social position

|  | Evaluation |  |
| --- | --- | --- |
| Indicator | Baseline (n=682) | End line (n=511) | Wilcoxon W test |
| My spouse shows me respect | 3.81 | 3.53 | 283009.5* |
| My spouse values my role in the household | 3.81 | 3.56 | 284954.5* |
| Other members of the extended family show me respect | 3.64 | 3.41 | 260955.0* |
| People in the community ask and value my opinion | 3.39 | 3.02 | 253852.5* |
| People in the community respect me | 3.58 | 3.20 | 253312.5* |

* p<0.05 based on Wilcoxon W effect size

The saving group members’ perceived improvement in social position is being felt most at household level than in the community. Further inferential analysis based on Wilcoxon W test revealed significant decline since baseline. This decrease signifies a fading economic and social power gained during the project interventions.

# SECTION 6: ASSESSMENT OF KEY BOC INDICATORS

In reference to the project’s design, the evaluation assessed progress of key project indicators since baseline. The total number of carryover beneficiaries reached attained a negative variance of -5.71% signifying below performance. While the total number of <35 years old attained positive variance of 32.47% implying that the project had surpassed its target. The cumulative savings for the groups stood at USD 319, 939, while total loans outstanding stood at USD 470, 404. The female membership stood at 70.6%. In terms of additional trainings, members who completed financial literacy registered a negative variance of -11.41% while those completing enterprise skills training registered a negative variance of -54.57%. Advanced business training had a positive variance of 0.05% implying full attainment of target. The findings of the evaluation indicate general progress in overall project performance. There were however different degrees of progress, impact and effectiveness in the specific components.

#### Table 27 Summary of project progress

| Project Indicator | Targets | Achievements | Variance |
| --- | --- | --- | --- |
| Total number of carryover beneficiaries | 33,073 | 31,186 | -5.71 |
| Total number of <35 olds in carryover groups: | 12,898 | 17,086 | 32.47 |
| Total amount of cumulative savings (carryover groups) in USD | N/A | 319,939 | - |
| Total amount of cumulative loans outstanding in USD (carryover groups) | N/A | 470,404 | - |
| % of female members – carryover groups: | N/A | 70.6% | -! |
| Total number of carryover group members completing financial literacy / financial skills training | 33,073 | 29,300 | -11.41 |
| Total number of carryover group members completing enterprise skills training (SPM) | 22,702 | 10,313 | -54.57 |
| Total number of carryover group members completing advanced business skills training | 3,902 | 3,904 | 0.05 |

# SECTION 7: CONCLUSION AND RECOMMENDATION

## 7.1 Conclusion

The evaluation portray mixed results with incremental performance and changes noted on such indicators as food production, investment and entrepreneurial activities, joint and member participation in decision making, purchase of assets, expenditure on special events and self-image. Low performance however was noted on keeping of business records, financial anxiety and civil society participation.

There’s increased engagement in income generating activities among carryover members as demonstrated by reduced proportion of members with no occupation, increased number of households increasing their business funding and increased number of members reporting increased profits, increased proportion of members involved in entrepreneurial activities including agriculture and fishing and employment both in formal and informal sectors. Moreover, members have increased knowledge in price setting for commodities and setting up of businesses than at baseline.

Generally there’s increased involvement of the carryover members in household decision making on financial expenses allocation either as individual or and through consultation with the spouse. There was increment in proportion of carryover members who reported improvements in coping mechanisms with financial difficulties, bills and daily consumer requirements.

More carryover members bought at least one asset in the last one year at the time of the baseline compared to the end line. The average number of assets owned increased during the project life. There’s improvement in contribution made by carryover members towards payment of housing rent and improvement of their housing.

The carryover members recorded significant improvements in food production as demonstrated by increase in proportion of households who produced enough harvests during the previous harvest season to cover the food need of their household members until the current harvest; increase in percentage of households who considered their year’s harvest as good and significant decrease in households who reported their harvest to have been bad.

Increase in uptake and utilization of financial services has been reported among the carryover members as shown by more members accessing credit from saving groups; substantial increase in average loan amount contracted in the last one year. Analysis of the saving tools revealed that more carryover members are now saving with the VSLA/Self- help group at end line than it was at baseline.

## 7.2 Recommendation

- The evaluation noted capacity gaps in the management and running of some saving groups thereby resulting to issues of default, mismanagement and misunderstanding among the membership. Future interventions should put more emphasis in strengthening governance and management structures of the VSLA groups. Quality monitoring and mentoring should be reinforced to guarantee sustained operations of the groups beyond project period;

- Agriculture has stood out as a key livelihood activity for most of the VSLA members because of its viability in the rural settings where the smallholder farmers reside. The VSLA is already providing finances for agricultural investment, what is missing however is quality agricultural extension support so as to achieve increased production and productivity. Strategic areas to be prioritized should include among others value addition and urban agriculture.  Strengthened linkages with relevant Government departments, agencies and private sector players will be crucial in achieving this objective.

- Although VSLA had become reliable sources of financial services to the members, they were not panacea to all the financial needs of the members. Linkage to formal financial services remains a major requirement and need which should be deepened to reach more groups. Future projects should work with formal financial institutions that already have partnerships with CARE on negotiated financial products. Such institutions include Barclays, Post bank and Equity banks.

# REFERENCE

- Singer, Jennifer. n.d. Board Briefing Note:  Backgrounder on GS&Ls. Toronto, Canada:  The Mastercard Foundation. http://www.themastercardfoundation.org/pdfs/GS&L_Website_Brief.pdf. Accessed December 2012

- Banking on Change Synthesized report from Country Office to PPMG

- VSL Associates website. Homepage: The VS&L Methodology. http://www.vsla.net/

- CARE Kenya (2010). A sustainable economic empowerment for Women Enterprise: A proposal for the Cherie Blair Foundation for Women

- Banking on Change Synthesized report from Country Office to PPMG

- Ritchie J & Spencer L (1994). Qualitative data analysis for applied policy research. In Analysing Qualitative Data, pp. 173–194 [A Bryman and RG Burgess, editors]. London: Routledge.

# ANNEXES

## Annex 1:  HH Survey tool

## Annex 2: FGD guide

## Annex 3: ToR

# Footnotes

http://www.progressoutofpoverty.org/

Ritchie J & Spencer L (1994). Qualitative data analysis for applied policy research. In Analysing Qualitative Data, pp. 173–194 [A Bryman and RG Burgess, editors]. London: Routledge.

# Text boxes

Carryover Groups baseline (Pre-test)

BoC intervention Package

Final evaluation (post-test)

Full group Impact/change

Yeah, apart from investing in my business, I have also built my house out of the money that I borrowed from the group. (R3, a male member of Tujijenge group)

Out of the loan I got from the group, I used it to buy a posho-mill that generates money for me and am very happy about it. (R3, a member of Kathageri group)

DDO

I am now very comfortable at home because I have managed to clothe my family, buy food, and pay hospital bills and school fees courtesy of the GS&L group. (R3, a male member of Kolunje Teachers group)

The group has helped me a lot. I live alone since I don’t have a husband. Whenever I get the small loans I usually buy iron sheets bit by bit and now I’m almost starting to build a house because I have bought most of the building materials. (R1, a female member of Lovely Sisters Carryover group)

I personally invest some of it in farming. I also use some to take care of my parents who are old and need to be looked after. I also ensure that my family and my house are well taken care of. I take some of the money to the bank too where I can get it in case it is time for farming and there are requirements that I need such as seedlings, fertilizers and even labour. So that is how I use my money. (R4, a male (Carryover) member of YagoKotieno Group)

It has changed my life because before I used to solely depend on my husband for money for food. But, now I can buy food on my own and when he comes home, he would find I have already prepared food. Also before I only used to have one business, but, now I have been able to open up other businesses too (R5, a female member of Hope in Storm, Carryover)

If I had not joined GS&L group I would borrow money from my friends and to convince them to lend me, I would promise to give it back with interest. This however, cannot be compared with the benefit of being in a group where you get loans without much struggle. (R5, a male member of WeyoTek, Carryover)

I am now very comfortable at home because I have managed to clothe my family, buy food, and pay hospital bills and school fees courtesy of the GS&L group. (R3, a male member of Kolunje Teachers group)

The group has helped me a lot. I live alone since I don’t have a husband. Whenever I get the small loans I usually buy iron sheets bit by bit and now I’m almost starting to build a house because I have bought most of the building materials. (R1, a female member of Lovely Sisters Carryover group)

I was able to convince a friend to join. I used to stay in a grass thatched house and later built a better house. When my friend saw this, he asked how I had been able to do that and I explained it to him. Later on he came and joined the savings and loans group.  (R2, a male member of Carryover)

Now we are able to plan and manage our businesses well. There was a period I would make a thousand shillings from my business and spend it all at the bar. Now I am able to know the importance of saving some of the money even if I have to use a bit of it. All this is because of the training I have had from CARE Kenya who taught me of the importance of saving. Business is doing well and I am now able to take my children to school with ease, and also pay medical bills. (R5, male member of YagoKotieno, Carryover)

There is a big difference since we joined GS&L, we can dress well, we can be presentable, and these days we are almost reaching the standard of teachers in the village. This money has changed our lives and now we are good women. (R4, Lovely sisters, carryover group)

I feel very secure and I have got companionship as a result of being a member of this group. We can share ideas with friends because the friends are there. (R1, a female member of Kolunje Teachers)

Since I joined this group I think I’m valued because I can even assist my friends because we have got savings and loaning here, so if they have got a problem, they can approach me then I extend to them the services that I get from the group. (R7, a male member of Kolunje Teachers)