# COMMUNITY SERVICES AND EDUCATION IN MTENDELI AND NDUTA CAMPS (KIBONDO, TANZANIA)

2001-2003

PROJECT RAPID ASSESSMENT REPORT

&

KARAGO AND KANEMBWA CAMPS BASELINE INFORMATION

Prepared by:

Devocatus Kamara (devocatus_kamara@wvi.org)

&

Dr.Yosh Kasilima (yosh_kasilima@wvi.org)

WVT-Consultancy Services Center

December,2003.

## Table of Contents

Table of Contents	2

Abbreviations	4

Acknowledgements	5

Executive Summary	6

1.0	Introduction	11

2. Methodology	15

3. Accomplishment/strengths/weaknesses & challenges	16

3.1 Education	16

3.1.1 Accomplishment	16

3.1.2 Success/Strength	17

3.1.3 Weakness and Challenges	18

3.1.4 Recommendations	19

3.2 Youth Sports and Culture/Peace and reconciliation	20

3.2.1 Accomplishments	20

3.2.2 Successes /Strengths	21

3.2.3 Weaknesses and Challenges	21

3.2.4 Recommendation	22

3.3 SGBV, HIV/AIDS and Gender	22

3.3.2 Successes /Strengths	23

3.3.3 Weakness and Challenges	24

3.4 Micro Project	25

3.4.1 Accomplishment	25

3.4.2 Successes/ Strengths	25

3.4.3	Weaknesses  & Challenges	26

3.5 Support to Vulnerable	28

3.5.1 Accomplishment	28

3.5.2 Successes /Strengths	29

3.5.3 Weaknesses and Challenges	29

3.5.4 Recommendations	30

3.6 Capacity Building	31

3.6.1 Accomplishment	31

3.6.2 Successes/ Strengths	32

3.6.3 Weakness and Challenges	32

Recommendations	33

4. Project Management	33

5. Best practices/Lesson learned	35

# List of Tables

Table 1: Refugee Camp Population (2000 – 2003)

Table 2: Micro Project Beneficiaries by Category- Mtendeli Camp

Table 3: Trend of Micro Project Supported – Mtendeli Camp

Table 4: SAEU Staff Capacity Building

Table 5: Integration of Vulnerable in Micro Projects – Nduta Camp

Table 6: Loan Repayment Rate Nduta & Mtendeli Micro Project Group

Table 7: Supported Vulnerable by Category since 2001.

Table 8: Facilitated & Voluntary Repatriation Trend By Camp

Table 9: Trend of Groups Supporting Vulnerable – Mtendeli Camp

Table 10: Primary Schools Parameters (2000 – 2003)

Table 11: Teacher: Pupil Ratio – Nduta Camp

Table 12: Teacher: Pupil Ratio – Mtendeli Camp

Table 13 :Grade I Enrolment rate – Nduta Camp

Table 14: Grade I Enrolment rate – Mtendeli Camp

Table 15: School Infra-structures

Table 16: Secondary School Parameters (2000-2003)

Table 17: Gender and Development

Table 18: Baseline Information – Karago Camp

Table 19: Baseline Information – Kanembwa Camp

Fig 1: Map of project Location

## Abbreviations

AM		Attached/Accompanied Minor

AIDS		Acquire Immune Deficiency Syndrome

CSO		Community Service Officer

CSW		Community Social Worker

DRA		Dutch Relief & Rehabilitation Agency

HIV		Human Immunodeficiency Virus

IRC		International Rescue  Committee

LFA		Logical Framework Analysis

MHA		Ministry of Home Affairs

NFE		Non Formal Education

SAEU		Southern Africa Extension  Unit

SGBV		Sexual and Gender Based Violence

TOT		Training of Trainers

TRCS		Tanzania Red Cross Society

PC		Program/Project Coordinator

UNHCR	United Nations High Commission for Refugees

UNICEF	United Nations Children’s Fund

UAM		Unaccompanied Minors

WFP		World Food Program

# Acknowledgements

We wish to thank individuals, groups and organizations that participated in one way or another in facilitating this assessment. We thank the Project Technical Adviser (Joyce Ishengoma) for making early preparations and regular communications among partners for effective project assessment. CARE Tanzania Education Coordinator (Mr. Blastus Mwizarubi) for clarifying the TOR that led to proper tools preparation.

Heartfelt thanks are due to, Mr. Christopher Nkwezi (Project Coordinator) and his team for organizing refugee community groups during the assessment exercise.  Sincere thanks are also extended to camp coordinators for the demonstrated commitment to actively participate in this exercise.  Community Social   Workers will always be remembered for their proactivity in mobilising specific respondent groups and interpreting the spoken local language into Swahili.

We also extend our thanks to the sampled groups for their willingness to respond to interviews and share their experiences. We also thank the refugee community members at large for their generosity/calmness that contributed to the success of this exercise.

Our gratitude also goes to the district leaders, SAEU Headquarters leadership team and other partner NGO leaders who accepted to give their opinion on the project performance.

We deeply thank CARE Tanzania and CARE Netherlands for their financial support

Thank you all.

1.Devocatus Kamara

2.Dr. Yosh Kasilima

WVT- Consultancy Services Centre.

# Executive Summary

Over the past 30 years, Burundi has been plagued by a power struggle between the elite of its two main ethnic groups (the Hutu and Tutsi), which led to the death of thousands of people and massive influx of refugees between 1993 and 1996, leading to opening the refugee camps in Kigoma and Kagera regions (Tanzania).

Kibondo district (part of Kigoma Region) is allocated with five refugee camps (Nduta, Mtendeli, Karago, Kanembwa and Mkugwa). The present refugee population in Kibondo amounts to 135,436 of which 46,639 refugees is accommodated in Nduta, and 41,185 refugees accommodated in Mtendeli camps. SAEU is responsible for supporting Education and community service sectors in the two camps. UNHCR has extended SAEU services in two more camps of Kanembwa (19,718 refugees) and Karago (26,101 refugees) with effect from 1st January 2004.

SAEU took over from Dutch Relief and Rehabilitation Agency (DRA- now CARE Netherlands) in May  2001. CARE Tanzania on behalf of CARE Netherlands manages the project implementation and provides capacity building inputs to SAEU.

Broadly, the program goal is to facilitate local capacity building in support of refugee community in Nduta and Mtendeli camps in Kibondo District, to gain ownership of community mobilization and education program with the view to prepare the refugees for voluntary and peaceful repatriation to Burundi, as soon as the condition allow.

This report contains the findings of the rapid assessment of the program (in the two camps of Mtendeli and Nduta) and the baseline information for Kanembwa and Karago camps, which was conducted as from 1st to 11th December 2003. The report highlights the achievement, lessons learnt and best practices for the period under assessment.

The Rapid Assessment methodology was fully participatory in nature, involving accommodation of response from various program partners and beneficiaries (refugees). More information about the project was gathered through reviewing of the project documents and interview of the Key Informants.

Key findings of the Rapid Assessment show that:

- Improved teaching and learning environment in Mtendeli and Nduta camps had positive impact on enrolment and attendance rates.  The number of pupils in primary schools has been increasing from 22,145 in year 2001 to 23,254 pupils in the year 2003 while the percentage attendance for school children has been maintained at above 90% for the past three years; the current percentage attendance was noted to be 99.7%. However, more than 4000 pupils have no classroom buildings and hence use open spaces and church building to attend their studies.

- There is improved academic performance at the two camps; the number of pupils joining secondary school education has increased from 115 in the year 2000 to 266 in 2003. It was also noted that Mtendeli Camp had also celebrated commendable performance in inter-regional examinations; the camp was ranked the 1st in the consecutive two years of 2001 and 2002, and the 3rd in the year 2003 out of 11 camps available in Kigoma region, while Nduta camp ranked the 2nd and 3rd in the year 2001 and 2002 respectively. However, the number of teachers is still very low compared to the number of pupils in the camps. The current Teachers pupil ratio in both camps stands at 1:92 against the standard ratio of 1:45. There is also inadequacy of teachers trained in handling disabled pupils.

- Campaigns and training undertaken on HIV/AIDS and Reproductive Health to the youth and adolescents has changed the peoples’ attitude on HIV/AIDS and Reproductive Health Issues. There is increased openness on HIV/AIDS issues. At Nduta one person declared openly to have tested HIV+, while 10 people at Mtendeli camp declared the same.

- The number of people who accept to go for Voluntary Counseling and Testing (VCT) has been increasing, 924 people attended VCT in the year 2001, that number increased to 1264 people in 2002, and in 2003 a total number of 1145 people showed up for VCT at Nduta Camp. However, use of video show has not been fully utilized by SAEU project during sensitization campaigns, the video tapes were shown to few community support groups during the training who were considered to be front liners in implementing project activities. Moreover, there has been repatriation of some of the trained peer educators.

- There is improved women participation in leadership positions At both Nduta and Mtendeli camps, the number of women in community leadership positions has increased from 46 (27.2%) in the year 2001 to 158 (48%) out of 329 community leaders in 2003. However, the deep rooted male chauvinism hinders change in males attitudes over women as manifested by insignificant change in the reported rape cases

- Awareness campaign and sensitization of the refugee community in regard to SGBV/SE issues has enabled SGBV Survivors report on SGBV cases to the counselors with confidence. While in the year 2001 no domestic violence was reported at Nduta camp, 177 SGBV cases were reported in 2002, and other 207 cases in the year 2003.

- People are more open and can talk on their HIV/AIDS status with confidence. While marking HIV/AIDS day in November 2003, two people at Nduta camp and six people at Mtendeli Camp disclosed that they’re HIV+. The number of people attending VCT at Nduta camp has been increasing from 924 in 2001, 1264 in 2002 and 1145 in the year 2003.

- A total of 1756 of refugees (70%) out of the targeted 2520 refugees (group members and families) benefited from the micro project initiatives in Mtendeli camp through accessing the  soft loan facility. However, the repayment rate of 57% for the extended loan is low. Some of the groups (e.g. carpentry in both Nduta and Mtendeli camps) had never paid back the loan disbursed in 2001.

- The number of refugees involved in IGA has increased through co-facilitation among qualifying refugees. For example, in Mtendeli camp the number of members engaged in carpentry have increased from 10 (2001) to 36 (2003). However, the high poverty level in the camps limits money circulation and thus leading to small volume sales among the entrepreneurs.  There is a need to target markets for micro project commodities outside Kibondo Township and the camps boundaries for the entrepreneurs in the refugee camps to generate meaningful profit and achieve self-sufficiency.

- There has been positive response among the refugee community to volunteer supporting the identified vulnerable individuals and groups in the camps. The number of groups providing services to vulnerable has increased from 3 (74 group members) in 2001 to 8 groups (470 members) in 2003.

- Regular follow up to the UAMs on school attendance has improved UAMs class performance. The two sample UAMs in Nduta camp has performed well in their exams. Ndailolele Kanjoi and Emile Manilembana both of Nduta three primary school came the third and seventh respectively out of 50 pupils in class six exams.

- The capacity building support provided to SAEU in form of supplies has been of much benefit in terms of service delivery to the beneficiaries. Both availability of Computers and skilled/experienced staff has facilitated easy communication to different partners and timely reporting. However, there has been delays in fund disbursement and procurement of the capital items.

- SAEU Kibondo team has a sound experience in refugee camp management and provision of service for basic needs in refugee camps. Our discussion with the Camp Manager – Nduta Camp, IRC and TCRS management in both Nduta and Mtendeli camps revealed appreciation by the networking partners on SAEU significant contribution towards smooth running of the two refugee camps. However, the staff turnover rate of 47% in search of greener pastures is relatively high and may ruin achievement of the intended  capacity building initiatives.

- A lot of useful information/ data is generated and collected from the two camps by the social service workers on various sectors where SAEU provide service. However, the data collected are kept as raw data without having systematic tools to facilitate regular data analysis / interpretation for performance measurement data storage and sharing.

- The community based approach has been instrumental in inculcating the spirit of  ownership of the programme among refugees. The volunteerism spirit has been demonstrated through provision of voluntary services by volunteer teachers in pre, post and adult classes;  schools  management; labor in construction works and caring of vulnerable individual by refugees in the  camps.

Key Recommendations

- The project should strive to construct more classrooms that will accommodate the innocent children who regularly skip lessons during the rain seasons. Parents are committed to provide their labor for classrooms construction.

- SAEU should consider regular re-training and refresher courses to the recruited non-qualified teachers to enable them attain acceptable teaching standards .

- SAEU should design a new strategy of incentive for teachers to decrease the number of teacher who resign and go for another job with good incentives. Provision of bicycles in loan could be sought as a sister NGO (TCRS) currently practices it.

- Teachers should be considered to be equipped with appropriate training skills/methodologies in areas of Reproductive Health and HIV/AIDS for them to better train adolescent youths in primary schools.

- The project should consider complementing the current method in sensitizing the refugee community against poor Reproductive Health and HIV/AIDS with the use of Video show to achieve a sustained impact on peoples’ behavior change

- SAEU should equip social workers and community leaders in the refugee camp with Behavior Change Communication Skills to enable sustained change in behavioral among refugee community

- SAEU management in Kibondo should device a system to ensure that the extended soft loan for micro Projects are repaid back as agreed to enable other interested entrepreneurs to access the loans. Self reliance committees should be strengthened and equipped with user-friendly tools that will facilitate record update and follow up on loan repayment.

- SAEU management in Kibondo should seek and develop a collaborative network with the other NGO promoting micro projects in the refugee camps such as TCRCS

- To jointly strategize for market channels for the handcraft products produced by refugees. Market sites (towns & cities) potential for tourists outside Kibondo should be targeted.

- The package for micro project materials should be revisited to consider provision of more relevant additional materials to the better performing groups to enable smooth take off of the initiated income generation activities. For example provision of pieces of clothes to the qualifying tailoring groups could enable them take off better with their business than the provision of the sewing machine alone.

- UAMs of school going age should be given a priority when clothes are being distributed to enable them attend school. UNHCR should design an appropriate food package in favor of  UAMs to enable them get the required nutrients and stop engaging in casual labor.

- There is a need for CARE Tanzania and SAEU management to openly discuss and strategize on speeding up the approval process of SAEU funding and procurement request that are submitted to CARE Tanzania for timely implementation of relief and emergency activities in the supported camps. The Internal agreement between CARE Tanzania, CARE Netherlands and SAEU on the management of the Capacity building budget should be re-discussed among parties to elicit the ownership concerns as raised by SAEU.

.

- Field staff working in the refugee camps are exposed to daily witnessing of traumatized refugee community, this might negatively impact staff’s life psychologically. There is a need for regular counseling of SAEU field staff.

- It is high time for SAEU management to revisit its remuneration package and update the same to consider provision of a more competitive package that will enable retention of experienced and committed staff.

- SAEU Kibondo should improve the information management system. Tool for regular data collection and analysis should be developed in light of the developed monitoring and evaluation plan. Analysis of data at the outcome level should be done on quarterly basis to facilitate informed decision making and information sharing among partner NGOs.

# Noted “Best Practices” & Lessons Learnt

- Community based approach has been vital to the success for SAEU Kibondo project. Community involvement has cultivated the spirit of project ownership among the refugees and reduced the implementation cost in some of the interventions. Notable cases where communities have been actively involved include:- casting of mud bricks, involvement of social workers and teachers; and the caring of vulnerable individuals by refugees among the refugee camps.

- SAEU discourages provision of cash loans to the micro project groups. Materials are purchased instead and handled to the group on loan. The presence of a jointly owned asset binds the group members to collectively monitor the assets to ensure appropriate use and loan security.

- SAEU’s approach to provision of community service and education program deliberately inculcate the peace and reconciliation attitude among the refugee community. The roles and responsibility of each target group involve advocating on peace building. Names of schools, micro project groups, sports teams carry  messages on peace building, development, cooperation and self reliance. For example “ Lundo”-(Love), “Tuileze Mbele” (Let us struggle for Development), “Tungule nobumenyi” (Let us build each others capacity), “Tuzamulane” (Cooperation), “Tumaini” (Hope)

- Provision of khangas( donated by UNICEF) to the girls in schools has motivated more girls to attend classes and improved their class performance. However, the boys in schools perceived the approach as being discriminative in favour of girls. The perceived discrimination against boys during distribution of clothes to girls only led to negative attitudes against the whole exercise as the boys argued that they or their families needed the khangas also.

- Vulnerable individuals are integrated in the micro project groups to enable them develop/acquire business and vocational skills through doing. This in turn, increases accessibility of the accrued benefits by the vulnerable while cementing the attitude of self-help among refugees.

- The use of self-reliance committees (made up of refugee representatives) to scrutinize the micro project loan applicants and monitoring of the progress of the micro project instead of direct involvement of SAEU staff is highly commended. Committee members leave within the camp and have a greater knowledge of the applicants’ behavior. This approach minimizes risk of providing micro project loan to unfaithful refugees.

- The use of cultural group performance in dissemination of  messages for peace building and community sensitization on SGBV issues has been more effective. The approach covers more people with a uniform message at the same time, and thus minimizing chances for message distortion.

- Participatory approach utilized during capacity building needs identification (Involvement of SAEU technical Team in the process) and development of capacity building plan enabled proper addressing of the identified gaps

1.0 Introduction

## 1.1 Background

Over the past 30 years, Burundi has been plagued by a power struggle between the elite of its two main ethnic groups (the Hutu and Tutsi), which led to the death of thousands of people. There has been massive influx of refugees between 1993 and 1996, leading to opening the refugee camps in Kigoma  and Kagera regions (Tanzania). As from May 1996, the political situation in Burundi worsened to such extent that tens of thousands of refugees fled into neighboring Tanzania. Ever since, Burundians have continued to seek shelter in Tanzania, while at the same time spontaneous return has been taking place to safer regions of Burundi, following gradual success of the peace building process.

The United Nations High Commissioner for Refugees (UNHCR) is in charge of   various  actors in provision of support and services to Burundians refugees who are being accommodated in camps. Kibondo district (part of Kigoma Region) is allocated with   five refugee camps (Nduta, Mtendeli, Karago, Kanembwa and Mkugwa). The present refugee population in Kibondo amounts to 135,436 of which 46,639 refugees are accommodated in Nduta, and 41,185 refugees accommodated in Mtendeli camps where SAEU is currently partnering with other NGOs to support various refugees’ Community Services and Education functions. Of recent, UNHCR has extended SAEU services in two more camps of Kanembwa (19,718 refugees) and Karago (26,101 refugees) with effect from December, 2003.

SAEU was formerly a teaching institution established as an intergovernmental organization in 1984. The organization was reconstituted and incorporated as an international Non-Governmental organization when its original mandate ended with successful conclusion of South Africa exiles education programmes inside South Africa. SAEU submitted a bid for CSE programme alongside other bidders and emerged winners in a selection team made up on UNHCR and DRA. SAEU has since May 2001 being implementing a Community Service and Education programme in Mtendeli and Nduta refugee camps (Kibondo District). Prior, the programme had been managed and implemented by the Dutch Relief and Rehabilitation Agency (DRA- now CARE Netherlands), since when the camps were opened in 1996 to accommodate the refugees fleeing politically inspired violence in Burundi. As from July 2001, DRA became part of CARE International and changed its name to CARE Netherlands. With effect from April 2002,  CARE Tanzania on behalf CARE Netherlands manages the project implementation and provide capacity building inputs to SAEU. Among other activities in Tanzania, CARE Tanzania is involved in a relief programme in a Kasulu based camp in Kigoma Region and is proficient in capacity building for development programmes.

The project is being co-funded by UNHCR and DMV/HH on annual basis.( 600,645 EURO and 423,732 EURO were approved in 2001 and 2002 respectively). SAEU work in close partnership with other UN agencies and other  NGOs working in Kibondo refugee camps. These organizations are UNICEF as a resource and supporting UN organization for programme activities related to children (formal education and non-formal education). In addition, the project is working together with IRC, RET, TCRS and UNICEF to support tracing and reunification efforts for Unaccompanied children. There is close collaboration with the Ministry of Home Affairs, District Authorities and Local government.

Broadly, the program goal is to facilitate local capacity building in support of refugee community in Nduta and Mtendeli camps in Kibondo District, to gain ownership of community mobilization and education program with the view to prepare the refugees for voluntary and peaceful repatriation to Burundi, as soon as the conditions allow.

## 1.2 Specific sector immediate objectives:

- To give support to community initiatives to provide primary education and non-formal education, including adult education, pre- and post-primary education and distant learning

- To facilitate community initiatives for income generating activities and environmental sound practices in order to enhance the quality of life in the camps. Skill development to youth is given a special attention for youths’ future prospects on return to Burundi.

- To support the refugee community in assisting vulnerable individuals and groups;

- To support and facilitate community initiatives for peace and reconciliation and preparations for a peaceful and voluntary repatriation;

- To raise awareness in sexual and gender based violence (SGBV), HIV/AIDS and other ills that affect the refugee community;

- To facilitate capacity building initiatives to enable SAEU to implement the project effectively.

The  Community Services and Education Project in Kibondo, focuses on education, community services as well as capacity building.  The Education component deals with the construction and rehabilitation of classrooms, offices and latrines, repair and production of school furniture, provision of education materials and training of school teachers. The community service components deals the mobilization of refugees community for support and care of the vulnerable members of the community like the unaccompanied minors, attached minors, single parents, HIV/AIDS victims, elderly singles & disabled, support and facilitation of community initiatives for peace and reconciliation, income generating activities, and support to victims of gender and sexual based violence.

The last component is capacity building which aims at strengthening the capacity of SAEU to effectively implement and manage the Community Services and Education project

This report contains the findings of the rapid assessment of the program (in the two camps of Mtendeli and Nduta) and the baseline information for Kanembwa and Karago camps, which was conducted  from 1st to 11th December 2003. The report highlights the achievements, lessons learnt and best practices for the period under assessment. Specifically, the report findings are organized to reflect the following:-

- Project implementation status to date (accomplishment vs the planed outputs/activities)

- The progress made towards achievement of the project goal and objectives.

- Comment on the appropriateness of the project design and management structure in achieving the project goal

- Capacity building initiatives/inputs  provided by CARE Tanzania to SAEU

- Lessons learnt and best practices

- The nature of collaboration, stakeholders’ participation, integration/ complementarities of the major stakeholders who are UNHCR, UNICEF, RET and other agencies in the area

- Baseline data for future programming in the newly allocated camps of Kanembwa and Karago

# 2. Methodology

The assessment exercise covered a total of 14 working days. The  methodology was fully  participatory in nature, involving accommodation of response from various program partners and beneficiaries (refugees).

Methodological process were as follows:-

Documentary analysis -drawing up on existing project data, reports and background documents.  Specific Reports included:-  The Annual Project Design Documents (project proposals), Annual and monthly project Progress Reports, Monitoring & Evaluation Plan, Capacity Building Needs Assessment Report and Plan. Internet search was also used to draw information on the current development on Burundi peace building process.

The T.O.R. were re-internalized and indicators agreed upon, and finally the assessment tools produced/ updated accordingly.

Different complementary methods were used to ensure validity and reliability of the collected information. Focus Group Discussions were organized with sampled respective beneficiary categories (30 Representative committees members, 10 primary school head teachers, 28 micro project groups leaders, 5 UAMs leaving alone, 30 foster parents, 30 disabled, 6 chronically ill people) to capture information from project beneficiaries concerning benefits/achievements and areas of improvement on the extended services and support from SAEU.

Interviews were also conducted with key informants including Kibondo District Commissioner, CARE Tanzania staff (Project Technical Officer, Education Sector coordinator, SAEU Leadership team members (CEO and Programme Coordinator), SAEU Kibondo  management team ( Project Coordinator, Community Services Camp Coordinator(s), Community Services  Coordinator). The consultants also interviewed Community Service Officers and Social workers from the two camps. The list of networking partners NGOs interviewed included the Camp Manager (TCRS), Incharge of IRC and UNHCR Field Offices.

The collected information was analyzed to summarize level of achievements, tangible benefits, areas of improvement, lessons learnt and best practices for each of the undertaken project intervention. Recommendations were also drawn for each sector to influence necessary changes for better future service delivery.

# 3. Accomplishments/strengths/weaknesses & challenges

## 3.1 Education

## The increase in camp population, caused by refugee immigration and birth (birth rate is estimated at 6%) demand the provision of education service to both schooling and school going age children in the camps. Support to primary education is the major focus of the intervention. The other areas supported under education sector include:- secondary education, adult education and pre-school, vocational education (with emphasis on traditional vocations such as carpentry, hairdressing and sewing in addition to computer literacy, business management and bookkeeping) .The education sector on the camp is based on the concept of “education for repatriation” utilizing the curriculum of the country of origin. The education sector seek to improve learning and teaching environment for quality and equal access to formal education and non formal education in the two camps of Mtendeli and Nduta camps. SAEU deploys a participatory approach where the refugees are involved in school buildings rehabilitation and construction. The project provides support for manufacturing, repair and maintenance of school furniture, provision of education materials as well. The project also organizes training to unqualified teachers and upgrading the Burundian teachers to qualified teachers through skills improvement in terms of subject content and teaching methodologies. Workshops and seminars are conducted to the school management committees (parents committees). Sensitization campaigns are also organized to raise parents’ awareness on the importance education to the girl child.

### 3.1.1 Accomplishment

SAEU in collaboration with the refugee community has constructed one hundred Eighty-two (182) classrooms and renovated 12 classrooms at 10 schools in Nduta and Mtendeli camps. Furthermore the project constructed 21 teachers office and one hundred and five pit latrines stances at different schools of Mtendeli and Nduta camps. 199 chairs, 124 tables and 743 desks have been produced and distributed to primary schools within the camps. The project also distributed several textbooks, exercise books and other scholastically materials.

The project supported 2 post primary schools, 3  adult education centers, and 8 pre-schools with education materials. Forty (40) Adult Education Volunteers and 81 Pre-school volunteer teachers were provided with bicycles as an incentive and as a tool to facilitate them perform their roles with less difficulties.

### 3.1.2 Success/Strength

Improved learning environment through provision of school furniture and construction of school building to all ten primary schools  in Nduta and Mtendeli refugee camps had a positive feedback on pupils enrolment rate. The number of pupils in primary schools has been increasing from 22,145 in year 2001 to 23,254 pupils in the year 2003 at both Nduta and Mtendeli Camps. The percentage attendance for school children has been maintained at above 90% for the past three years, the current percentage attendance was noted to be 99.7%, which indicate a good recommendable job done by all education sector actors within the two camps.

Intervention conducted by SAEU on girl child through refugee community awareness creation and court intervention managed to decrease the cases of early marriage. The number of girls that dropped out of school has decreased from 341 in 2001 to 70 in both Mtendeli and Nduta Camps at the time of this assessment (December 2003).

The refugee community have been sensitized on illiteracy eradication, there has been some achievements in improving the ratio of literacy people among the refugee community, the number of people attending literacy classes has increased in both Nduta and Mtendeli camps.

Provision of scholastical materials and trainings that were conducted to teachers of all categories in all school residing within Nduta and Mtendeli camps has improved primary school performance. It was of interest to note that, during inter-regional examinations for the year 2001 and 2002, Nduta camp was ranked the 2nd and 3rd respectively out of all 11 camps available in Kigoma region. Mtendeli Camp had also celebrated commendable performance in inter-regional examinations; the camp was ranked the 1st in the consecutive two years of 2001 and 2002, and the 3rd in the year 2003.

Academic performance for grade six pupils has been improving at both  camps. The number of pupils joining secondary school education has increased from 115 in the year 2000 to 266 in 2003. It was also noted that more than 60% of all student who sat for exams attained pass mark and qualify to join the next higher-level classes.

### 3.1.3 Weakness and Challenges

Although SAEU supported rehabilitation and construction of classrooms at Nduta and Mtendeli Camps, the rapid growing number of children who qualify to join primary school education overwhelms that effort. At Nduta camp 21 classes with more than 2200 pupils and other 1934 pupils at Mtendeli camps have no classroom buildings thus using open spaces and church building to undertake their studies. Other school facilities such as furniture and books are not adequate; the situation is very critical at newly established schools such as Nduta 5 (Victory) Primary School, which was not in existence during the time of distribution of educational material.

Improvement in academic performance is largely compromised by inadequate number of qualified teachers. To address the problem, for the last two years,  SAEU has been conducting  once per week, a year long on the-job training to upgrade unqualified teachers. However, the number of teachers is still very low compared to the number of pupils in the camps. The current Teachers pupil ratio in both camps stands at 1:92 against the standard ratio of 1:45.

Furthermore, there is a big need of teachers and equipment for training pupils with disabilities such as deaf and handicapped pupils. While Matumaini primary school (Nduta 3) has two classes of disabled pupils, only one teacher has special skills for teaching disabled pupils. While no such single school exist at Mtendeli camp. The resource centers that were established in the camps are lacking adequate reference books for teachers to continue undertake personal studies and thus improve their performance.

Lack of clothes/school uniform especially for girls, orphans and other needy children encourage drop out and school absenteeism. For all five visited schools at Nduta and Mtendeli camps, most of pupils were not dressed in uniforms. Although both boys and girls have equal opportunity during grade one enrolment at the camps, the number of girls start decreasing in grade IV to VI due to lack of clothes.

Inadequate food ration provided to refugee is another hindering factor for improving school academic performance. There is irregular school attendance due to the fact that some pupils are engaged in casual labor in the nearby villages while searching for  additional food for supplementing the given ration.

Repatriation of some of trained teachers to their country of origin, and some of the trained teachers seeking employment opportunities to other organization providing services with better remunerations and rewarding system than that of SAEU, this has led to identifying and training nonprofessional teachers who could not meet the teaching standards.

There is inadequacy in provision of teaching and learning materials, for example a pupil get two exercise books per term instead of the required 8 exercise books on the assumption that, parent will contribute for the deficit while the camp economic status does not allow the parents to meet such expenses.

Changes in education curriculum in Burundi are not promptly communicated in the camp. For example, currently English subject is being taught in standard 5&6 in Burundi, while no such arrangements have been made in the camps.

Teachers spend most of their time with pupils who are either youth or potential immediate future youths. The youths are more prone to HIV/AIDS and poor reproductive health practices due to ignorance, poor knowledge coupled with adolescent sexual behavior. However, the teacher are not equipped with Sexual Reproductive Health education thus are not able to extend that knowledge to their pupils.

### 3.1.4 Recommendations

- There is a need to establish a school-feeding program in the camps to reduce the number of truants caused by inadequate food rations, SAEU could facilitate writing a proposal to WFP or any other possible donor for the project

- There is still a high demand for books in all primary schools, SAEU should continue facilitate schools in both camps with textbooks. The established Resource Centers should be provided with adequate reference books for teachers to undertake personal studies.

- More than 2200 pupils at Nduta Camp and other 1934 at Mtendeli Camps have no classrooms. The project should strive to construct more classrooms that will accommodate these innocent children who regularly skip lessons during the rain seasons. Parents are committed to provide their labor for classrooms construction.

- SAEU should consider regular training and refresher courses to the recruited non-qualified teachers to enable them attain acceptable teaching standards

- Despite SAEU’s effort in training and upgrading of refugee teachers, the Teacher-Pupil ratio is still very low, it is recommended that, on top of these training, SAEU should design a new strategy of incentive for teachers to decrease the number of teacher who resign and go for another job with good incentives. Provision of bicycles in loan could be sought as a sister NGO (TCRS) currently practices it.

- Teachers should be considered to be equipped with appropriate training skills/methodologies in areas of Reproductive Health and HIV/AIDS for them to better train adolescent youths in primary schools.

## 3.2 Youth Sports and Culture/Peace and Reconciliation

Idleness, property less, lack of a clear future perspective, being forced to stay far from home and the restriction on movement outside the camp, leads to many frustrations among the refugee community. This, then may leads to violence, banditry, drunkardness and disrespect for values and morals among the refugee community. SAEU implements the peace and reconciliation sector in the two camps with the view to enhance harmonious relationship for peaceful and voluntary repatriation, and further reintegration of refugees in their country of origin. The project promotes and facilitates discussion on how to build peace when back in Burundi and how to reconcile arising conflicts in the camps. Undertaken activities include: - support and facilitation of community initiatives for peace and reconciliation through various forms of harmonious dialogue, inclusion of peace and reconciliation as a cross cutting theme in all the project interventions, and organizing various sports and cultural performances to entertain, educate and foster relationship and develop win-win attitude among refugees.

### 3.2.1 Accomplishments

The project has registered 7926 adolescent and 18438 youths at Mtendeli and Nduta camps. About 26,000- adolescents  (98%) out of 26,364-targeted adolescent population were reached with the messages through training, campaigns, and meetings.  One hundred and fifty (150) youth peer educators and other community support groups were trained on Adolescent Sexual and Reproductive Health at Nduta Camp.  The HIV/AIDS committee composed of 29 members has been established at Nduta Camp, and 50 peer parent educators were trained on reproductive health.  Several training to entire refugee community members on HIV/AIDS, Home Based Care, Voluntary Counseling and Testing have been conducted at both camps.

The refugee community has been mobilized to engage in sports and culture groups. The formed sports groups have been supported with different sports material including football, volleyball, handball, basketball and netball. SAEU has constructed 2 netball ground, 4–handball ground and 10-football ground at Nduta and Mtendeli camps. The youth centers have been established at Nduta and Mtendeli camps which are used for organizing sports, skill development and provision of HIV counseling and Testing Services.

### 3.2.2 Successes /Strengths

It was previously considered as a taboo for one to openly discuss issues related to HIV/AIDS in Burundian community. Undertaken campaigns and training on HIV/AIDS and Reproductive Health to the youth and adolescents has changed the peoples’ behavior and attitude on HIV/AIDS and Reproductive Health Issues. There is increased openness on discussing  HIV/AIDS issues. At Nduta camp, one person declared openly to have tested HIV+, while 10 people at Mtendeli camp declared the same.

The number of people who accept to go for Voluntary Counseling and Testing has been increasing, 924 people attended VCT in the year 2001, the number increased to 1264 people in 2002, and in 2003 a total number of 1145 people showed up for VCT.

It was noted that, participation of peer parent educators has enhanced acceptability of the methodology in disseminating messages regarding adolescent sexual health, reproductive health and HIV/AIDS to the refugee community.

Youths have been integrated in micro projects and sports and thus there is reduced idleness among the youths and adolescents. The number of refugee community members engaging in sports has increased from 10,091 in 2001 to 36,077 in the year 2003.

### 3.2.3 Weaknesses and Challenges

The use of video show enhance fast understanding among observers of the effect of poor reproductive health and HIV/AIDS, thus is the good method  for awareness creation in the community. However, use of video show has not been fully utilized by SAEU project during sensitization campaigns, the method was used for training few community support groups who are considered to be front liners in implementing project activities.

There has been voluntary repatriation involving some of the trained Peer educators, this has led to new demand for training other peer educators to fill the gaps, however, the available resources are not sufficient to cater for the created demands.

### 3.2.4 Recommendation

- The project should consider complementing the current method in sensitizing the refugee community against poor Reproductive Health and HIV/AIDS with the use of Video show to achieve a sustained impact on peoples’ behavior change

## 3.3 SGBV, HIV/AIDS and Gender

Women in Burundian community society have little decision making power. Women are responsible for rearing children, cooking, cleaning, fetching water and collecting firewood on top of the other collective family responsibilities. The low status of women in Burundian society increases the vulnerability for the women to suffer from domestic and sexual violence including rape. The gender and sex based violence are also attributed to the hopeless social economic situation in the camps due to idleness, despair and frustrations among the refugee community. The notable high birth rate (6%), prevalence of STI and rape cases, justifies the densely populated refugee camps to be potential areas for high transmission of HIV/AIDS. SAEU target the large refugee community with activities for gender, HIV/AIDS and SGBV awareness rising. The objective is to reduce risky behavior related to HIV/AIDS, SGBV and gender among youth women and children. The deployed strategies include conducting mass meetings and discussions with community representatives, dissemination of messages through cultural performances in public and youth centers, distributing posters on sexual and domestic violence prevention and assisting victims of sexual and domestic violence to report their cases to the relevant organizations.

3.3.1 Accomplishments

A total of 84 awareness-raising meetings on SGBV, HIV/AIDS and gender were organized at both Nduta and Mtendeli camps. 2853 people including 1534 women and 1319 men participated in these meeting which block leaders, women representatives, head teachers, and church leaders attended. Twenty-five (25) training with a participation of 503 male and 503 female were conducted to youths, women, and men. Areas of training included; HIV/AIDS prevention, Self Reliance Initiative, Reproductive Health education, peer educators skills, Culture/sports and life skills.

SAEU also organized 12 mass awareness campaigns with participation of more than 23,000 people. The messages that were disseminated during the campaigns aimed at sensitizing the refugee community to fight against human rights violations manifested by child abuse, sexual exploitation, early/forced marriages, domestic violence/divorces and reduced HIV/AIDS stigmatization. Over the implementation period, the project has been providing moral support, counseling, and material supports to SGBV Survivors.

### 3.3.2 Successes /Strengths

Burundian refugee communities in Nduta and Mtendeli Camps have been well sensitized on gender issues including equal gender participation in social and economic activities. The number of women in leadership position has been increasing since the year 2001 showing that the conducted training and campaigns have been very successful.  At both Nduta and Mtendeli camps, the number of women in community leadership position has increased from 46 (27.2%) in the year 2001 to 158 (48%) out of 329 community leaders available in two camps during this assessment (December, 2003).

It was also noted that, participation of women in different committees has improved. During the year 2001, 59 (31.2%) women out of 189 representatives were members in different committees including food, peace, health, education and HIV/AIDS committees compared to 97 (44%) women out of 220 representatives who are currently members in the same committees.  Number of women seeking for employment opportunities within the camps has raised, for example in the year 2001, about 245 women (33%) out of 742 people were employed in different positions while currently, women in employment opportunities are amounting to 436 constituting 49.9% of all employed people in the two camps.

Women and men are given equal opportunities for engagement in micro-projects, with the noted 143 micro project groups, involving 1242 beneficiaries, 521 were males and 721 were women. Furthermore, women are equally encouraged to join groups that provide support to vulnerable. Percentage of women engaged in groups supporting vulnerable has increased from 28 % in 2001 to 50% in the year 2003.

There is a slight increase in girl’s enrolment for primary school education, in the year 2001, about 10392 girls (47%) out of 22145 were attending primary school education, the number has risen to 11121 (48%) out of 23254 in year 2003. A similar scenario was noted  in secondary school education where the enrolment for girls’ children has raised from 160 (20.8%) out of 766 students in the year 2001 to 215 (22.6%) out of 951 students in 2003.

Awareness campaigns and sensitization of the refugee community in regard to SGBV issues has enabled SGBV Survivors report on SGBV cases to the counselors with confidence. While in the year 2001 no domestic violence was reported at Nduta camp, 177 SGBV cases were reported in 2002, and other 207 cases in the year 2003. At Mtendeli camp, the community resolved 75 out 166 domestic violence reported in 2003. However, some of the men are reluctant to report incidences of domestic violence that are done on them by their wives.

The community has been empowered on HIV/AIDS issues; people are more open and can talk on their HIV/AIDS status with confidence. While marking HIV/AIDS day in November 2003, two people at Nduta camp and six people at Mtendeli Camp disclosed that they’re HIV+. The number of people attending VCT at Nduta camp has been increasing from 924 in 2001, 1264 in 2002 and 1145 in the year 2003.

### 3.3.3 Weakness and Challenges

The deep-rooted culture among Burundi refugee community, the male chauvinism in particular hinders attainment of the intended behavioral change. For example there is no significant reduction in reported raping cases at Nduta camp, the reported cases in 2001 was 28 raping cases, while in the years 2002 and 2003, each year reported 25 raping cases.

Immorality among the community has sometimes led to night marriages, and early marriages. Some of the adults who left their couples in Burundi have engaged in new marriage and these have been reported to cause chaos during repatriation or in case of family re-unification. In such circumstances, children have been left to be burden to women.

##### 3.3.4 Recommendations

- SAEU should equip social workers and community leaders in the refugee camp with Behavior Change Communication Skills to enable sustained change in behavioral among refugee community

- SAEU should support and train Faith-Based leaders to be able to provide the expected support in moral rehabilitation and peace building. More training on Human Rights are needed to the entire refugee community

## 3.4 Micro Projects

Micro projects are typically income generation activities introduced in the camp to facilitate the potential entrepreneurs refugees (with a priority to youth) and vulnerable to engage in productive micro business. Groups are supported in terms of materials needed for IGA and vocational/life skill training in relevant areas. Refugee involvement and active participation in projects identification, selection/screening of applicants, implementation and monitoring is effected through Self-Reliance Initiative Task Force (SRTFC) committees (comprising of refugees). Supported IGA initiatives are identified in collaboration with the refugees based on local market needs and country of origin future market needs. Micro project initiatives seek to develop/strengthen relevant skills among refugees that they could use in the future in the event of peaceful repatriation / integration to their country of origin.

### 3.4.1 Accomplishments

A total of 143 micro projects groups involving 1,242 beneficiaries (521 male, 721 female) have been formed/supported in the two camps of Nduta and Mtendeli under SAEU facilitation. A total of 110 vulnerable individuals were integrated in the active income generation groups. Specific IGA initiative groups supported in the two camps include: - tailoring (18), carpentry (8), hair dressing/salon (7), bicycle repair (1), pottery (4), iron smith (4), shoe repair (4), restaurant (1), dairy cow keeping (67), handcraft/knitting (11), soap making (1), gardening (8), embroidery (2), computer training (2), milling machine (2) and masonry (5).

### 3.4.2 Successes/ Strengths

A total of 1756 of refugees (70%) out of the targeted 2520 refugees (group members and families) have benefited from the micro project initiatives in Mtendeli camp while 267 group members in Nduta camp benefited from micro project support.

The extended support and the imparted skills among the group members are highly appreciated by the beneficiaries. Some of the group members reported to have improved family nutritional status through purchase of other food supplements that are not part of UNHCR food ration package. A majority of other community members (non-group members) are obliged to work as laborers to Tanzanians’ farms in the neighboring villages to get the necessary food supplements. Some of the refugees have been alleged to cause insecurity in the nearby villages in search of areas to lender their cheap labor. This in some cases has ended in legal implications.

Non-group members have also benefited in someway by accessing services that are provided by the supported members. For example, the tailoring groups repairs clothes free of charge for the refugees who are unable to pay. Group members and their families pay half the cost as benefits in kind to the group members.

There has been notable growth in number of people engaged in IGA as a result of the qualifying group members training the other interested non group members on the acquired vocational skills. For example, in Mtendeli camp the number of members engaged in carpentry have increased from 10 (2001) to 36 (2003). Each of the formed/facilitated tailoring group in Mtendeli camp had extended their vocational skills to at least 2 new non-group members.

Awareness on the importance of vocational skills among youth has risen to an extent that more youth are demanding engagement in vocational skill training beyond SAEU support capacity.

Most of the groups in Mtendeli camp that received loan from DRA had managed to repay their loan. Some of the groups have managed to purchase additional assets after repaying the loan to SAEU.

### Weaknesses  & Challenges

### The repayment rate of 57% for the extended loan is low (see table……..). some of the groups ( e.g. carpentry in both Nduta and Mtendeli camps) had never paid back the loan disbursed in 2001.

The refugees are restricted to penetrate to the local villages and Kibondo Township to avoid banditry and theft incidences, which were previously  alleged to involve unfaithful refugees. Consequently, the local Tanzanians in the neighboring villages are not allowed to enter into the refugee camps on security grounds. This restriction has limited access to both markets for the products and raw materials /commodities that is usually obtained from either Kibondo township or the neighboring villages by the micro project group members.

There has been spontaneous repatriation of some of the groups’ members where the other group members are not given an advance notice. In some cases, group members have suffered a loss of group assets following unfaithful group members taking with them some of the group properties.

The high poverty level in the camps limits money circulation and thus leading to small volume sales among the entrepreneurs.  There is a need to target markets for micro project commodities outside Kibondo Township and the camps boundaries for the entrepreneurs in the refugee camps to generate meaningful profit and achieve self-sufficiency.

3.4.4 Recommendations

- SAEU management in Kibondo should device a system to ensure that the extended loan for micro Projects are repaid back as agreed to enable other interested entrepreneurs to access the loans. Self reliance committees should be strengthen and equipped with user friendly tools that will facilitate record update and follow up on loan repayment.

- SAEU management in Kibondo should seek and develop a collaborative network with the other NGO such as TCRS promoting micro projects in the refugee camps to jointly strategize for market channels for the handcraft products produced by refugees. Market sites (towns & cities) potential for tourists outside Kibondo should be targeted.

- Micro Project loan guidelines should be updated to reflect ownership of the jointly owned assets by refugees on repatriation to their country of origin. Lack of clarity on the future group assets ownership modalities may pause a potential area of conflict among group members upon repatriation.

- Regular saving among group members should be encouraged to enable capital growth that could enable group members replace the wearing tools and equipment

- The package for micro project materials should be revisited to consider provision of more relevant additional materials to the better performing groups to enable smooth take off of the initiated income generation activities. For example provision of pieces of clothes to the qualifying tailoring groups could enable them take off better with their business than the provision of the sewing machine alone.

## 3.5 Support to Vulnerable

The population displacement in Burundi led to disruption of families and of the traditional copping mechanism. There is a high need to support various categories of vulnerable within the refugee camps. The project encourages the refugee community to care for the vulnerable groups and individual. These  include: - handicapped, unaccompanied elderly, un-accompanied minors, single parents, orphans, and survivors of sexual and gender based violence.

The community is assisted to take care of vulnerable individuals and groups through tracing UAMs family members and re-unifying them, encouraging and assisting foster parents in taking care of UAMs, provision of basic needs to unaccompanied elders, single parents and victims of violence. The project in collaboration with the social workers undertake follow up on school attendance of unaccompanied minors; and facilitate provision of services to disabled by a trained physiotherapist. Mobilization on prevention of sexual and domestic violence is also one of the key undertaken activities.

### 3.5.1 Accomplishments:

SAEU has managed to mobilize a team of committed  Community  Social Workers who support   provision of service to vulnerable in the refugee camps.

There has been notable increase in number of vulnerable that are being integrated in the micro project yearly. Review of camp records in Nduta camp indicated an increase in number of the integrated vulnerable individuals from 19 (2001) to 30 (2003)

A total of 13,568(72%) vulnerable from the two camps of Nduta and Mtendeli camps have been supported for the past three years. The target was support 18,754 vulnerable.

60 UAMs (45 male and 15 female) and 622 AMs (335 male and 287female) were identified and registered at reception for effective follow up and support. Community Social workers and community structures (Community members, women representatives, block leaders, youth representatives, religious leaders and teachers) were trained on children rights for effective care and protection of children. UAMs and AMs of school going age were registered for school and follow up undertaken to ensure that they attend classes.

### 3.5.2 Successes /Strengths

There has been positive response among the refugee community to volunteer supporting the identified vulnerable individuals and groups in the camps. The number of groups providing services has increased from 3 (74 group members) in 2001 to 8 groups (470 members) in 2003. (See table…….) The type of support provided by these groups includes house repairing, fetching water, collecting firewood, repairing clothes, collecting bundles of grass and construction of latrines to the vulnerable. This attitude has contributed to the rehabilitation of unit and togetherness, which is an important ingredient to peace building initiatives.

The provided physical aid materials including the tricycles,  crutches, toilet seats (wooden boxes), beds and clothes. They  are highly appreciated by the beneficiaries. The tricycle and the support stick have enabled the disabled vulnerable to walk around the camp and participating in the camp events and socializing with other community members.

Regular follow up to the UAMs on school attendance has enabled UAMs to concentrate on studies and thus improved their class performance. The two sample UAMs in Nduta camp has performed well in their exams. Ndailolele Kanjoi and Emile Manilembana both of Nduta three primary school came the third and seventh respectively out of 50 pupils in class six exams.

# 3.5.3 Weaknesses and Challenges

The UAMs who are not attached to foster parents are obliged to provide cheap labor in the nearby villages to get supplementary food varieties which are not provided under UNHCR food basket. This sometimes limits them from concentration in class. Clothes (school uniform in particular) was reported to be a hindrance for comfortable school attendance by the UAMs

The provided physical aid materials are not replaced timely. Some of the physically disabled refugees were provided with pairs of crutches, which have not been replaced for the past four years while the same people have increased their height. In some cases, the physically disabled ones are not involved in the selection of appropriate support sticks to be provided.

Forster parents have been trained on child rights awareness, child development and support to children and integration of UAMs and AMs in community. Some of the foster parents regard AMs as their children and hence try to stop them from taking part  in immoral and culturally unacceptable events. Some of the attached minors have raised complaints sometimes perceiving the taken action as being mistreatment on their side.

### 3.5.4 Recommendations

- UAMs of school going age should be given a priority when clothes are being distributed to enable them attend school. UNHCR should design an appropriate food package in favor of  UAMs to enable them get the required nutrients and stop engaging in casual labor.

- Physically Disabled refugees (handicapped) should be consulted on selecting the type of crutches to people with disabilities. The crutches should be replaced as one grows in size while SAEU consider provision of adjustable crutches which are most suitable and desired by the interviewed vulnerable.

- SAEU should consider organizing appropriate training to the attached minors to inculcate the family belonging attitude, respect and value of the foster parents by the supported attached minors.

## 3.6 Capacity Building

CARE Tanzania facilitated a participatory capacity building need assessment in order to identify SAEU’s capacity strength and gaps in terms of staff skills, management, governance,  human resource, admin & finance, organizational sustainability and networking. Based on the identified capacity gaps, the capacity building plan was developed to address the gaps.

The identified gap areas for SAEU capacity building included; Monitoring and Evaluation, Proposal writing, Gender mainstreaming, Basics of computer applications, French, HIV/AIDS prevention, Facilitation skills, and Fund raising. Other identified areas of capacity building were  in institutional strengthening  to support SAEU with office equipment, install Local Area Network (LAN), install and undertake training on PAM accounting soft ware, provision of communication equipment , Review and update the finance, administration and human resource manuals.

CARE Tanzania on behalf of CARE Netherlands provides capacity building inputs for SAEU with the purpose of enhancing SAEU’s capacity in designing, supervising and monitor the programme effectively.

CARE Tanzania in collaboration with SAEU identified various resource persons (Consultants) to facilitate training, workshops and seminars to various SAEU staff categories as it was jointly identified and agreed on the capacity building plan. CARE Tanzania also facilitated procurement of communication equipment and review of SAEU’s manuals for admin & finance, and human resource.

### 3.6.1 Accomplishment

SAEU staffs have received training in different disciplines. The undertaken training included; Log frame Analysis & Monitoring and Evaluation (12 staff), Gender mainstreaming (11 staff), Project Proposal writing (16 staff), Basics of computer (14 staff), French (11 staff), NGO Administration Management (1 staff), English course (4 staff) and PSV Driver course (3 staff). This was 73% achievement as per project plans.

The pending training include; HIV/AIDS, Facilitation skills and Resource Mobilization.

SAEU also have been supported with 2 vehicles, 1 computer, one LCD projector, 1 printer, and 2 codan Radios, SAEU Financial & Administration, and Human Resource manuals have been reviewed and updated to suit the current situation.

### 3.6.2 Successes/ Strengths

The support provided to SAEU in form of supplies has been of much benefit in terms of service delivery to the beneficiaries. Both availability of Computers and skilled/experienced staff has facilitated easy communication to different partners and timely reporting.

Training received by SAEU staff has improved their knowledge and skills especially in the basics of computer and Monitoring and Evaluation. Some staff has been engaged in writing proposals and utilizing Monitoring and Evaluation framework for reporting. However, SAEU has faced a challenge of multiple demand report format from various stakeholders, the situation that has denied fully utilization of skills received during capacity building sessions.

### 3.6.3 Weakness and Challenges

Training become of much beneficial to the program if trainings are done at the initial stage of the project for the project staff utilize the skills acquired during those trainings. However, some training were not done in time, for example Project Account Management (PAM) training is yet to be done though it was scheduled for the year 2003. Such delays limit timely application of the knowledge.

The current era is of frequent change in technology that demand for regular new capacity building needs identification. However, the program conducted only one need identification event at the start of the project and there is no check mechanism that can identify new needs for capacity building.

There were a 3-month delay in purchasing office equipment such as computers and LCD projector. In some instance fund disbursement from CARE Tanzania was also delayed while there is a pressing demand in the refugee camps. It was noted that, approval procedures for procurement and money disbursement could be the cause of such delay. Currently, at CARE Tanzania, the cheque is approved twice per week of which if missed it has to be delayed for a whole week

### Recommendations

- There is a need for CARE Tanzania and SAEU management to openly discuss and strategize on speeding up the approval process of SAEU funding and procurement request that are submitted to CARE Tanzania for timely implementation of relief and emergency activities in the supported camps. The Internal agreement between CARE Tanzania, CARE Netherlands and SAEU on the management of the Capacity building budget should be re-discussed among parties to elicit the ownership concerns as raised by SAEU.

- There is a need to capacity build each other on financial and narrative report requirement at all levels, CARE partners and SAEU should agree and strive to avoid unnecessary regular changes in financial and narrative report format

- Capacity building need identification should be a continuous process in order to catch up with the current rapid change in technological advancement

- Field staff working in the refugee Camps are exposed to daily witnessing of traumatized refugee community, this might negatively impact staff’s life psychologically. There is a need for regular counseling of SAEU field staff.

# 4. Project Management

SAEU Kibondo is in charge of the day to day implementation of the project. The Project Coordinator is the team Leader supported by  Community Service Coordinator, Camp Coordinators, Community Service Officers, the Administrator, an Accountant and Drivers. Teams of Community Social Workers (refugees) support the community service activities in the two camps.  SAEU Headquarters is charged with the task of providing the leadership support, fundraising and overall co-coordination of  Kibondo Programme. The head quarter is also charged with the task of maintaining healthy networks with other stakeholders (including the donor, CARE Tanzania and CARE Netherlands), supporting Kibondo team in recruiting staff for key positions and provision of supportive monitoring functions.

CARE Tanzania is responsible for capacity building programme, both at SAEU headquarters and Kibondo teams. In addition, CARE Tanzania provide narrative and financial reports on a three-monthly basis to CARE Nederland and safeguard proper liquidity planning and budget control.

There has been a healthy collaborative network between CARE Program Technical Officer, CARE Tanzania Education Coordinator and SAEU staff. Identification of the capacity building gaps was done in collaboration with SAEU staff through engaging a consultant. The participatory approach in training needs identification has been commended by both CARE Tanzania and SAEU  staff.

SAEU Kibondo team has a sound experience in refugee camp management and provision of service for basic needs in the camps. Our discussion with the Camp Manager – Nduta Camp, IRC and TCRS management in both Nduta and Mtendeli camps revealed appreciation by the networking partners on SAEU significant contribution towards smooth running of the two refugee camps.

The Project proposals were well designed to address key aspects of refugee camps operations. The current year (2003) project proposal has been detailed to reflect the expected outputs. This is highly commended for accountability and performance measurement. The developed monitoring and evaluation plan is an essential tool to keep the project progress in track. However, this need to be operationalised in the program interventions for the plan to be more meaningful.

4.1 Weaknesses and Challenges

A briefing discussion held with the Kibondo District Commissioner revealed the fact that reintegration of refugees into the Tanzanian community is not the wish of the Government of Tanzania, and its aim is voluntary repatriation of refugees to the country of origin (Burundi) as soon as the situation is considered safe. However, the trend for voluntary repatriation indicates slow pace with only 15,515 refugees (10%) from the five camps within Kibondo out of the total refugee population of 152,245  to have  been repatriated to Burundi for the past three years.

Notwithstanding the unwillingness to return back to Burundi, the life of the refugees remaining in the camps is filled with constraints and hardship. Their movements are restricted to an area of 4 kilometers radius of the camps and are almost totally dependent on handouts for basic survival needs.

The food rations that the refugees receive from the WFP are subject to periodic cuts depending on food availability from the international community. This had led to instability in the camp with notable domestic violence among couples.

There has been delays in project funding from CARE Tanzania to SAEU for fund disbursement to Kibondo. The fund approval, which is done only twice a week, limits timing of project implementation in case there are issues to be clarified before approval of the submitted requests. It was also noted that procurement of capital items takes longer time than expected.

Staff turn over is at the high side. Review of Kibondo project records indicated 18 staff (45%) had left the project in search of greener pastures. This on the other side compromise the capacity building initiatives as some of the staff who had recently received capacity building training were among the staff reported to have been left the project.

A lot of useful information/ data is generated and collected from the two camps by the social service workers on various sectors where SAEU provide service. However, the data collected are kept as raw data without having systematic tools to facilitate regular data analysis / interpretation.

Recommendations

- SAEU management should advise CARE Tanzania management on the best way  that could facilitate timely project funding and ensure timely procurement of the capital items in the future.

- It is high time for SAEU management to revisit its remuneration package and update the same to consider provision of a more competitive package that will enable retention of experienced and committed staff.

- SAEU Kibondo should improve the information management system. Tool for regular data collection and analysis should be developed in light of the developed monitoring and evaluation plan. Analysis of data at the outcome level should be done on quarterly basis to facilitate informed decision making and information sharing among partner NGOs.

# 5. Best practices/Lesson learned

- Community based approach has been vital to the success for SAEU Kibondo project. Community involvement has cultivated the spirit of project ownership among the refugees and reduced the implementation cost in some of the interventions. Notable cases where communities have been actively involved include:- casting of mud bricks, involvement of social workers and teachers; and the caring of vulnerable individuals by refugees among the refugee camps.

- SAEU strategy seeks to improve the economic status of refugees through promotion of micro project to eligible/potential refugees. The option of utilizing the developed skills among refugees deserves to be commended. Internal opportunities for service are deliberately created through providing tender to the qualified refugees to provide manageable services in the camps. For example:- carpenters are given tender for manufacture of furniture, “Mama lishe” groups are supported through providing food to workshop participants and visitors in the camps.

- SAEU discourage provision of cash loans to the micro project groups. Materials are purchased instead and handled to the group on loan. This enforces the group members to collectively monitor the assets to ensure appropriate use and security. Repayment is done by cash and collection done regularly at shorter interval as a risk management strategy

- SAEU encourages trained micro project members to volunteer and identify other interested non-group member and train them on the gained vocational skills to have a multiplier effect of vocational skills among refugees. There was doubling in number of refugees practicing some of the vocational skills following as a result of refugees training each other.

- SAEU approach to provision of community service and education program deliberately inculcate the peace and reconciliation attitude among the refugee community. The roles and responsibility of each target group involve advocating on peace building. Names of schools, micro project groups, sports teams caries a message on peace building, development, cooperation and self reliance. For example “ Lundo”-(Love), “Tuileze Mbele” (Let us Struggle for Development), “Tungule nobumenyi” (Let us build each others capacity), “Tuzamulane” (Cooperation), “Tumaini” (Hope)

- Provision of clothes (uniforms) to the girl child in school has motivated more girls to attend class and improved their class performance. However, the boy child in school perceived the approach as being discriminative. Disgust attitude developed against the supported school going girls as the situation in camps compels boys to consider themselves to be equally needy.

- Vulnerable individuals are integrated in the micro project groups to enable them develop/acquire business and vocational skills through doing. This in turn, increases accessibility of the accrued benefits by the vulnerable while cementing the attitude of self-help among refugees.

- The use of self-reliance committees (made up of refugee representatives) to scrutinize the micro project loan applicants and monitoring of the progress of the micro project instead of direct involvement of SAEU staff is highly commended. Committee members leave within the camp and have a greater knowledge of the applicants’ behavior. This approach minimizes risk of providing micro project loan to unfaithful refugees.

- Diversity among refugee community in terms of region of origin (in the country of origin), ethnicity, religion, and political affiliation; posses a challenge in managing /facilitating refugee community. Mtendeli camp where a majority of the refugee came from the same region seems to be more facilitatable than Nduta camp where refugees originated from different areas of Burundi.

- The use of cultural group performance in dissemination of  messages for peace building and community sensitization on SGBV issues has been more effective. The approach covers more people with a uniform message at the same time, and thus minimizing chances for message distortion.

- Participatory approach utilized during capacity building need identification (Involvement of SAEU technical Team in the process) and development of capacity building plan enabled proper addressing the identified gaps

Table 1: Refugee Camp Population (2000 – 2003)

| Camp | Kanembwa | Mkugwa | Karago | Mtendeli | Nduta | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Year 2000 | 17,795 | 1,977 | 52,125 | 41,700 | 46,228 | 159,825 |
| 2001 | 18,456 | 1,701 | 36,700 | 47,172 | 40,305 | 144,334 |
| 2002 | 19,000 | 1,721 | 36,600 | 46,922 | 48,002 | 152,245 |
| 2003 | 19,718 | 1,793 | 26,101 | 41,185 | 46,639 | 135,436 |

Source: SAEU Record

Table 2: Micro Project Beneficiaries by Category- Mtendeli Camp

| Category | Reached beneficiaries | Total | Target | Remarks |
| --- | --- | --- | --- | --- |
|  | Male | Female |  |  |  |
| Tailoring | 42 | 54 | 96 | 129 |  |
| Carpentry | 105 | 0 | 105 | 168 |  |
| Livestock | 103 | 88 | 191 | 300 |  |
| Computer training | 117 | 49 | 166 | 180 |  |
| Pottery | 38 | 28 | 66 | 124 |  |
| Iron Smith | 27 | 0 | 27 | 60 |  |
| Shoe making | 30 | 0 | 30 | 67 |  |
| Restaurant | 02 | 15 | 17 | 30 |  |
| Milling machine | 26 | 05 | 31 | 35 |  |
| Hair dressing | 13 | 20 | 33 | 60 |  |
| Hair saloon | 32 | 0 | 32 | 72 |  |
| Bicycle repair | 26 | 2 | 28 | 45 |  |
| Diary cows | 55 | 10 | 65 | 85 |  |
| Knitting | 44 | 208 | 252 | 320 |  |
| Soap making | 21 | 08 | 29 | 35 |  |
| Masonry | 28 | 0 | 28 | 40 |  |
| Gardening | 53 | 42 | 95 | 165 |  |
| Embroidery | 02 | 22 | 24 | 32 |  |
| Hand craft | 14 | 381 | 395 | 525 |  |
| Tailoring training | 24 | 22 | 46 | 48 |  |
|  | 802 | 954 | 1756 | 2520 |  |

Source: Mtendeli Camp Records

Table 3: Trend of Micro Project Supported – Mtendeli Camp

| Category of Micro project supported | 2001 | 2002 | 2003 |
| --- | --- | --- | --- |
|  | # of Grp | M | F | # of Grp | M | F | # of Grp | M | F |
| Masonry | 1 | 4 | 0 | 2 | 6 | 0 | 5 | 18 | 0 |
| Pottery | 1 | 6 | 3 | 2 | 13 | 8 | 4 | 19 | 17 |
| Iron smith | 1 | 6 | 0 | 2 | 9 | 0 | 3 | 12 | 0 |
| Carpentry | 1 | 24 | 0 | 4 | 33 | 0 | 7 | 48 | 0 |
| Tailoring | 7 | 13 | 19 | 5 | 11 | 17 | 7 | 18 | 18 |
| Shoe making | 2 | 9 | 0 | 2 | 8 | 0 | 4 | 13 | 0 |
| Restaurant | 1 | 0 | 5 | 1 | 1 | 5 | 1 | 1 | 5 |
| Hair dressing | 0 | 0 | 6 | 2 | 6 | 11 | 1 | 7 | 3 |
| Computer training | 0 | 0 | 0 | 1 | 58 | 26 | 1 | 59 | 23 |
| Milling machine | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 26 | 5 |
| Knitting | 0 | 0 | 0 | 1 | 7 | 28 | 2 | 37 | 180 |
| Tailoring training | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 24 | 22 |
| Hair saloon | 1 | 6 | 0 | 2 | 14 | 0 | 2 | 12 | 0 |
| Bicycle repair | 2 | 8 | 1 | 2 | 8 | 1 | 1 | 10 | 0 |
| Daily cows | 0 | 0 | 0 | 20 | 17 | 3 | 45 | 38 | 7 |
| Gardening | 3 | 7 | 4 | 5 | 13 | 15 | 8 | 33 | 23 |
| Livestock & poultry | 5 | 22 | 28 | 6 | 25 | 26 | 8 | 56 | 34 |
| Soap making | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 21 | 8 |
| Hand craft | 1 | 0 | 4 | 5 | 9 | 42 | 9 | 5 | 335 |
| Embroidery | 0 | 0 | 0 | 1 | 0 | 4 | 2 | 2 | 18 |
| Total | 27 | 105 | 70 | 63 | 238 | 181 | 113 | 492 | 698 |
|  |  | 175 |  | 419 |  | 1190 |

# Table 4: SAEU Staff Capacity Building

|  | Type of Training | Category of Staff and number trained | Duration |
| --- | --- | --- | --- |
| 1. | Computer Training | 1 Chief Executive Director | 2 weeks |
|  |  | 1 Deputy Director |  |
|  |  | 2 Project Coordinator |  |
|  |  | 1 Administrator |  |
|  |  | 2 Community Service Officer |  |
|  |  | 4 Finance Officers |  |
|  |  | 1 Trainer – Dar Office |  |
|  |  | 1 Secretary |  |
|  |  | 1 CARE Tanzania staff |  |
| 2. | Proposal Writing | 1 Chief Executive Director | 2 weeks |
|  |  | 1 Deputy Director |  |
|  |  | 1 Project Coordinator |  |
|  |  | 1 Community Coordinator |  |
|  |  | 1 Camp Coordinator |  |
|  |  | 1 Administrator |  |
|  |  | 6 Community Service Officer |  |
|  |  | 3 Finance Officers |  |
|  |  | 2 Trainer – Dar Office |  |
| 3. | Gender Mainstreaming | 1 Deputy Director | 2 weeks |
|  |  | 2 Trainer |  |
|  |  | 1 Finance Officer |  |
|  |  | 1 Camp Coordinator |  |
|  |  | 6 Community Service Officer |  |
| 4. | French | 1 Project Coordinator | 2 weeks |
|  |  | 1 Camp Coordinator |  |
|  |  | 9 Community Service Officer |  |
| 5. | NGO Administration Management | 1 Project Coordinator | 2 weeks |
| 6. | English course | 4 Drivers | 2 weeks |
| 7. | Engine Overhaul | 1 Driver | 2 weeks |
| 8. | PSV Drivers Course | 2 Driver | 2 weeks |
| 9 | Monitoring & evaluation | 12 staff ( Dar office + Kibondo) | 4 days |

Table 5: Integration of Vulnerable in Micro Projects – Nduta Camp

| Group category | 2001 | 2002 | 2003 |
| --- | --- | --- | --- |
|  | Other beneficiaries | Vulnerable | Other beneficiaries | Vulnerable | Other beneficiaries | Vulnerable |
|  | M | F | M | F | M | F | M | F | M | F | M | F |
| Tailoring (sewing) | 26 | 20 | 5 | 2 | 26 | 20 | 5 | 2 | 19 | 20 | 3 | 2 |
| Carpentry | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |
| Livestock keeping | 12 | 18 | 5 | 7 | 8 | 7 | 4 | 3 | 0 | 0 | 0 | 0 |
| Computer skills | 0 | 0 | 0 | 0 | 55 | 23 | 0 | 0 | 53 | 19 | 0 | 0 |
| Tailoring training | 0 | 0 | 0 | 0 | 8 | 8 | 4 | 4 | 30 | 18 | 10 | 8 |
| Pottery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 18 | 0 | 5 |
| Iron smith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |
| Hair saloon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 1 | 1 |
| Total | 44 | 38 | 10 | 9 | 103 | 58 | 13 | 9 | 122 | 78 | 14 | 16 |
|  | 82 | 19 | 161 | 22 | 200 | 30 |
| Annual total | 101 | 183 | 230 |

Table 6: Loan Repayment Rate Nduta & Mtendeli Micro Project Group

| Micro project category | Name of Camp | Loan Disbursement date | Loan amount (Tshs) | Repayment (Tshs) | Outstanding balance (Tshs) | Repayment rate (%) |
| --- | --- | --- | --- | --- | --- | --- |
| Carpentry | Nduta | 2001 | 150,000 | 10,000 | 140,000 | 7% |
| Chairmaker | Nduta | 2001 | 168,000 | 60,000 | 108,000 | 36% |
| Bicycle repair | Nduta | 2003 | 191,100 | 21,000 | 170,100 | 11% |
| Hairdressing | Nduta | 2003 | 100,100 | 49,000 | 51,100 | 49% |
| Carpentry | Mtendeli | 2001 | 225,000 | 75,000 | 150,000 | 33% |
| Women restaurant | Mtendeli | 2003 | 109,500 | 60,000 | 49,000 | 57% |
| Saloon mwenzangu | Mtendeli | 2003 | 102,000 | 24,000 | 78,000 | 24% |
| Shazuberwe saloon | Mtendeli | 2003 | 101,000 | 31,000 | 70,000 | 31% |
| Milling machine | Mtendeli | 2003 | 3,525,700 | 2,343,865 | 1,181,835 | 66% |
|  |  |  | 4,672,400 | 2,673,865 | 1,998,035 | 57% |

Source: Nduta & Mtendeli camp records

Table 7: Supported Vulnerable by Category since 2001.

| VULNERABILITY CATEGORY | MTENDELI CAMP | NDUTA CAMP |
| --- | --- | --- |
|  | Male | Female | Total | Target | Male | Female | Total | Target |
| Un accompanied minors | 459 | 225 | 684 | 309 | 20 | 15 | 35 | 836 |
| Attached minors | 828 | 597 | 1425 | 2407 | 437 | 332 | 769 | 1977 |
| Single female | 0 | 73 | 73 | 102 | 0 | 18 | 18 | 9 |
| Physically disabled | 885 | 350 | 1235 | 2582 | 370 | 271 | 641 | 206 |
| Un accompanied elderly | 876 | 2855 | 3677 | 3783 | 118 | 63 | 181 | 111 |
| Chronically ill | 252 | 152 | 404 | 529 | 23 | 60 | 83 | 26 |
| Single parents | 402 | 2015 | 2417 | 4125 | 75 | 798 | 873 | 314 |
| Victims of Violence | 113 | 83 | 196 | 219 | 18 | 10 | 28 | 3 |
| Mentally disabled | 374 | 359 | 733 | 1154 | 58 | 44 | 102 | 62 |
|  | 4129 | 6709 | 10838 | 15210 | 1119 | 1611 | 2730 | 3544 |
| Grand totals | Total supported= 13,568 (72%) Total target= 18,754 |

Table 8: Facilitated & Voluntary Repatriation Trend By Camp

| YEAR | KARAGO | MTENDELI | KANEMBWA | NDUTA | MKUGWA | TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
|  | FAM. | BEN. | FAM. | BEN. | FAM. | BEN. | FAM. | BEN. | FAM. | BEN. | FAM. | BEN. |
| 2002 | 355 | 939 | 212 | 654 | 19 | 41 | 406 | 1,062 | 7 | 25 | 999 | 2,721 |
| 2003 | 1,145 | 4,445 | 894 | 3,225 | 188 | 665 | 1,356 | 4,385 | 18 | 71 | 3,604 | 12791 |
| TOTAL | 1,500 | 5,384 | 1,106 | 3,879 | 207 | 706 | 1,762 | 5,447 | 25 | 96 | 4,603 | 15,512 |

Source: SAEU Record

Table 9: Trend of Groups Supporting Vulnerable – Mtendeli Camp

| Year | Group name | Group members | Group activity (type of support provided) |
| --- | --- | --- | --- |
|  |  | M | F | Total |  |
| 2001 | Dufashanye | 24 | 18 | 42 | House repairing, fetching water, collecting firewood |
|  | Rukundo | 4 | 3 | 7 | Tailoring (repairing clothes) |
|  | Twitezimbele | 25 | 0 | 25 | Making doors and chairs |
|  | Total | 53 | 21 | 74 |  |
| 2002 | Dufashanye | 36 | 40 | 76 | House repairing, fetching water, collecting firewood |
|  | Twunguranububenyi | 19 | 25 | 44 | Collecting bundles of grass and firewood |
|  | Turihamwe | 3 | 5 | 8 | Tailoring |
|  | Rukundo | 4 | 3 | 7 | Tailoring (repairing clothes) |
|  | Vyizigiro | 10 | 25 | 35 | Collecting firewood and fetching water |
|  | Abasangirakivi | 0 | 40 | 40 | Repairing houses, construction of latrines |
|  | Twitezimbere | 36 | 0 | 36 | Making doors and chairs |
|  | Total | 108 | 138 | 246 |  |
| 2003 | Yourefa | 32 | 25 | 57 | Collecting firewood |
|  | CAF | 28 | 17 | 45 | Repairing houses |
|  | Turihamwe | 37 | 29 | 66 | Soap making |
|  | Rukundo | 4 | 3 | 7 | Tailoring (repairing clothes) |
|  | Dufashanye | 65 | 55 | 120 | Repairing houses, construction of latrines |
|  | Twitezimbere | 36 | 0 | 36 | Making doors and chairs |
|  | Majambele | 40 | 34 | 74 | Repairing houses, construction of latrines |
|  | Abasangirakivi | 0 | 65 | 65 | Collecting firewood |
|  | Total | 242 | 228 | 470 |  |

Source: Mtendeli camp records

Table 10: Primary Schools Parameters (2000 – 2003) – Nduta and Mtendeli Camps (Nduta Camp - Ushirikiano, Urafiki, Matumaini, and Undugu Primary schools; Mtendeli Camp - Mtakuja, Hope, Tujikumbuke, Solidarity and Stella Primary schools)

|  |  | NDUTA CAMP | MTENDELI CAMP |
| --- | --- | --- | --- |
|  | Name of School | 2000 | 2001 | 2002 | 2003 | 2000 | 2001 | 2002 | 2003 |
|  |  | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls |
| A | Enrollment | 5261 | 4478 | 5973 | 5185 | 6775 | 6074 | 6921 | 6315 | 5308 | 4648 | 5780 | 5207 | 5982 | 5275 | 4952 | 4645 |
| B | Attendance | 5073 | 4349 | 5636 | 4944 | 6129 | 5280 | 6921 | 6315 | 5236 | 4642 | 5764 | 5190 | 5796 | 5057 | 4932 | 4624 |
| C | Attendance (%) | 96.4 | 97.1 | 94.4 | 95.4 | 90.5 | 86.9 | 100 | 100 | 98.6 | 99.9 | 99.7 | 99.7 | 96.9 | 95.9 | 99.6 | 99.5 |
| D | Sat for exam | 4988 | 4283 | 5467 | 4821 | 5855 | 5065 | 6250 | 5801 | 5032 | 4231 | 5636 | 5087 | 5505 | 4876 | 4642 | 4538 |
| E | Passed Exams | 3845 | 2525 | 3495 | 2845 | 3563 | 3094 | 3892 | 3530 | 3017 | 2157 | 3888 | 3103 | 3523 | 2826 | 2952 | 2496 |
| F | % passed | 77 | 55.9 | 63.9 | 59 | 60.9 | 61 | 62.3 | 60.9 | 59.9 | 50.9 | 68.9 | 60.9 | 63.9 | 57.9 | 63.5 | 55 |
| G | Drop out | 150 | 84 | 258 | 199 | 617 | 613 | 0 | 0 | 257 | 203 | 203 | 142 | 156 | 169 | 135 | 70 |
| H | Joined Secondary Education | 89 | 17 | 92 | 63 | 124 | 17 | 149 | 37 | 9 | 0 | 92 | 37 | 74 | 8 | 67 | 16 |

# Table 11: Teacher: Pupil Ratio – Nduta Camp

| Name of School | 2001 | 2002 | 2003 |
| --- | --- | --- | --- |
|  | Number of teachers | Number of pupils | Number of teachers | Number of pupils | Number of teachers | Number of pupils |
|  | M | F | T | Boys | Girls | T | M | F | T | Boys | Girls | T | M | F | T | Boys | Girls | T |
| Ushirikiano | 30 | 3 | 33 | 1489 | 1249 | 2738 | 27 | 3 | 30 | 1612 | 1389 | 3001 | 25 | 6 | 31 | 1782 | 1505 | 3287 |
| Urafiki | 18 | 9 | 27 | 1288 | 1159 | 2447 | 18 | 9 | 27 | 1540 | 1364 | 2904 | 19 | 8 | 27 | 1550 | 1452 | 3008 |
| Matumaini | 21 | 9 | 30 | 1681 | 1410 | 3091 | 21 | 10 | 31 | 1901 | 1709 | 3610 | 28 | 9 | 37 | 1965 | 1833 | 3798 |
| Undugu | 24 | 7 | 31 | 1515 | 1367 | 2882 | 21 | 8 | 29 | 1722 | 1543 | 3265 | 23 | 7 | 30 | 1778 | 1686 | 3464 |
| Total | 93 | 28 | 121 | 5973 | 5185 | 11158 | 87 | 57 | 117 | 6775 | 6005 | 12780 | 95 | 30 | 125 | 7075 | 6476 | 13557 |

# Table 12: Teacher: Pupil Ratio – Mtendeli Camp

| Name of School | 2001 | 2002 | 2003 |
| --- | --- | --- | --- |
|  | Number of teachers | Number of pupils | Number of teachers | Number of pupils | Number of teachers | Number of pupils |
|  | M | F | T | Boys | Girls | T | M | F | T | Boys | Girls | T | M | F | T | Boys | Girls | T |
| Mtakuja | 26 | 4 | 30 | 1573 | 1442 | 3015 | 21 | 4 | 25 | 1295 | 1157 | 2452 | 21 | 5 | 26 | 1095 | 956 | 2051 |
| Hope | 24 | 5 | 29 | 1384 | 1229 | 2613 | 21 | 5 | 26 | 883 | 814 | 1697 | 18 | 7 | 25 | 884 | 763 | 1587 |
| Tujikumbuke | 28 | 3 | 31 | 1544 | 1403 | 2347 | 25 | 2 | 27 | 1252 | 1171 | 2423 | 24 | 3 | 27 | 1149 | 1070 | 2219 |
| Solidarity | 23 | 1 | 24 | 1279 | 1133 | 2412 | 24 | 2 | 26 | 1540 | 1293 | 2833 | 23 | 4 | 27 | 903 | 957 | 1860 |
| Stella | - | - | - | - | - | - | 22 | 2 | 24 | 1012 | 840 | 1852 | 19 | 4 | 23 | 981 | 899 | 1880 |
| Total | 101 | 13 | 114 | 5780 | 5207 | 10987 | 113 | 15 | 128 | 5982 | 5275 | 11257 | 105 | 23 | 128 | 4952 | 4645 | 9597 |

Table 13 :Grade I Enrolment rate – Nduta Camp

|  | Name of School | 2000 | 2001 | 2002 | 2003 |
| --- | --- | --- | --- | --- | --- |
|  |  | Boys | Girls | Target | Boys | Girls | Target | Boys | Girls | Target | Boys | Girls | Target |
| 1 | Ushirikiano | 94 | 69 | 300 | 284 | 269 | 600 | 307 | 336 | 750 | 262 | 250 | 700 |
| 2 | Urafiki | 278 | 306 | 600 | 299 | 319 | 700 | 438 | 468 | 950 | 439 | 421 | 1000 |
| 3 | Matumaini | 63 | 18 | 100 | 333 | 279 | 600 | 387 | 421 | 800 | 233 | 184 | 1000 |
| 4 | Undugu | 479 | 489 | 900 | 393 | 434 | 750 | 485 | 406 | 800 | 533 | 525 | 900 |
|  | Sub Total | 914 | 882 | 1900 | 1309 | 1301 | 2650 | 1617 | 1631 | 3300 | 1467 | 1380 | 3600 |
|  | Total (B&G) | 1796 | 1900 | 2610 | 2650 | 3248 | 3300 | 2847 | 3600 |
|  | % Enrolment | 94.5 | 98.5 | 98.4 | 79 |

Table 14: Grade I Enrolment rate – Mtendeli Camp

|  | Name of School | 2000 | 2001 | 2002 | 2003 |
| --- | --- | --- | --- | --- | --- |
|  |  | Boys | Girls | Target | Boys | Girls | Target | Boys | Girls | Target | Boys | Girls | Target |
| 1 | Mtakuja | 1322 | 1194 | 2588 | 1573 | 1442 | 3155 | 1295 | 1157 | 2819 | 1095 | 956 | 2237 |
| 2 | Hope | 1125 | 992 | 2299 | 1384 | 1229 | 2693 | 883 | 814 | 2383 | 824 | 763 | 1656 |
| 3 | Tujikumbuke | 1506 | 1340 | 2896 | 1544 | 1403 | 3007 | 1252 | 1171 | 2332 | 1149 | 1070 | 2289 |
| 4 | Solidarity | 1355 | 1192 | 2673 | 1279 | 1133 | 2499 | 540 | 1293 | 2242 | 903 | 957 | 1891 |
| 5. | Stella | - | - | - | - | - | - | 1012 | 840 | 1683 | 981 | 899 | 1978 |
|  | Sub Total | 5308 | 4648 | 10456 | 5780 | 5207 | 11354 | 5982 | 5275 | 11859 | 4952 | 4645 | 10051 |
|  | Total (B&G) | 9956 | 10987 | 10987 | 11354 | 11257 | 11859 | 9597 | 10051 |
|  | % Enrolment | 96.2 | 96.76 | 94.9 | 95.5 |

# Table 15: School Infra-structures

| CAMP | No. of Classes | Pit Latrine | Community center | Office | Chairs | Tables | Desks | Books |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Const | Renov. | Constr | Renov. | Const | Renov. | Const | Renov. | prod | Repaired | Prod | Repaired |  |  |
| Mtendeli Camp | 126 | 4 | 25 | 0 | 1 | 1 | 10 | 8 | 140 | 11 | 75 | 19 | 192 |  |
| Nduta Camp | 56 | 8 | 80 | 2 |  |  | 3 |  | 34 | 14 | 28 | 2 | 551 |  |
| Total | 182 | 12 | 105 | 2 | 1 | 1 | 13 | 8 | 174 | 25 | 103 | 21 | 743 |  |
| Total actual | 194 | 107 | 2 | 21 | 199 | 124 | 743 |  |

Table 16: Secondary School Parameters (2000-2003)

|  |  | DOVE Secondary School - NDUTA CAMP | Mtendeli Secondary School - MTENDELI CAMP |
| --- | --- | --- | --- |
|  | Name of School | 2000 | 2001 | 2002 | 2003 | 2000 | 2001 | 2002 | 2003 |
|  |  | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls |
| A | Enrollment | 163 | 47 | 277 | 102 | 317 | 89 | 376 | 101 | 358 | 62 | 329 | 58 | 426 | 113 | 360 | 114 |
| B | Attendance | 149 | 41 | 277 | 102 | 312 | 87 | 290 | 100 | 352 | 56 | 322 | 53 | 424 | 108 | 351 | 109 |
| C | Attendance (%) | 91.4 | 87.2 | 100 | 100 | 98.4 | 97.8 | 77.1 | 99 | 98.3 | 90.3 | 97.8 | 91.3 | 99.5 | 95.5 | 97.5 | 95.6 |
| D | Sat for exam | 149 | 41 | 277 | 102 | 312 | 89 | 290 | 100 | 350 | 56 | 322 | 52 | 420 | 109 | 351 | 107 |
| E | Passed Exams | 138 | 39 | 257 | 89 | 299 | 81 | 283 | 98 | 341 | 51 | 302 | 48 | 411 | 103 | 341 | 102 |
| F | % passed | 92.6 | 95.1 | 92.8 | 87.3 | 95.8 | 91 | 97.6 | 98 | 89.7 | 91 | 93.7 | 92.3 | 97.8 | 94.4 | 97.1 | 95.3 |
| G | Drop out | 14 | 5 | 0 | 0 | 5 | 2 | 86 | 1 | 6 | 6 | 7 | 5 | 2 | 5 | 9 | 5 |
| H | Joined HLI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 4 | 1 |

Table 17: Gender and Development - Trend of both gender participation in leadership

positions, social and economic activities

|  |  | MTENDELI CAMP | NDUTA CAMP |
| --- | --- | --- | --- |
|  |  | 2001 | 2002 | 2003 | 2001 | 2002 | 2003 |
|  |  | M | F | M | F | M | F | M | F | M | F | M | F |
| A | Community Leaders | 21 | 17 | 36 | 23 | 39 | 28 | 102 | 29 | 121 | 43 | 132 | 130 |
| B | Food Committee Members | 15 | 7 | 21 | 13 | 27 | 16 | 12 | 3 | 13 | 7 | 18 | 8 |
| C | Peace Committee members | 9 | 6 | 9 | 5 | 4 | 25 | 4 | 7 | 8 | 12 | 14 | 12 |
| D | Health Education Committee | 31 | 13 | 38 | 12 | 43 | 24 | 43 | 12 | 42 | 14 | - | - |
| E | HIV Committee | 7 | 3 | 11 | 08 | - | - | 9 | 8 | 14 | 8 | 17 | 12 |
| F | People Employed at the Camps | 430 | 214 | 437 | 221 | 443 | 261 | 67 | 31 | 79 | 41 | 430 | 175 |
| G | Security Guards | 29 | 19 | 51 | 31 | 58 | 37 | 13 | 4 | 21 | 8 | 54 | 21 |
| H | Engaging in Sports | 6710 | 3007 | 7173 | 4231 | 8673 | 4476 | 266 | 108 | 443 | 237 | 21770 | 1155 |
| I | Engaging in Handcraft | 0 | 107 | 0 | 201 | 2 | 354 | 0 | 26 | 0 | 29 | 2 | 59 |
| J | Running Hair Saloon | 3 | 2 | 11 | 2 | 13 | 16 | 2 | 3 | 13 | 7 | 14 | 6 |

COMMUNITY SERVICES AND  EDUCATION  BASELINE INFORMATION

Name of the Camp: Karago Camp

Name of Respondent: J. Bajumuzi – CSO – Education

Date: 10/12/2003

Table 18: Baseline Information

| Sector | Indicator description | Baseline value at December 2003 |
| --- | --- | --- |
|  | Total Population | 24135 |
| Broad Goal | Number of groups assisting vulnerable individuals | 13 |
|  | Number of refugee actively involved in IGA | 3096 |
|  | Level of literacy at the camp | 76% |
|  | Number of voluntary repatriation in 2003 | 4445 (1145Families) |
| Education | Number of furniture available |  |
|  | Number chairs available | 50 |
|  | Number of tables available | 56 |
|  | Number of desks available | 1249 |
|  | Number of books available | 12,183 |
|  | Number of boys attending primary schools | 3674 |
|  | Number of girls attending school | 3671 |
|  | Pre-School Age Children | Boys:1434 Girls:1578 |
|  | Number of primary schools | 6 |
|  | Number of secondary schools | 1 |
|  | Number of Adult classes | 9 |
|  | Number of people attending adult classes | 496 |
|  | Number of classrooms available (in use) | 88 |
|  | Number of classrooms need rehabilitation | - |
|  | Number of offices available | 4 |
|  | Number of teachers employed | 112 |
|  | Number of pit latrines available | 6 |
|  | Number of pupils passed exams in 2002 | 34 |
|  | Number of pupils sat for exams in 2002 | 103 |
|  | Number of pupils dropped out | 108 |
|  | Number of student joined Secondary School | 27 |
| Micro-project | Number /category of groups supported (Male & Female) Livestock Kiosk Hair Cutting Saloon Tailoring Carpentry Soap Making Hand Craft Restaurant | Male: Female M:928 F:1963 M:12 F: 4 M: 23 F: 0 M: 33 F: 13 M: 17 F: 0 M: 2 F: 9 M: 96 F: 33 M: 6 F: 10 |
|  | Number of individuals supported. | 37 |
|  | Productivity of the supported groups/individuals. |  |
|  | Percentage of the covered groups/individuals. | 60% |
|  | Percentage of the covered individuals. | 70% |
| Support to vulnerable | Number of vulnerable groups – (EVI) | 358 |
|  | Number of unaccompanied minor | 57 |
|  | Number of attached minor | 242 |
|  | Number of Single parents | 1188 |
|  | Number of chronically ill patient | 36 |
|  | Number of Elderly single | 101 |
|  | Number of Disabled | 223 |
|  | Number of orphans | 53 |
|  | Number (per type) of assistance given | 4 |
|  | Type of assistance given | Food, NFI, Counseling |
| Peace and Reconciliation | Number of workshops and training conducted | 59 |
|  | Teaching peace and reconciliation in schools | 12 |
|  | Number of inter camp visit organized | 4 |
|  | Number of peace and reconciliation groups existing in the camp | 9 |
| Gender, HIV/AIDS and SGBV | The number training on Gender issues | 1 |
|  | Number of campaign on gender awareness raising | 10 |
|  | Number of Information Education Communication (IEC) materials disseminated | 15 |
|  | Number of training on Reproductive Health, STI and HIV/AIDS. | 19 |
|  | Number of BCC (Behaviour Change Communication) materials presented. | 25 |
|  | Number of BCC (Behaviour Change Communication) sessions organized. | 60 |
|  | Number of campaign on Reproductive Health/STI and HIV/AIDS | 12 |
|  | Number of campaign on Reproductive Health | 1 |
|  | Ratio of women in leadership position | 86 (24%) |
|  | Number of people attending VCT | 474 |
|  | Number of SGBV Cases reported in 2003 | 193 |
|  | Number of STI in 2003 | 266 |
|  | Number of condoms distributed in 2003 | 5372 |
|  | Number of PLWHA | 3 |
| Capacity Building | Number of staff available | 22 |
|  | Number of micro project officers | 5 |
|  | Number of community based Rehabilitation officers | 1 |
|  | Number of SGBV officers | 2 |
|  | Number of Youth & Culture Officers | 1 |
|  | Number of Women & Gender officers | 1 |
|  | Number of Education Officers | 1 |
|  | Number of staff trained | 150 |
|  | Type of training received |  |
|  | Technical and material supported |  |

Total Population: Karago Camp: 24,135

Children of School going age: Boys: 367 Girls: 3671

Pre-school age children: Boys: 1434 Girls: 1578

COMMUNITY SERVICES AND  EDUCATION  BASELINE INFORMATION

Name of the Camp: Kanembwa Camp

Name of Respondent: G. Nyondo Camp Coordinator

Date: 10/12/2003

Table 19: Baseline Information

| Sector | Indicator description | Baseline value at December 2003 |
| --- | --- | --- |
|  | Total Population | 19718 |
| Broad Goal | Number of groups assisting vulnerable individuals | 18 |
|  | Number of refugee actively involved in IGA | 1720 |
|  | Number of voluntary repatriation between 2002- 2003 | 706 |
| Non formal Education | Pre-school teachers | 27M, 49F |
|  | Number of pre-school pupils | 1376M, 1405F |
|  | Pre-school classroom | 18 |
|  | Pre-school toilets | 17 |
|  | Adult education language training | 348M, 143F |
|  | Literacy training | 123M, 97F |
|  | Vocational training | 329M, 71F |
|  | Non formal education teachers | 62M, 8F |
|  | Number of pupils dropped out btn April 02 to Sept 03 | 160 |
|  | Number of student joined Secondary School | Female |
| Micro-project | Number /category of groups supported (Male & Female) Iron smith Carpentry (6 groups) Tailoring (1 group) Shoe making (1 group) Restaurant (1 group) Hair dressing (2 groups) Bakery (2 groups) Radio repair (2 groups) Bicycle repair (4 groups) Gardening (82 groups) Livestock (43 groups) Soap making (1 group) Soft drink (1 group) Fish farming (2 groups) Local coach making (1 group) Gitar making (1 group) Hand craft (14 groups) | 14 male 55 male 8 (3F,5M) 16 male 8 (6M,2F) 10 female 14 female 48 male 81 (2F, 79M) 1627 (542F,1085M) 390 (179F,211M) 7 (3F,4M) 33 female 22 (5F,17M) 16 male 16 male 167 (90 F, 77M) |
|  | Number of individuals supported. |  |
| Support to vulnerable |  |  |
|  | Number of unaccompanied minor | 25 |
|  | Number of attached minor | 173 |
|  | Number of Single parents | 390 male, 59 female |
|  | Number of chronically ill patient | 34 |
|  | Mentally disabled | 68 |
|  | Number of Elderly single | 14 female |
|  | Number of elderly single un accompanied | 186 |
|  | Number of Disabled | 274 |
|  | Children in need of special attention | 504 M, 433 F |
|  | Extreme vulnerable | 108 |
| Peace and Reconciliation | Number of workshops and training conducted | 3 |
|  | Teaching peace and reconciliation in schools | 3 |
|  | Number of inter camp visit organised | 4 |
|  | Number of peace education meetings | 13 |
|  | Number of peace and reconciliation groups existing in the camp | 4 |
| Gender, HIV/AIDS and SGBV | The number training on Gender issues | 38 meeting, 3 training |
|  | Number of campaign on gender awareness raising | 0 |
|  | Number of training on Reproductive Health, STI and HIV/AIDS. | 40 meetings, |
|  | Number of BCC (Behaviour Change Communication) sessions organized. | 18 meeting, 2 training |
|  | Number of campaign on Reproductive Health/STI and HIV/AIDS | 20 meeting, 3 traing |
|  | Number of campaign on Reproductive Health | 0 |
|  | Ratio of women in leadership position | 336F, 240M |
|  | Security | 35M, 5F |
|  | Sports | 256M, 319F |
|  | Employment | 260M, 99F |
|  | Food committee | 12M, 12F |
|  | Number of people attending VCT | 498 |
|  | Number of SGB Cases reported in 2003 | 117 |
|  | Number of STI in 2003 | 235 |
|  | Number of condoms distributed in 2003 | 10224 |
|  | Number of PLWHA | 5 made public announcement |
| Capacity Building | Number of staff available | 38 |
|  | Number of micro project officers | 1 |
|  | Number of community based Rehabilitation officers | 1 |
|  | Number of SGBV officers | 1 |
|  | Number of Youth & Culture Officers | 1 |
|  | Number of Women & Gender officers | 1 |
|  | Number of Education Officers | 1 |
|  | Number of staff trained |  |
|  | Type of training received |  |
|  | Technical and material supported |  |

Total Population: Kanembwa camp 19718

Children of School going age: Boys: 4830 Girls: 4746

Youth 2644 male, 2501 female

###### Map of project location

# Text boxes

Figure 1