Evaluation e-Library (EeL) cover page

| Name of document | ZMB - SGBV Angolan Refugees 01-05 |
| --- | --- |
| Full title | SEXUAL AND GENDER BASED VIOLENCE (SGBV) ANGOLAN REFUGEE PROGRAM AND SURROUNDING LOCAL COMMUNITY Final Report |
| Acronym/PN | SGBV |
| Country | Zambia (Angolan refugees) |
| Date of report | January 2005 |
| Dates of project | 2004 |
| Evaluator(s) |  |
| External? | No |
| Language | English |
| Donor(s) | UNHCR Bureau for Population and Refugee Migration (BPRM) |
| Scope | Project |
| Type of report | Other (self-reported annual summary report) |
| Length of report | 17 pages |
| Sector(s) | SGBV (sexual and gender-based violence) |
| Brief abstract (description of project) | The project supports the overall multi-agency effort to provide humanitarian assistance, protect human rights and meet basic needs of Angolan refugees in accordance with Humanitarian Charter on Disaster Response Standards which CARE has adopted as a guiding principle for its programming. The main strategy during the year 2004 has been on building and strengthening capacities of beneficiary communities in skills acquisition, information sharing as well as community organization and participation. As the repatriation became a reality, messages on sexual and gender violence reflected on going back home to Angola and the importance of a traveling and settling in a place free from violence. It is hoped that initiatives that has been done around peace building and reconciliation will play a meaningful role in the returnees ‘lives as they go back to Angola. (p.2) |
| Goal(s) | To sustainably reduce incidences of SGBV amongst the refugees in the Nangweshi Camps and surrounding communities. (p.2) |
| Objectives | To raise awareness and sensitize communities on the rights of women and children To strengthen the capacity of formal and informal institutions (i.e. implementing partners) to prevent and respond to SGBV incidences To promote the formation of local and civil society organizations (CSO) to sustainably address SGBV. (p.3) |
| Evaluation Methodology | [Self-report] |
| Results (evidence/ data) presented? | In text and tables |
| Summary of lessons learned (evaluation findings) | Changing attitudes, beliefs and values is a long-term life event. As such SGBV challenges continued to occur. During the year 2004 cases of defilement, Sexual harassment, physical child abuse, early sexual encounters among teenagers, wife battery continued to occur. Despite this, it was however noted during the year that the SGBV Program has continued to empower and enlighten more people than the previous targeted number about the importance of respect for each other’s rights, peace building, co-existence and self-reliance. The SGBV Program has also continued to challenge negative practices and attitudes as well as giving perpetrators and would be perpetrators a time for reflection. (p.3) |
| Observations | Annual report to donor |
| Additional details for meta-evaluation: |
| Contribution to MDG(s)? | 3:Women’s Empowerment / 6: HIV-AIDS |
| Address main UCP “interim outcomes”? | Gender Equity |
| Were goals/objectives achieved? | 1=Yes |
| ToR included? | No |
| Reference to CI Program Principles? | Indirectly (Humanitarian Charter on Disaster Response Standards) (p.2) |
| Reference to CARE / other standards? | No |
| Participatory evaluation methods? | No |
| Baseline? | No |
| Evaluation design | Formative (process) |
| Comment | Example of self-evaluation in form of annual report |

SEXUAL AND Gender Based VIOLENCE (sgbv)

Angolan Refugee Program AND SURROUNDING LOCAL COMMUNITY.

Final Report

# Agreement Number SPRMCO04CA035

SUBMITTED TO BUREAU FOR POPULATION AND REFUGEE MIGRATION (BPRM)

### January 2005

1.PROJECT DESCRIPTION

1.1Overall Project Goal

The overall goal of this project is to sustainably reduce incidences of SGBV amongst the refugees in the Nangweshi Camps and surrounding communities. The project supports the overall multi-agency effort to provide humanitarian assistance, protect human rights and meet basic needs of Angolan refugees in accordance with Humanitarian Charter on Disaster Response Standards which CARE has adopted as a guiding principle for its programming.

1.2 Guiding Strategy

The main strategy during the year 2004 has been on building and strengthening capacities of beneficiary communities in skills acquisition, information sharing as well as community organization and participation. As the repatriation became a reality, messages on sexual and gender violence reflected on going back home to Angola and the importance of a traveling and settling in a place free from violence. It is hoped that initiatives that has been done around peace building and reconciliation will play a meaningful role in the returnees ‘lives as they go back to Angola.

1.3 Reporting period

This report covers activities implemented between January 04 and December 04, covering the entire contract period. This contract represented the third and final BPRM contract for CARE’s SGBV programming in Nangweshi. Through consultation with UNHCR by December 31st 2004, SGBV activities were handed over to Africa Humanitarian Action (AHA) an implementing partner dealing with health services in the two refugee camps. BPRM provided agreement to handover all assets to UNHCR for continued use in refugee programs in Zambia.

1.4 Beneficiaries

The project targets the entire refugee population in the two Nangweshi camps and the surrounding villages. This report outlines activities undertaken in the two refugee camps and surrounding local communities of Mbume, Matebele, Nangweshi and Kaanja. The year 2004 witnessed peace in Angola being a reality and repatriation process taking off. There was a slight change in population in the two refugee camps. About 6,216 were repatriated to different parts of Angola but mainly from Lumbala ng’imbu, Moxico, Cazombo and Huambo provinces. According to UNHCR/Government statistics as of December 2004, the population in the two camps stood at about 23,397.

1.5 Programming Summary

Awareness raising in the year aimed at strengthening the capacities of the SGBV support groups in the camps and local villages with skills, knowledge and information sharing that will help them prevent and respond effectively to incidences of SGBV. Participating in campaigns in international and local days strengthened the sense of community belonging.

Training for year 2004 aimed at strengthening the capacities of the SGBV support groups in the camps and local villages with skills that will help them deal effectively with incidences of SGBV. Training was done in such areas as: Zambian law, refugee rights, duties and obligations, human rights, child abuse in schools, gender violence in homes community and in groups. Other issues related to: community organization, participation and development, income generating for groups, the role of community leaders in prevention and response to gender violence, participatory rural appraisal, repatriation, peace building and conflict resolution within families and communities. The approach was to equip the support groups with skills that help rebuild confidence in families and communities as well as promoting peace.

Conducting community gender education side by side with mobile/juvenile court sessions has been one of the highlights in the year. Other activities relates to holding meetings, with support groups, implementing partners, receiving cases, making referrals and follow-ups on SGBV cases and of juveniles on probation as well as providing counseling to survivors and perpetrators.

Changing attitudes, beliefs and values is a long-term life event. As such SGBV challenges continued to occur.  During the year 2004 cases of defilement, Sexual harassment, physical child abuse, early sexual encounters among teenagers, wife battery continued to occur. Despite this, it was however noted during the year that the SGBV Program has continued to empower and enlighten more people than the previous targeted number about the importance of respect for each other’s rights, peace building, co-existence and self-reliance. The SGBV Program has also continued to challenge negative practices and attitudes as well as giving perpetrators and would be perpetrators a time for reflection. Men and women have voluntarily sustained their support groups and established informal support mechanisms within their circles. Village headmen from the surrounding communities have shown more interest after being trained in such issues as promotion of human rights, women’s rights, children’s rights, group minority rights, counseling and are reaching out to communities beyond the coverage area. Recreation activities were strengthened and youths continued to be active through sports entertainment, information sharing on reproductive health with community. However because of anxieties caused by repatriation, there was a drop in reported cases, which was noted in the two refugee camps in the third and fourth quarter.

The greatest challenge in the year 2004 lay in the fact that the while the information about the program had gone beyond the coverage area, it was not possible to reach out to these communities. On a positive note, it was noted however that program assistants and other local and civic leaders were making efforts to reach out despite the distances, which in some instances were more than 30 to 40 kms. from Nangweshi. The project went beyond the coverage area in SGBV sensitization to cover Chibale, Mbeta Island, Naliyo, and the Kalongola ferry point considered to be a high-risk area in SGBV incidences because of the long history of being a central place for humanitarian and refugee work.

1.6 Objectives

To meet the overall goal the project established the following objectives;

- To raise awareness and sensitize communities on the rights of women and children

- To strengthen the capacity of formal and informal institutions (i.e. implementing partners) to prevent and respond to SGBV incidences

- To promote the formation of local and civil society organizations (CSO) to sustainably address SGBV.

1.7 Activities and Achievements (NB: Indicators are for the entire project duration)

Output 1: Implementing partners, and educators/facilitators support to project implementation increased.

| Indicators | Activity & Achievements | Challenges | Lessons learnt | Next Quarter |
| --- | --- | --- | --- | --- |
| Number and types of training of trainers conducted and number of people trained (Gender disaggregated data). Target: 24 trained in 12 trainings/6 modules. Number of modules and translations. Target 6 modules. | Seven in–house SGBV related trainings provided to Program assistants and other refugee assistants. Other Trainings provided were as follows: Psycho – social counseling Reproductive health and gender violence Participatory Rural appraisal/Income generating activities. Group formation cohesion community organization and development for community groups Partnership in prevention and response to Sexual and Gender Based violence. Peace education and life skills for teachers and church leaders The role of teachers and Neighborhood watch in preventing violence Empowering skills for women Support groups The role of Village Headmen church leaders The role of Traditional dancers and peer educators in prevention and response to gender violence The functions and conduct of local courts customary law and the rights of women. Six modules on Community Psych-social counseling, SGBV & Human rights, Police response to SGBV and the role of peer educators in response prevention, the role of teachers & neighborhood watch translated into Local Silozi, Umbundu and Portuguese. | Program Assistants leaving to go to colleges’ and repatriating meant that one had to keep recruiting new ones. Demand for more reading and translated materials in local Umbundu, Silozi and Portuguese. | That SGBV volunteers groups can work together to solve their own problems Training of trainers and regular in-house training provides a forum for skills acquisition. That partnership in SGBV activities assist in sharing information and resources during trainings. Translated modules in local languages serves as an added advantage for understanding the SGBV related issues well. | Activities handed over to another Implementing partner- African Humanitarian Action (AHA) |

Output 2: Community traditional, religious and section leaders/block leaders trained in basic psychosocial counselling.

| Indicators | Activity & Achievements | Challenges | Lessons learnt | Next Quarter |
| --- | --- | --- | --- | --- |
| Number of leaders trained. Target: 50 Number of psychosocial support mechanisms established and functioning. Target: 6 | 83 Village headmen, block, section, male support group and church leaders trained and re- trained in prevention and response to SGBV incidences and psycho -social counseling. An average of two meetings held in each area with refugee leaders village headmen and women support members to review gaps in response services. Three informal Support mechanisms established within the refugee and local communities to support survivors of SGBV. (Some leaders offered shelter for a night to survivors and perpetrators of violence and escorting them to the police or SGBV center.) | That there is need to take time to plan and reflect on concept of abuse of women and Children, which border on challenging the patriarchy, for example traditional practices still put women in vulnerable position open to abuse. Customs and practices that still perpetuate abuse of women and children and cannot be changed overnight. Some community leaders are being threatened by some family members of perpetrators for providing shelter to victims of wife battery. Repatriation challenged some efforts gained so far as it was not possible to establish long-term supportive structures in the camp. | That Community leaders need regular meetings and training for them to be effective in managing communities. That community leaders are being can be effective in changing attitudes and spearheading behavioral change if they are equipped with information. That community leaders and structures can effectively offer support services and shelter victims of gender violence which can be strengthened by being trained as psychosocial counselors. | SGBV activities handed over to AHA another implementing partner. |

Output 3: SGBV reporting, coordination and monitoring increased and strengthened at camp and local village levels.

| Indicators | Activity & Achievements | Challenges | Lessons learnt | Next Quarter |
| --- | --- | --- | --- | --- |
| Percent of IPS utilizing standard reporting & documentation system. Target: 75% Percentage of SGBV cases reported with follow up action instituted. Target: 80%+ | 70% of IPs (Police, Health, and UNHCR) are utilizing the standard reporting & documentation system. An average 12 meetings were held with different groups in the camps and local communities each month. 75 % of the SGBV cases reported were followed up and action instituted. | Improving the documentation system and correct use of the incident report form among all the Implementing Partners to capture SGBV cases. Implementing partners often complain about the amount of time to be spending on filling the incidence report form. Fear of revenge from perpetrator’s families preventing some survivors from reporting SGBV incidences. Some individuals wanting to escape justice by trying to interpret SGBV acts using outdated customs and traditions, for example some ethnic groups had previously allowed sex with family members and only required cleansing by paying slaughtering an animal. | That regular meetings and re-training with all stakeholders help in learning and re-planning how to capture SGBV incidences and follow ups. That SGBV dimensions change with the changing of life events. For example some disputes arise from the fact one partner might not be ready to repatriate and may fight with her/his spouse over who should have custody of children during repatriation. That partnership assists in preventing and responding timely to acts of SGBV. | Activities handed over to another Implementing partner- African Humanitarian Action (AHA) |

Output 4: Medical, legal and judicial systems supported to address SGBV cases and increase conviction rates.

| Indicators | Activity & Achievements | Challenges | Lessons learnt | Next Quarter |
| --- | --- | --- | --- | --- |
| Number of cases addressed through formal systems. Target: 300 Number successful convictions. Target: 15% Number of Mobile courts. Target: 2 | 204 SGBV cases (74 SGBV cases from the two camps & 130 SGBV cases from the local surrounding community) & 92 non-SGBV addressed through the formal system. 3 Defilement, 3 attempted defilement 2 Attempted rape, 1 incest, 4 sexual harassment 9 threatening violence to family, 21 child abuse/emotional violence 21 child abuse, 2 child abuse leading to death, 98 Wife battery, 24 husband battery, 6 early pregnancy early, 1 early marriage 30 Family Neglect/child custody. CASES: (SEE ANNEX 1,2,3,4,5,6 &7) 8 males & 1 female were handed prison sentences for SGBV acts. 3 male Juveniles handed down 2 year probationary sentences each. 2 Juveniles acquitted after jointly charged. 5 SGBV cases still pending and are before the courts. 1 before high court 4 before the magistrate court. 62 people received treatment arising from SGBV acts. 81 received counseling from the police, community leaders, and SGBV center. 47 people were arrested for SGBV acts. 2 mobile/ Juvenile court sessions facilitated. | Some men still feel there is over-dramatizing as issues of sex and sexuality should be private and not be a subject of public debate. High rate of men having multiple female partners leading to spouse fighting. Some family members still want to protect perpetrators by trying to withdraw cases and contesting that offenders are too old to be prosecuted and if found guilty, go to prison. Some family members still want to shield perpetrators by not reporting SGBV acts opting to settle the case privately Some perpetrators abusing the freedom availed to them by not turning up for court after being on police bond or court bail. | That the formal system with the assistance of the informal networks also helps in making sure that SGBV cases are not hidden but addressed accordingly. That most women are continuing in abusive relationship because of lack of information, high level of illiteracy, strict divorce rights in the name of tradition and lack of economic independence. That quick deliverance of justice through courts and securing of convictions also serve as deterrence to would be perpetrators. That there is greater goodwill and understanding now by the Police and Judiciary who give priority to investigation and prosecution of defilement cases. That mobile court serves as a reminder and educator on the importance of self-control as well as respect for human dignity. | SGBV activities handed over to AHA another implementing partner. |

Output 5: Capacity and membership of community groups and clubs strengthened and increased respectively- focus on men and youth groups.

| Indicators | Activity & Achievements | Challenges | Lessons learnt | Next Quarter |
| --- | --- | --- | --- | --- |
| Percent increase in membership numbers. Target: 20% Number of activities undertaken by groups/club members. Target: 30% Number of people receiving training. Target: 1200 Percent of groups forming support structures. Target: 25% | Three Local Groups formed in Mbeta Island/ Nangweshi, Naliyo/ Matebele, Chi bale- Mbume area. Total 40% An average 586 men and youth were active in program organization this year. Five Activities–Supportive counseling, referrals. Organizing gender/HIV/AIDS workshops, fund raising for group activity, as well as general Community Gender Sensitization. Trained and workshops are 1,174 89 Church leaders, 21 Village headmen, 217 Teachers, 306 Neighbor hood watch members 51 Block, section and camp counsel 62 psycho- social counselors 240 women support groups, 70 Traditional dancers 12 Kalingindo Musical Bands. 20 Peer educators 30 Female footballers 29 Program assistants. 20 implementing partners 7 health personnel 15 % of groups forming informal supportive structures. | Changing some negative attitudes in some men towards women and girls for example this year, a 72-year-old man beat his family badly because the wife was not ready to have sex with him. Reaching all key community structures, groups and networks, sharing information, skills and induce behavioral change. Some men still feel they have the right to have sex with their wives anytime which often led to violent fights in homes while some men and women still feel wife battery should not be a subject of public debate. Poverty increases the vulnerability of girls and women leading to sexual exploitation. The formative stage of the support groups makes them less effective in handling SGBV issues. | That using men/youths to target other men/youths can be effective in changing attitudes. That regular meetings with community members are good for reflection on SGBV acts. That partnership in handling SGBV acts is effective in prevention and response. That teachers and other community structures can be an effective channel of communication on SGBV issues to the community. That groups can effectively organize themselves around issues of prevention and response to gender violence including Community organization and participation. | SGBV activities handed over to AHA another implementing partner. |

Output 6: Availability and Access to local language IEC resource materials increased.

| Indicators | Activity & Achievements | Challenges | Lessons learnt | Next Quarter |
| --- | --- | --- | --- | --- |
| IEC materials available in suitable languages. Reaching messages/ Materials disseminated. Target: 90% Percent of groups implemented campaigns Target: 75 | 2,000 Posters prepared in Portuguese 500 on child abuse, 500 on rape, defilement, 500 0n Domestic violence .500 wife battery International Women Day Cerebrations 50 booklets on CRC in Silozi, English and Portuguese, 1,500 brochures with messages on the promotion of women’s rights distributed. 9 promotion sessions conducted using traditional dancers, youth footballers, gymnastics, and Kalingindo music band. Ana average of 9,407 people attended the awareness campaigns in different areas. An average of 2,563 youths: 3,689 males & 3,255 females attended recreation activities. World Refugee day cerebrations. 1 500 SGBV Brochures translated from English to Portuguese and Silozi Languages and distributed to the community. 2,000 leaflets 1,000 on Child abuse, 1,000 on reproductive health distributed to the youths, 60%, 2000 CEDAW articles translated in local Silozi Portuguese language and distributed to the community.3, 000 HIV/ AIDS Cartoons translated from English and Portuguese and distributed to the community. 6 SGBV promotional sessions conducted using Kalingindo musical band and traditional dancers. An average 6,154 people participated in the world refugee day promotion sessions. 16 days of activism and World AIDS Cerebrated in each of the six centers. Activities: Songs and dance, Drama, poems quiz, football matches. 6 Promotional sessions conducted. 1,400 Attended the promotional campaigns in the two camps and the local villages. 500 red ribbons & 120 pieces of materials (chitenge) distributed in the local villages. 500 SGBV leaflets, 1000 leaflets on women, children and HIV/AIDs translated from English to Portuguese and Silozi Languages. 210 youths attended the candle light service in the main camp. 45% materials distributed 40% represent self-planning group implemented campaign on issues of SGBV from the two camps and local centers. | More adults requiring reading materials translated in local Silozi, Umbundu and Portuguese languages. Demand for more picture –story brochures with direct messages. Fighting stigma and reducing the rate of HIV/AIDS infection especially in the local community and prevent new infection in the refugee camps. Community Individuals using their Positions to abuse women in the guise of culture. For example a traditional medicine man who demands marriage as payment for treating a woman client. | That posters and cartoons with messages of HIV/AIDS prevention motivates communities to continue reflecting on the messages. That leaflets are good channel for reaching out to large audiences. Community groups need a little more information on SGBV/HIV/AIDS and facilitation around developmental issues and promotion of human rights in the community. That international and national days save as a massive communication and awareness tool to communities That refugee leaders, village headmen and women are a use full communicating tool in empowering fellow community members with information on prevention and response to SGBV including caring for those already infected with HIV/AIDS. | SGBV activities handed over to African Humanitarian action (AHA) another implementing partner. |

**CEDAW (Convention on the Elimination of All forms of violence against Women.)

** CRC (Convention on the Rights of Children.)

Output 7: Formation and capacity of local SGBV oriented civil society organizations (CSO) supported.

| Indicators | Activity & Achievements | Challenges | Lessons learnt | Next Quarter |
| --- | --- | --- | --- | --- |
| Number of local and CSOs formed and functional. Target: 2 Number of SGBV activities implemented by local CSOs: Target: 5 | 4 local CSO formed and functional and are able to organize themselves and provide services on issues of prevention and response to Sexual and Gender Based Violence. 4 Activities: Counseling and referrals. Community gender education Youth Education, Sports and recreation, Group formation, support networks and fund raising for groups. | Repatriation and preparation for going home made some refugee individuals not to be active in groups. Sustaining the group activities in view of repatriation and handover of SGBV activities to another partner. Some individuals especially in newsgroups feel they should be given money to sustain themselves. | That organized groups can effectively respond to Sexual and Gender violence (SGBV) That community weekly meeting helps to plan activities and bridge gaps around prevention and response to sexual and gender based violence. | SGBV activities handed over to (AHA) another partner. |

Output 8: SGBV Practices and Programming amongst UNHCR implementing partners improved.

| Indicators | Activity & Achievements | Challenges | Lessons learnt | Next Quarter |
| --- | --- | --- | --- | --- |
| Number of IPS adopting best practices and standards. Target 5 Number of training during exchange visits. Target: 5 visits | 5 IPS are utilizing standard reporting- UNHCR, Health, Police, Social Welfare and the Judiciary. 1 planning workshop with UNHCR Implementing partners and government departments. 2 regional workshops by UNHCR and UNICEF/Zambian Government held to share best practices. 1 training workshop on sexual and gender based violence organized by Young Women Christian Association (YWCA.) 2 visits to the YWCA Drop –In- Center. 1 meeting and visit organized by YWCA on the formation of male support groups to spearhead the response and prevention of Sexual and Gender Based Violence in western province of Zambia. | High turn over of Program assistants from SGBV unit and partners repatriating and leaving for colleges creates the need to keep recruiting new ones. Strengthening the men’s network on the fight against violence against women. | That SGBV volunteers are able to work effectively as program assistants. That holistic approach to combating SGBV helps in capturing information and assists in tracking down perpetrators. That partners have improved on their information capturing and response to SGBV incidences That more men now understand that SGBV is every one’s concern and forming support networks to fight Gender Violence. That the workshop conducted by YWCA was an eye opener, educative and a reflective line for the local court justices and other personnel from government departments. | SGBV activities handed over to AHA another partner. |

##### 3.4 Other issues related to planned activities and achievements

This year the SGBV program has been able to cultivate a positive attitude among the beneficiaries towards community organization, participation and ownership of the program. Through continuous capacity building, re-training and meetings, the project was able to promote activities aimed at behavioral change. Other activities this year gave members a community reflection on negative images and attitudes about women and children, which often acts as a hindrance to project implementation. Despite the anxieties about the handover of activities to another partner and repatriation, the refugee community and local communities continued to participate in different SGBV activities.

The SGBV program continued to cooperate and work with other stakeholders in the provision of services to the target population.  The year 2004 has seen greater, partnership, networking and sharing of notes and information among Implementing Partners and government departments on SGBV issues. Specifically:

- UNHCR provided the overall protection to survivors and perpetrators, as well as guidance in the refining of the multi-sectorial protocols, guidelines and the use of incident report form (IRF). In addition, UNHCR provided the general program monitoring and evaluation through their protection units and community services. UNHCR organized a Regional workshop on the management of HIV/AIDS/SGBV in refugee camps.

- The Government of Zambia through its numerous departments rendered considerable service to the SGBV program and remains a vital partner.

  - Office of the Refugee Commissioner through the Refugee Officer (RO) provided security, policy framework and guidelines on the handling of refugees as well as encouraging co-existence with the local communities.

  - The Ministry of Agriculture and Cooperatives provided facilities for office space for Nangweshi and Kaanja centers. Office space at the farmers training center was also extended to facilitate the holding of mobile court sessions.

  - The Judiciary department through the Magistrate court provided legal justice the survivors and perpetrators as well as dispension of justice by facilitating the holding of the mobile court system.

  - The magistrate also provided trainings in conjunction with Young Women Christian Association (YWCA) for 21 village headmen in Human rights, Women’s rights Children’s rights including the role of Village headmen in prevention and response to Sexual and Gender Based Violence.

  - The police provided counseling and security to survivors and perpetrators. In addition the police facilitated the provision of legal justice through prosecution of the cases.

  - Ministry of community Development and Social Welfare gave support services to survivors and represented the Juveniles and presented documents for the court.

  - The Ministry of Health specifically Senanga District Hospital provided medical services to referral cases of survivors and perpetrators.

- Cooperation with other Non-Governmental Organizations.

  - The African Humanitarian Action (AHA) provided medical services, counseling and other support services to survivors and perpetrators in the camp and surrounding local communities.

  - The Christian Outreach for Relief and Development (CORD) and Jesuit Refugee Service (JRS) provided community services to the target population as well as the integration survivors.

  - Young Women Christian Association (YWCA) facilitated the training of support groups in identifying and prioritizing development activities in their communities.

  - Links strengthened with Shangombo women catholic league and the provincial gender focal person.

  - The Village Headmen and local civic leaders supported Sexual and Gender Based Violence (SGBV) Program by giving support services to survivors, counseling, holding meetings, sharing information and reaching out to communities beyond our coverage area.

ANNEX 1:SGBV Cases received from the two camps and local community:

| Cases | Frequency | Referred to Police | Referred to clinic | Referred to community leaders | Total | Case result /out come |
| --- | --- | --- | --- | --- | --- | --- |
| Defilement | 3 | 3 | 3 | 0 | 3 | Perpetrator was released on bond pending court appearance. The girl is pregnant. |
| Attempted defilement | 3 | 3 | 3 | 0 | 3 | In the hands of the police |
| Incest | 1 | 1 | 0 | 0 | 1 | Pending before high court |
| Attempted rape | 2 | 2 | 0 | 0 | 2 | In the hands of the police |
| Sexual Harassment | 4 | 4 | 0 | 0 | 4 | One case registered as incest last quarter is not incest but sexual harassment. |
| Child Abuse /Death by strangulation/beating | 2 | 2 | 2 | 0 | 2 | The uncle and father to the victims are in custody awaiting court appearance. |
| Child Abuse/ Emotional violence | 21 | 0 | 0 | 18 | 21 | The section leaders counseled the parents/guardians. Who pledged not to repeat the actions? |
| Wife battering/Emotional/psychological violence | 98 | 42 | 24 | 48 | 98 | Counseling was done at the police station (victim Support Unit community services and SGBV center. |
| Husband Battery | 24 | 5 | 1 | 13 | 24 | Parties received counseling at the SGBV office Section leaders, Village Headmen and referred to UNHCR and Community Services for monitoring. |
| Threatening violence to spouses / family | 9 | 3 | 0 | 9 | 9 | Referred to Police and community leaders for counseling |
| Family neglect/Child custody | 30 | 0 | 0 | 9 | 30 | 7 cases referred to UNHCR. |
| Early pregnancy | 6 | 0 | 5 | 0 | 6 | Referred to the Health center for monitoring |
| Early Marriages | 1 | 0 | 0 | 1 | 1 | Parents |
| Total | 204 | 65 | 38 | 101 | 204 |  |

ANNEX 2:  Non-SGBV cases from the two camps and the local community.

| Cases | Frequency | Referred to Police | Referred to community leaders | Resolved |
| --- | --- | --- | --- | --- |
| Theft | 40 | 21 | 0 |  |
| Property destruction | 3 | 0 | 1 | 1 |
| Suspected witchcraft | 3 | 2 | 1 | 3 |
| Separation of cards | 3 | 0 | 0 | 3 |
| Public insults | 4 | 2 | 3 | 3 |
| TOTAL | 53 | 25 | 5 | 10 |

Annexe: 3 SGBV case pending before the High Court in Mongu.

| NO | Type of case | Ages /Sex of survivor | Nationality Of Survivor | Age/Sex of Perpetrator | Nationality of perpetrator | Period of Occurrence | Case result/out come |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Incest | 14 | F | Zambian | 50 | M | Zambian (Father to the survivor) | Several repeated acts between Nov 02 to May 03 | Pending before High Court |

Annex: 4 SGBV pending before the magistrate court in Senanga.

| Year | NO | Type of case | Ages /Sex of survivor | Nationality of Survivor | Age/Sex of Perpetrator | Nationality of perpetrator | Period of Occurrence | Case result/out come |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2003 | 1 | Attempted defilement | 4 | F | Angolan | 45 | M | Angolan | 03 Nov 03 | Pending (Perpetrator did not show up for court - Believed to have gone back to Angola. His family is still in Nangweshi refugee Camp.** |
| 2004 | 2 | Physical abuse/strangulation/ murder | 12 | F | Angolan | 39 | M | Angolan | April 04 | Pending, awaiting instructions from Director of Public Prosecutions. (DPP) |
| 2003 | 4 | Indecent Assault | 23 | F | Zambian | 22 28 | M M | Zambians | May 03 | Pending before court |
| 2004 | 5 | Murder (wife) | 48 | F | Zambian | 48 | M | Zambian | May 04 | Pending, awaiting instructions from the director of public prosecutions (DPP) |

Annexe: 5 SGBV cases that secured custodial sentences from January 04 to December 04.

| Year | NO | Type of Case | Age/Sex of Survivor | Nationality of Survivor | Age/Sex of Perpetrator | Nationality of Perpetrator | Period of occurrence | Case outcome |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2004 | 1 | Defilement | 12 years | Angolan | F | 69 years | M | Angolan | Jan 2004 | 5 Years imprisonment |
| 2004 | 2 | Defilement | 12 Years | Angolan | F | 59 | M | Angolan | Jan 04 | 5 Years imprisonment |
| 2004 | 3 | Defilement | 14 Years | Angolan | F | 35 | M | Angolan | Feb 04 | 5 Years Imprisonment |
| 2004 | 4 | Un lawful wounding | 12 Years | Angolan | F | 38 | M | Angolan | Feb 04 | 3 and half years Imprisonment |
| 2004 | 5 | Un lawful wounding | 39 | Zambian | M | 54 | F | Zambian | May 04 | 18 months imprisonment |
| 2004 | 6 | Rape | 22 Years | Zambian | F | 21 | M | Zambian | Sept 03 | 5 Years Imprisonment |
|  |  |  |  |  |  | 21 | M | Zambian | Sept 03 | 5 Years Imprisonment |
|  |  |  |  |  |  | 18 | M | Zambian | Sept 03 | 5 Years Imprisonment |
| 2004 | 7 | Indecent Assault | 29 Years | Zambian | F | 32 | M | Zambian | July 03 | 5 Years Imprisonment |

Note: There are no recorded case to show that a refugee committed an SGBV act against a local or a local against a refugee.

Annex 6: Juveniles as offenders.

Non- SGBV cases tabled during mobile/ Juvenile court sessions in July 2004.

| NO | Type of case | Period of Occurrence | Nationality of accused | Sex /age of accused | Case out come |
| --- | --- | --- | --- | --- | --- |
| 1 | Theft | 2004 | Angolans (Jointly Charged.) | 15 | M | 2 years probation (See welfare Report) |
|  |  | 2004 |  | 16 | M | 2 years Probation |
|  |  | 2004 |  | 16 | M | Acquitted |
| 2 | Breaking into a building and committing a felony | April 2004 | Angolan | 15 | M | Acquitted |
| 3 | Breaking into a building | May 2004 | Zambian Jointly charged | 15 | M | 2 years probation (See social welfare report) |
|  |  |  |  | 17 | M | Acquitted |

Annex 7:Non – SGBV cases- Adult Offenders:

Non -SGBV cases tabled during the mobile court in July 2004.

| NO | Type of case | Nationality of accused | Sex of perpetrator | Case outcome |
| --- | --- | --- | --- | --- |
| 1 | Burglary &Theft | Zambian | M | 3 months imprisonment |
| 2 | Stock Theft | Zambian | M | 5 years imprisonment |
| 3 | Criminal trespass | Zambian Zambian | M M | 18 months imprisonment. |
| 4 | Theft | Zambian | M | 3 months imprisonment |

| NO | Type of case | Nationality of accused | Sex of perpetrator | Case outcome |
| --- | --- | --- | --- | --- |
| 5 | Stock theft | Angolan | M | Adj |
| 6 | Stock theft | Zambian | M | Adj |
| 7 | Stock theft | Zambian | M | Adj |
| 8 | Stock Theft | Zambian | M | Adj |
| 9 | Stock theft | Zambian | M | Adj |
| 10 | Stock theft | Zambian | M | Adj |
| 11 | Stock theft | Zambian | M | Adj |
| 12 | Stock theft | Zambian | M | Adj |
| 13 | Un lawful Possession of prohibited articles | Zambian | M | Adj |

| NO | Type of case | Nationality of accused | Sex of perpetrator | Case outcome |
| --- | --- | --- | --- | --- |
| 14 | Stock theft | Angolan | M | Withdrawn |
| 15 | Stock theft | Zambian | M | Withdrawn |
| 16 | Stock Theft | Zambian | M | Withdrawn |
| 17 | Stock Theft | Zambian | M | Withdrawn |
| 18 | Un lawful Possession of Prohibited articles | Zambian | M | Withdrawn |
| 19 | Stock Theft | Zambian | M | Withdrawn |