## Household Livelihood Support (HLS) Project

Project Location: Tetovo Area, Macedonia

PN#MK001 FC #KS107

CIDA/IHA #4160/MK

Contract Agreement signed on March 22, 2002, FAX Note 7671

Grant of CAN$ 500,000.00 to CARE Canada

# Mid-term Evaluation Report

by Guy Dionne, P. Eng. & Agr.

CARE Regional Technical Advisor

for Eastern Europe

December 6, 2002

Project Timeframe and Reporting Period: 		from 2002-03-22 to 2003-04-30

(Originally the project was designed to end by:		2002-12-31

Deadline for Reporting Submission:			2003-06-15

Contact Persons:

CIDA		Director General, International Humanitarian Assistance Program

Multilateral Programs Branch

Canadian International Development Agency (CIDA)

200 Promenade du Portage, Hull, Quebec, Canada K1A OG4

Canadian Embassy, Office in Macedonia

Head of Office

Mitropilit Teodosie Gologanov 44, 1000 Skopje, Macedonia

Tel.: 389 (2) 125-228, FAX 389 (2) 226-5777

CARE Canada		Desk Officer, Stefan Paquette, stefan@care.org

Headquarters		6 Antares Drive, Ottawa, Ontario, Canada

Tel.: (613) 228-5641, FAX (613) 226-5777

CARE			Country Director, Nicholas Webber, webbern@care.org

Country Office		Metohija Street 5, 38000 Pristina, Kosovo

Tel.: 381 (38) 222-435 or 243-546, FAX 381 (38) 225-7666

Project Manager, Ljubomir Dimovski, dimovskil@unet.com.mk

Technical Advisor, Guy Dionne, guy.dionne@oricom.ca

Maksim Gorki 20/3, 1000 Skopje, Macedonia

Tel.: 389 (2) 222-229, FAX 389 (2) 214-635

Table of Contents

1. Introduction								 3

2. Mid-term Evaluation							 4

2.1 Background of the Mid-term Evaluation			 4

2.2 Terms of Reference						 4

2.3 Methodology						 5

2.4 Limitation							 8

3. Background								 9

3.1 General Context						 9

3.2 CARE Macedonia						 9

3.3 CARE Macedonia’s Livelihood Support (HLS) Project		 9

3.4 Appropriateness of Project Design 				 9

4. Review of all Project deliverables					10

4.1 Project Objectives 						10

4.2 Output/results and indicators					11

4.3 Beneficiary Selection					12

4.5 Project Activities, Timeframe and Responsibilities		17

4.6 Visibility							23

4.7 Conditionality, Risks & Assumptions				25

5. Project Effectiveness & Efficiency					26

5.1 Management						26

5.2 Internal Control						27

5.3 Budget and Financial Projections				28

6. Lessons Learned							30

7. Conclusion and Recommendations					31

Annexes

Annex I:  HLS Project - Plan of Operation			32

1. Introduction

This Mid-term Evaluation reports findings and lessons learned from the operation of the Household Livelihood Support (HLS) Project in Macedonia. HLS Project was funded by CIDA International Humanitarian Assistance (IHA) Programme and executed by CARE Canada through CARE Macedonia. The report summarizes the achievements up-to-date and the operations of the HLS implementation (July to November 2002) in the Tetovo Areas.

The purpose of this mid-term Evaluation is to document the array of experiences from the field and to recommend improvements to the project execution team.  A specific focus was brought in analysing all project management functions and internal control procedures.

The document is divided in five main sections: the methodology used, a brief description of the HLS project, a review of all project deliverables, an analysis of project effectiveness & efficiency and the lessons Learned.

We hope the recommendations contained in this publication can be a useful framework for guiding the project team. It may also serve CARE as to build an argument in favour of its regional re-organization in Eastern Europe and the nationalization of its management personnel. It is hoped that lessons learned will be helpful not only for the field workers, but also for other CARE offices.

2. Mid-term Evaluation

The evaluation of the CARE Livelihood Support (HLS) Project, a small-scale income generating activities project, was carried out from 02/12/02 to 07/12/02 at mid-term of the project end. Methods used for the evaluation include review of project records and interviews with CARE staff, 4 beneficiary households and 1 representative from the local authorities.

The limited time available and the nature of this mid-term evaluation brought its major focus on internal practices and ways to improve delivery and its deliverables. The collection and analysis of accurate data especially with regards to transparency was a priority. The Project Plan of Operation was reviewed and its clarity facilitated the process of this CARE internal evaluation

2.1 Background of the Mid-term Evaluation

The terms of reference of this mid-term evaluation were established in order to insure that all deliverables and internal project procedures are contributing towards the achievement of all project deliverables outlined from the project plan of operation available in Annex I.

On November 1, the first period of the project had been finalized. Also all preparation elements for the next two periods were completed. Within the framework of this evaluation, CARE Regional Technical Advisor was requested to review the conduct of the operations up-to-date and to provide recommendations for project improvements that can positively guide its completion. The evaluator wants to underline that the clarity of the terms of reference were highly appreciated.

2.2 Terms of Reference

CARE Regional Technical Advisor was given the following Terms of reference, which were fold in six parts: tasks and outputs, coordination with other projects and programs, duration of the assignment, experience and qualifications of consultant, reporting obligations, and all services and facilities to be provided by the client.

# Tasks and outputs:

| TASK 1 | OUTPUTS |
| --- | --- |
| Evaluate the results of the first phase of the project “Distribution of Emergency Agricultural Kits (EAK)” in respect of: The process of Identification of the EAK; The process of identification of project beneficiaries; The process of procurement of EAK; and The process of distribution of EAK. | Prepare mid-term evaluation report for the finalization of the first phase of the project. |
| TASK 2 | OUTPUTS |
| Evaluate the plans and recommend improvements for the second period “Training” and third period “Distribution of Income Generation Kits (IGK)” in respect of: Training plan; The process of preparation of guidelines for the training; The process of Identification of the IGK; and The process of identification of beneficiaries for the IGK. | Prepare recommendations for the implementation plan for the second and third phase of the project |

### Coordination with other projects and programs

International: 	The consultant will report directly to the Head of delegation of CARE Kosovo, Nick Weber. In the same time the Consultant will coordinate the activities with CARE Canada CI Macedonia.

Within Macedonia: 	The consultant will coordinate the activities inside Macedonia with the CARE International - Macedonia representative.

##### Duration of the Assignment

Project start date:		The assignment will start on December 1.

Duration:  		The duration of the assignment is 1 week.

### Experience and Qualifications of the Consultant

The consultant will be able to provide personnel with demonstrable experience in the task areas of this assignment. The minimum required qualifications for this assignment are:

- Good knowledge of the Balkan region;

- Preferable experience working in Macedonia;

- University degree in Agriculture;

- International experience in agricultural development projects;

- Previous experience with “CIDA” funded projects

### Reporting Obligations

General: 	The Consultant will report to the mission representative of CARE International Kosovo  – Nick Weber. All reports will be available for CARE International Kosovo; CARE Canada and CARE International Macedonia. All activities in Macedonia, will be coordinated with the CI mission representative in Macedonia.

Reporting:	The Consultant will prepare “evaluation report” for the first phase of the project. The consultant will prepare an “recommendation report” for the implementation of the 2 and 3 phase of the project.  Both reports to be completed and submitted in electronic copy to the CI mission representative in Macedonia before completion of last day of assignment.

###### Services and Facilities to be Provided by the Client

The client will provide all necessary data needed for the implementation of the assignment;

Secure, furnished office space adequate for consultant needs, Computer, telephone line and Internet connection.

- Facilitate arrangements for meetings with all relevant institutions.

- Make project staff available to participate in discussions related to the consultants’ tasks.

- Print any materials

2.3 Methodology

The methodology draws on experience of conducting monitoring and evaluation assignments for CIDA projects over a number of years in the Eastern Europe. It has been refined to meet the particular requirements of the HLS Project Mid-term Evaluation set in the terms of reference. The work is based on documentary evidence, interviews with key stakeholders, fieldwork, objective analysis of findings and the preparation of a structured report.

The Mid-term Evaluation Methodology used six steps:

- Reviewing of available project documentation;

- Assessing time delivery schedules of deliverables;

- Controlling expenses up-to-date;

- Conducting semi-structured interviews with project staff;

- Conducting interviews with a total of 5 beneficiaries from 4 different municipalities. Random sampling was used to elect beneficiaries to ensure an un-biased control procedure; and

- Conducting interviews with 2 local authorities involved with the project in 2 different villages.

This Mid-term Evaluation was intended to build on the results of the first implementation period of the HLS Project completed in November 30, 2002 and, in particular, to:

- Review progress in implementation since the project start-up and evaluate the outcomes to date;

- Examine implementation of the re-designed HLS Project in respect of the selection of the beneficiaries, and delivery of the assistance; and

- Assess the future utilisation of additional CIDA funding to the HLS Project.

Field visits were conducted at the field level to the following beneficiaries and local authorities:

- Alisami Fejzulahi – beneficiary from Slatino

- Borce Stojcevski – beneficiary from Leshok

- Emin Emini – beneficiary from Prshovce

- Drakce Markovski – beneficiary from Dobroshte

- Nikola Bozinovski - Local authority leader in village Leshok

- Fadil Sabriu - Local authority leader in village Prshovce

- Gajur Idrizi– Local authority leader in village Slatino

The HLS Project has used the following questionnaire, next page, to rank its beneficiary selection within a quantitative framework.

HLS BENEFICIARY SELECTION QUESTIONNAIRE

Municipality:  ____________________ Village: ____________   Date of interview: _____________

Name of the beneficiary:__________________________ EMBR____________________________

1. Household data

  - Ethnicity

| a) Albanian |  | b) Macedonian |  | c) Serb |  | d) Turks |  | e) Roma |  | f) Other |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

  - Number of members in the household

| a) Total |  | b) Children |  | c) Children |  | d) Older |  | e) Male |  | f) Female |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | < 15 years |  | 15-18 years |  | > 65 years |  | 18-65 years |  | 18-65 years |  |

  - Members of the family who returned to the village

| a) Whole family |  | b) Part of the family |  |
| --- | --- | --- | --- |

  - Category of destruction of the family house

| 1st |  | b) 2nd |  | c) 3rd |  | d) 4th |  | e) No damages |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

  - Do you have some material losses from the crisis?

| a) yes |  |  | If yes, explain what type |  | b) no |  |
| --- | --- | --- | --- | --- | --- | --- |

  - Do you have hosted refugees in your household?

| a) No |  | b) Yes, < than 2 |  | c) Yes, 2-5 |  | d) Yes, > 5 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

  - Farm classification (own and under lease)

| a) 0-0.2 ha |  | b) 0.2-0.5 ha |  | c) 0.5-1 ha |  | d) 1-3 ha |  | e) > 3 ha |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

  - Is farming primary activity of the household?

| a) Yes |  |  | b) No |  |  |
| --- | --- | --- | --- | --- | --- |

  - Definition of family labor

| Type of worker | Number of members |
| --- | --- |
| a) Full time workers out of farm (receive monthly salary) |  |
| b) Bankruptcy surplus |  |
| c) Registered unemployed workers |  |
| d) Unemployed, unregistered in the Employment Bureau |  |
| e) Relative’s support from abroad |  |
| Total |  |

  - What kind of agricultural products do you grow on your farm?

| Crop | Own (ha) | Land leased in (ha) | Land leased out (ha) |
| --- | --- | --- | --- |
| a) Cereals |  |  |  |
| b) Fruits |  |  |  |
| c) Vineyards |  |  |  |
| d) Vegetable |  |  |  |
| e) Mushrooms |  |  |  |
| f) Fodder |  |  |  |
| g) Meadows |  |  |  |
| h) I don’t have any field production |  |  |  |

  - What kind of livestock do you breed on the farm?

| Livestock | Number | Age (%) | Breed |
| --- | --- | --- | --- |
| a) Cow |  |  |  |
| b) Sheep |  |  |  |
| c) Cattle |  |  |  |
| d) Pig |  |  |  |
| e) Goat |  |  |  |
| f) Bees |  |  |  |
| g) Poultry |  |  |  |
| h) Fisheries |  |  |  |
| i) I don’t have any livestock production |  |  |  |

  - Annual farm production

| Livestock | Number | Product 1 | Product 2 |
| --- | --- | --- | --- |
| a) Cow |  | Milk/l |  | Cattle/kg |  |
| b) Sheep |  | Milk/l |  | Lambs/kg |  |
| c) Cattle |  | Meat/kg |  |  |  |
| d) Pig |  | Meat/kg |  | Pigs/kg |  |
| e) Goat |  | Milk/l |  | Goatling/kg |  |
| f) Bees |  | Honey/kg |  | Wax/kg |  |
| g) Poultry |  | Eggs/units |  |  |  |
| h) Fisheries |  | Fish/kg |  |  |  |
| i) I don’t have any livestock production |

  - Do you have your own fodder production?

| Type | Own (ha) | Under Lease (ha) |
| --- | --- | --- |
| Wheat |  |  |
| Barley |  |  |
| Maize |  |  |
| Maize for silage |  |  |
| Lucerne |  |  |
| Clover |  |  |
| Other leguminous crops (hay) |  |  |

  - Do you have your own production of silage or concentrate for fodder?

| a) silage |  | b) concentrate |  | c) no |  |
| --- | --- | --- | --- | --- | --- |

  - Do you use irrigation on your land?

| a) yes |  |  | If yes, explain what type |  | b) no |  |
| --- | --- | --- | --- | --- | --- | --- |

  - What kind of agricultural mechanization do you use?

| Machinery | Own (type) | Rented |
| --- | --- | --- |
| a) Tractor |  |  |
| b) Harvester |  |  |
| c) Cultivator |  |  |
| d) Harrow (grubber) |  |  |
| e) Baler |  |  |
| f) Fertilizer spreader |  |  |
| g) Trailer |  |  |
| h) Milking pump |  |  |
| i) Lakto freezer |  |  |
| k) Pasteurizer |  |  |
| h) Other |  |  |

  - What kind of stable do you have?

Damages      Repaired

| a) Primitive, old fashion stable |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| b) Solid stable |  |  |  |  |  |
| c) Modern stable |  |  |  |  |  |
| d) I don’t have a stable |  |  |  |  |  |

  - What kind of utilities do you have in the stable?

| a) well |  | b) waterworks |  | c) electricity |  | d) telephone |  | e) automatisation |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| f) infrastructure |  | g) without any utilities |  |
| --- | --- | --- | --- |

  - Are you interested in building/reconstruction of the stable?

| a) Yes |  |  | b) No |  |  |
| --- | --- | --- | --- | --- | --- |

  - Are you ready to invest in dairy production?

| a) Yes |  |  | b) No |  |  |
| --- | --- | --- | --- | --- | --- |

- Organizations present on the field

  - What type of assistance have you received in the past 6 months?

| Type of assistance | Provided by |
| --- | --- |
| a) |  |
| b) |  |
| c) |  |
| d) |  |

- Preferable assistance

  - What kind of agricultural kit do you prefer?

| Agricultural kit | Priority |
| --- | --- |
| a) Honey production kit |  |
| b) Mushroom production kit |  |
| c) Poultry |  |
| d) Sheep |  |
| e) Goats |  |
| f) Greenhouses |  |
| g) Mechanization |  |
| h) Cows |  |
| i) Other |  |

  - In what kind of training program would you like to participate?

| Topic | Priority (1 - 5) | Basic training | Advanced training | Topic |
| --- | --- | --- | --- | --- |
| a) Farm accounting and funding possibilities |  |  |  |  |
| b) Beekeeping |  |  |  |  |
| c) Mushroom production |  |  |  |  |
| d) Poultry breeding |  |  |  |  |
| e) Greenhouse production |  |  |  |  |
| f) Cow breeding |  |  |  |  |
| g) Other (specify) |  |  |  |  |

- Income generation

  - Average annual costs

| Costs | Denars |
| --- | --- |
| a) Utility (electricity, water, telephone, tax etc) |  |
| b) Household expenses (food, hygiene, transport etc) |  |
| c) Agricultural and other production |  |
| d) Other |  |
| Total costs |  |
| Incomes |  |
| a) Agricultural and other production |  |
| b) Salary and retirements |  |
| c) Social Support (bankruptcy surplus) |  |
| d) Other (specify) |  |
| Total incomes |  |

Comments of the interviewer:

2.4 Limitation

Even if the project team has increased by 165% its delivery services to its targeted clients, the gold of this mid-term evaluation is not to document the results achieved in the first five months of the project but to analyse current capacities and systems in place that will be instrumental in the successful project delivery.

3. Background

The CARE Macedonia Livelihood Support Project promotes self-reliance of returnees and internally displaced people (IDPs) in Macedonia as well as vulnerable people in the respective host communities. The aim of the project is to provide returnees, IDPs and economically disadvantaged families with the means to cover basic living needs and to establish greater self-sufficiency through agricultural production, animal husbandry, or through other sustainable small-scale income-generating activities. The program responds to individual needs and abilities of the beneficiaries who comprise of refugees and IDPs resulting from the conflict. You may find the approved project proposal in the Appendix A, available in Annex I of this document.

3.1 General Context

Since February of 2001 the conflict in the Former Yugoslavia Republic of Macedonia (FYROM) has resulted in a large displacement of families within Macedonia and into neighboring Kosovo. An estimated 122,000 individuals have left their homes due to escalating clashes between the armed Ethnic Albanian Armed Groups (EAAG) and Macedonian security forces.  Approximately 60,000 of this total population are mostly ethnic Albanian refugees living with host families in the Gjilan/Gnjilane in Kosovo. An estimated 60,000 ethnic Macedonian, Albanian, Serbian and Roma have been displaced within Macedonia.

3.2 CARE Macedonia

CARE Macedonia is the first CARE Country Office to have its management staff nationalized. Technical experts both at national or international levels provide technical inputs to the HLS Project. CARE Kosovo operates all regular internal controls to make sure that all internal policies and procedures are followed. CARE Macedonia financial system is weekly linked to CARE Kosovo by electronic data transfers and reconciled monthly.

3.3 CARE Macedonia’s Livelihood Support (HLS) Project

The HLS Project implementation team is committed to networking, partnership and coordination through strong existing relationships with local governments, and with national and international organizations in order to avoid duplication of funding. The team is autonomous and highly skilled; it comprises only 3.5 people.

CARE International covers a large portion of the Balkan Peninsula and has implemented several agriculture and economic development projects and programs. Documented tools and lessons learned are shared among the network of country and field offices and as such the Kosovo Office supervises HLS Project as approved earlier.

3.4 Appropriateness of Project Design

The first external consultation of the project at its operational start-up explored design issues in detail, examining the rationale for the project in the regrettable context of a quickly put together proposal. The broad remit of the assistance has certainly presented difficulties in bringing early coherence to the activities, and in articulating the project chain of results in such a way as to meet objectives of the assistance. The Plan of Operation has clarified these issues; there is a clear logic to the HLS Project, which is now much more in evidence.

Within the HLS Project, there are those initiatives (such as direct emergency support) that can bring about a quick and visible impact on the economic prospects of returnees and the most vulnerable. But equally, there is a necessity to tackle institutional and structural issues to economic development in return areas (income generation support, ago-technical training and farming accounting training), which will, over time, bring about improved economic prospects in Tetovo areas, for its beneficiaries, and make the sustainability of small scale income generation activities.

4. Review of all Project deliverables

The Project Plan of Operation has corrected the large structural defects of the original proposal, as mentioned earlier, where project purposes were too broad; expected results and their related indicators were input driven; and activities did not cross-match the project’s financial capacity.

This section will review if the project re-design, as from the approved Plan of Operation, has set appropriate assumptions and realistic deliverables. The Goal of the HLS project is:

- To ensure livelihood security of returnees, IDPs and vulnerable households in the North of the Tetovo Area.

All stakeholders involved in this project recognize that the timeframe of the project may not enable the project to achieve this long-term goal. CIDA’s International Humanitarian Assistance (IHA) Programme, in its new operational guidelines, does not require its partners to set up a goal for the implementation of its humanitarian assistance. Although, the project team in Macedonia has decided to set one to enable a project vision in order to explore other economic opportunities in the project targeted areas for further development initiatives.

Nevertheless, the project has stand to its goal to service most vulnerable through the provision of Emergency Agricultural Kits (EAK) but will be more likely to achieve its goal by the provision of its Income Generation Kits (IGK) to its economically active beneficiary segment. Also by reducing the size of the targeted area, the project has more chance to reach economies of scale and critical mass.

4.1 Project Purposes

##### The HLS Project has two purposes, which are as follow:

- To increase family income through small-scale enterprise activities;

- To deliver project beneficiaries an emergency or agricultural support kit with the cooperation of the local authorities and other organization working in the area.

The following table drafts the current progress in the achievement of the HLS Project Purposes up-to-now and until the project completion.

| HLS Project Mid-term Evaluation – Progress in the Achievement |
| --- |
| Purposes | July to November 2002 | December to June 2002 |
| To increase family income through small-scale enterprise activities; | Within this period the project has succeeded in reducing cash flow burden of its most venerable targeted beneficiaries for Emergency Kits. A total of 215 households received services. | The HLS Project team consider that this project purpose will be achieved in the following project implementation periods, which will include the distribution of Agricultural Support or Income Generation Kits and agriculture training and technical assistance. |
| To deliver project beneficiaries an emergency or agricultural support kit with the cooperation of the local authorities and other organization working in the area. | Within this period the project has distributed the emergency kits. The beneficiary selection included local authorities and selection committees were formed in all villages targeted by the project. These committees are involving one representative of a local NGO. | The beneficiary selection for the distribution of all Agricultural Support or Income Generation Kits is completed. The local authorities and selection committees were involved in the beneficiary selection process within all villages targeted by the project. The distribution activity will also involve all stakeholders. |

4.2 Output/results and indicators

The two following tables respectively describe and comment feedback and relevance of both the selection of the project expected results and their indicator measurements.

| HLS Project Mid-term Evaluation - Feedback on the selection of Project Expected Results |
| --- |
| Narrative Summary | Expected Results | Feedback |
| Goal To ensure livelihood security of returnees, IDPs and vulnerable households in the North of the Tetovo Area. | Impacts Improved livelihood security of the targeted beneficiaries. | The project team is confident that the project will really improve the livelihood conditions of their beneficiaries. |
| Purposes To increase family income through small-scale enterprise activities. To deliver project beneficiaries an emergency or agricultural support kit with the cooperation of the local authorities and other organization working in the area. | Outcomes Improved household incomes. Improved inter-ethnic dialogues. | The result of this outcome will be more likely to be seen with the delivery of the agricultural support kit. Although, the Emergency Kit delivery has reduced cash flow constraints of the targeted households. The participation of local authorities and local NGOs has set a dialogue between different parties. The training component of the project will more likely support the achievement of this result by enabling all ethnic groups to work and learn together elements of common interests. |
| Inputs Executive Agency: CARE (Involved local authorities and local NGOs in the selection and delivery of project deliverables) Number of Staff: 4 (Reduced to now to 3.5 members) Number of beneficiaries: 130 households (Increased to 265 households) (215 households currently reached) (250 beneficiaries will be included in training sessions compared to 100 as originally planned) Budget: CAN$ 500,00.00 Activities: Distribution of Emergency Kits Distribution of Agricultural Kits Farming Accounting Training Commodity Production Training | Outputs Responded needs for emergency support. Increased access to agricultural commodity income generation activities. Improved awareness about profitable farming. Increased capacities to select profitable agricultural commodities. Improved integration of the HLS Project activities with existing local governments and local and international organizations. | The selection process involving a quantitative baseline and the creation of queries from a database have enabled the project to target evident needs. Community participation and interviews with local experts have enable the project to target relevant income activities to be promoted. A quality-training curriculum has been developed in this regard. All agricultural training will involve a variable cost analysis. Although, allocation of fixed costs shall be analysed by the project team. In this regard the HLS Project has executed a remarkable job. The transparency of the selection process and the involvement of local representatives are impressive. |

| HLS Project Mid-term Evaluation - Relevance of the Indicator Measurement |
| --- |
| Expected Results | Performance Measurement | Relevance |
| Impacts Improved livelihood security of the targeted beneficiaries. | Impact Indicators 75% of beneficiaries are satisfied with the project delivery. Testimonials and Success Stories | Yes Yes (To be measured at the project closure). |
| Outcomes Improved household incomes. Improved inter-ethnic dialogues. | Outcome Indicators % of increased in household income. Perception about the inter-ethnic dialogues. Quality of participation of local authorities. % of farmers book-keeping their accounting operations. | Yes (the baseline study will enable the analysis). Yes (the training venues will enable the project to document this indicator). Yes (the training venues will enable the project to document this indicator). Yes (can be hard to measure if the project is not extended). |
| Outputs Responded needs for emergency support. Increased access to agricultural commodity income generation activities. Improved awareness about profitable farming. Increased capacities to select profitable agricultural commodities. Improved integration of the HLS Project activities with existing local governments and local and international organizations. | Output Indicators Overall average of the training quizzes. Number of households receiving the emergency support kit. Number of households receiving the agricultural support kit Number of household dependants (children, men and women) | Yes (Tests will need to be prepared in this regard). Yes (has been fully monitored with a high standard tracking system). Yes (will be fully monitored with a high standard tracking system). Yes (has been and will be fully monitored with a high standard tracking system). |

4.3 Beneficiaries

The table and chart below of grants disbursed show that 215 households have been assisted with the project Emergency Assistance Kit (EAK). The ethnic segmentation shows that Serbian and Turkish minorities where included to Albanian and Macedonian recipients.  The project has forecasted to reach 265 households by the end of its mandate in comparison to 130 as originally planned. The number of households per ethnicity and its representative number of dependants are presented in the table below.

| HLS Project Beneficiary Ethnic Representation |
| --- |
| Ethnicity | Number of Households | Number of dependants | Percentage of Participation by Ethnicity |
| Albanian | 125 | 841 | 58.14% |
| Macedonian | 85 | 446 | 39.53% |
| Serb | 1 | 5 | 0.47% |
| Turk | 4 | 19 | 1.86% |
| Total | 215 | 1311 | 100% |

Through its selection process, the HLS Project has collected and analysed a large number of data that will be useful for further project design information and impact assessments. For example, you have in the chart beside the segmentation by average number of household members.

Reviewing the circumstances of the beneficiaries supported shows that the validity of awarding the grant has been appropriate and broadly justified on the basis of eligibility and the criteria established for support.

The selection process was supported from an Access software application built by an external Information Technical professional. This application has created a series of queries and quantitative analytical tools that generated beneficiary selection lists. Each list has links to its client records. The process is fully transparent and enables review if local complaints are raised. Data are then reprocessed and a new list is then easily regenerated.  The selection of beneficiaries is well documented internally as you can see below.

HLS Project Selection Criteria

  - Selection of municipalities

Selection of municipalities was made according to the initial assessment, done in July 2002. In regards of data collected, it was considered that the impact of the project will be bigger if activities would be narrow to four municipalities. After initial assessment it was decided to concentrate project delivery in municipalities Dzepcishte, Tearce, Jegunovce and Vratnica.

1.2.	Selection of villages

Selected municipalities in the region of North Tetovo have 30 villages. Priority in delivery project activities  was given to ARK villages, which were affected with direct war activities:

(i)	Neproshteno

(ii)	Leshok and

(iii)	Tearce

All three villages are part of the municipality Tearce. The other villages were selected according to the village assessment. Selected villages for project activities delivery were following:

Table 1: Villages included in the project activities delivery

| Municipality | Village |
| --- | --- |
| Dzepcishte | Germo |
| Jegunovce | Kopance |
| Jegunovce | Raotince |
| Tearce | Slatino |
| Tearce | Prshovce |
| Tearce | Nerashte |
| Tearce | Dobroshte |
| Tearce | Neproshteno |
| Tearce | Tearce |
| Vratnica | Staro Selo |
| Vratnica | Rogashevo |
| Vratnica | Belovishte |
| Vratnica | Jazince |
| Vratnica | Dolno Orashje |
| Total: 4 | Total: 15 |

1.3.	Selection of beneficiaries

Selection of project beneficiaries was made in order to achieve ethnicity participation in following proportion:

(i)	Albanians – 60% and

(ii)	Macedonians – 40%

Number of direct households as project beneficiaries is 265 households in selected villages in region of north Tetovo.

(i)	Beneficiaries for Emergency Response Kit – 215

(ii)	Beneficiaries for Agriculture Assistance Kit – 50

(iii)	Participants on Training programs - 250

Lists of beneficiaries for Emergency Response Kit and Agriculture Assistance Kit was prepared from representatives from local authorities, according to the selection criteria that was delivered by CARE International Team.

General criteria for selection of beneficiaries were: citizenship in the potential villages, households with more than four members, with unemployed persons as well as households without relative support from abroad.

Beneficiary selection criteria:

According to the priority, Beneficiaries selection criteria are as follows:

1.	Returnees in respective villages (whole household)

(i)	Households with houses in 3rd and 4th category of damage

(ii)	Households hosted refugees from other regions involved in the crisis

(iii)	Ethnicity (priority to nationalities that are less represented – Serbs, Roma, Turks)

(iv)	Inhabitancy in respective village (according to ID Card)

2.	Unemployed family members and number of receivers of Social Benefit (Jugohrom)

(i)	Households with houses in 3rd and 4th category of damage

(ii)	Handicapped persons (with mental and physical handicap)

3.	Number of members in the household

4.	Households with agriculture as primary activity

(i)	Households with more than 0.2ha arable land

(ii)	Households that have livestock production

Within the pre-selected regions and villages, lists with potential beneficiaries that should be interviewed have been selected according the criteria from the representatives of the local authorities.

2	Beneficiary Selection Process

Beneficiary selection process was implemented in several phases:

(i)	Collecting list of potential beneficiaries from the respective villages

(ii)	Adjusting number on the beneficiaries on the list with 25% more beneficiaries than estimated number of beneficiaries in the village

(iii)	Implementation of the interviews with 354 potential beneficiaries

(iv)	Data entering and creation of Access Data Base

(v)	Defining criteria for Computer selection of the beneficiaries within the data base

(vi)	Performing Selection Committee Meetings

All phases were performed in the period August – October 2002. In some of the phases during implementation, Team of CARE International was supported by representatives of local authorities and 6 interviewers representatives from local NGO’s.

Collecting list of potential beneficiaries from the respective villages

Collection of list with potential beneficiaries for the project started in August 2002 and finished in September 2002. Lists were prepared from local authorities, according to the criteria provided by CARE International Team.

Adjusting number on the beneficiaries on the list

In some villages, there were more than 50% beneficiaries that was necessary. In order to achieve real number, additional criteria was provided to respective villages:

(i)	Households with whole family returned to the village

(ii)	Households with more than 4 family members

After receiving of revised lists, total number of potential beneficiaries was 354.

Implementation of the interviews

Implementation of the survey started at the end of September and finished in first week of October, 2002. For on-time performing of the survey, team of CARE International was supported by 6 interviewers, representatives from local NGO’s. In the survey 354 potential beneficiaries were included.

Creation of Data Base

All information that was collected during the survey was entered in Access data base, in order to provide possibility for their analysis. Process of data entering was realized in November, 2002.

Defining criteria for Computer selection of the beneficiaries within the data base

After creation of data base, in order to get clear selection of beneficiaries, several criteria was taken in consideration, according to priority:

(i)	Farm classification

(ii)	House Destruction

(iii)	Number of household members

(iv)	Family returned to the village

(v)	Hosted refugees

(vi)	Material losses

(vii)	Farming as primary activity

(viii)	Annual Household Net Income

Farm classification

Components of the ERK and AAK were in correlation with agricultural production in the household. Therefore farm classification was one of the main criteria for beneficiaries selection.

In this criteria, beneficiaries were divided in two groups: beneficiaries that have more than 0.2 ha land and the others that do not have any land or have less than 0.2ha. Beneficiaries with more than 0.2 ha land were taken in consideration as priority.

House destruction

Second important criteria was house destruction. Priority to get assistance had beneficiary with higher number of house destruction, starting with 4, than 3, 2, 1 and at the and were beneficiaries without house destruction.

Number of household members

Households with bigger number of household members have priority in this criteria.

Family returned to the village

Households that have whole family members returned to the village have priority in this criteria. Households that have some of the family members not returned in the respective village were settled on the bottom of the list of beneficiaries for this criteria.

Hosted refugees

Households that have hosted refugees during the crisis have priority according to this criteria.

Material losses

According to this criterion, households that suffered some material losses during the crisis, have priority for getting assistance from the project.

Farming as primary activity

Households that have farming as primary activity were taken in consideration as more important for project assistance, in correlation with nature of the project.

Annual Household Net Income

A last criterion that was included in selection process was annual household net income. Households with the lowest income were considered as most important and have priority for this criteria. Sorting of the other households was in ascending position.

After data analysis, and respecting above-mentioned criteria, list of selected potential beneficiaries for each village was prepared according to the priority.

Performing Selection Committee Meetings

Selection Committee meetings were performed in all villages included in the project delivery. Members of the selection committees were:

1.	Representatives from 15 local municipalities representing each villages;

2.	Representatives from local NGO’s that have multiethnic membership (Ortlius; Vizija; Predizvik; Multikultura);

3.	Representatives from CARE International team.

On the meetings of the selection committees the preprepared list of beneficiaries was reviewed. The list was printed out of the database including filters and sorting mechanisms that created lists with priorities. The role of the selection committees was to verify the lists and to confirm that all data imputed in the database was correct. In several occasions, corrections were done, based on findings of the selection committees. This changes were recorded in the minutes of meeting of each village.

In the same time beneficiaries for the IGK were selected. In this case more emphasis was put on farmers capacity for implementing IG activity.

The selection process creates list as the one next page that shows the data published for each beneficiary village list. The data are about the clients that were visited during the Mid-term Evaluation.

| HLS Project Beneficiary Selection Data Sample for Beneficiaries Visited |
| --- |
| Ref | Municipality | Village | Name | Ethnicity | Farm size | Destruction Category | Total household members | Children <18 | Male & Female >65 | Male & Female 18 - 65 | Family Return Yes / No | Hosted IDP Yes / No | Material losses | Is farming primary activity Yes / No | Annual household Income | Annual household Expenses | Annual Net Profit / loss |
| 14 | Tearce | Slatino | Alisami Fejzullahi | Albanian | 0.2 - 0.5 ha | No damages | 5 | 1 | 0 | 4 | Part of family | No | No | Yes | 36,000 | 95,500 | (59,500) |
| 8 | Tearce | Prshovce | Emin Emini | Albanian | 0.2 - 0.5 ha | No damages | 6 | 3 | 0 | 3 | Whole family | No | No | Yes | 61,200 | 62,900 | (1,700) |
| 3 | Tearce | Dobroshte | Drakce Markovski | Macedonian | 0.5 - 1 ha | No damages | 4 | 1 | 0 | 3 | Whole family | No | No | Yes | 113,040 | 188,500 | (75,460) |
| 15 | Tearce | Leshok | Borce Stojcevski | Macedonian | 1 - 3 ha | 1 | 5 | 2 | 0 | 3 | Whole family | No | Yes | Yes | 228,000 | 199,400 | 28,600 |

4.5 Project Activities, Timeframe and Responsibilities

The table below presents the modification to the project activities in terms of delivery, timing, responsibilities and gross financial projections as well as estimated costing to date. The estimated costing exercise is at this point an allocation of direct project costs. Crosses have been laid down on the delivery timeframe of each activity to reassess timing till the end of the project. The project responsibilities for the activities are clearly shared between the Project Manager (PM), the Agricultural Officer (AO), the Community Development Officer (CDO) and the Financial Officer (FO).

| HSL Project – Plan of Operation – Timeframe and Responsibilities Mid-term Review |
| --- |
| Activity No. 1 Training | Operation | August 2002 to April 2003 | Responsibility | Estimated |
|  | Household | Training |  | Name |  |
|  | 100 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1. | Farming Accounting | 30 | 4 | A | S | O | N | D | J | F | M | A |  | USD 8,000 |
|  | a) Interview other agro-practitioners |  |  |  | X | X |  |  |  |  |  |  | AO, PM, FO |  |
|  | b) External professional consultations |  |  |  | X | X |  |  |  |  |  |  | AO, PM, FO | $500 spent |
|  | c) Document a training manual |  |  |  |  | X | X | X |  |  |  |  | AO, PM, FO | to date |
|  | d) Deliver to targeted groups |  |  |  |  |  |  | X |  |  |  |  | AO, PM, FO |  |
|  | e) Organize peer-producer training |  |  |  |  |  |  | X |  |  |  |  | AO, PM, FO |  |
|  | f) Monitor peer-producer delivery |  |  |  |  |  |  |  | X | X | X | X | AO, PM, FO |  |
|  | h) Survey clients' satisfaction |  |  |  |  |  |  |  | X |  |  |  | AO, PM, FO |  |
| 1.2. | Commodity production training | 70 | 12 | A | S | O | N | D | J | F | M | A |  |  |
|  | a) Interview other agro-practitioners |  |  |  | X | X |  |  |  |  |  |  | AO, PM | USD 8,000 |
|  | b) External professional consultations |  |  |  | X | X |  |  |  |  |  |  | AO, PM |  |
|  | c) Document a training manual |  |  |  |  |  | X | X | X |  |  |  | AO, PM | $2,800 spent |
|  | d) Deliver to targeted groups |  |  |  |  |  | X | X | X | X |  |  | AO, PM | to date |
|  | e) Organize peer-producer training |  |  |  |  |  |  | X | X | X |  |  | AO, PM |  |
|  | f) Monitor peer-producer delivery |  |  |  |  |  |  |  | X | X | X |  | AO, PM |  |
|  | h) Survey clients' satisfaction |  |  |  |  |  |  | X | X | X | X |  |  |  |

The Mid-term Evaluator has reviewed the well-prepared training terms of the HLS Project Agricultural Training Program. We would like to underline that the Farming Accounting Training is a cutting-edge in Macedonia and do precede the implementation of the regulation on the obligation of farm holders to produce their farming financial statements.

The general comment is that quality to details and a will to deeply find high profile local professional experts was given. All contract agreements with each expect are through and responsibilities and obligations are well defined. You may consult down below in italic the un-edited Work plan of the HLS Project Training Program. The Agricultural Officer has also documented a Detailed Work Plan Table, which was also added to this section next page. This table, for each training venue, presents the lecturers or trainers, the timing, the material needed and the budget allocation.

HLS Project Training Program Work plan

One of the major activities of CARE International team during the winter months will be organization and performing several training programs for the beneficiaries in the region of North Tetovo. These training programs will be performed in order to initiate increasing family income through small-scale enterprise activities.Topics for the training programs will be related with agricultural production and farm accounting. Training programs in the field of agriculture will be in the following topics: sheep breeding, poultry breeding, greenhouse production and mushroom production. All training programs will be performing in several workshops with different topics. Some of the training programs will be lecturing, and the others will be practical, on-farm training.

## Project beneficiaries

Potential beneficiaries for the third phase of the project will be participants in the workshops related to the kit that they will receive. The workshops will be open to the other beneficiaries from the region that are interested to participate and learn more in the respective field. It is estimated that on each workshops 20 to 25 beneficiaries would participate.

## Lecturers on the training program

In order to ensure good results and provide Training programs on a professional level, the project has decide to engage experts in the selected fields. All experts have an experience in training process and are university professors or authorized experts in respective fields.

| HLS Project Agriculture Training Program - Detailed Work Plan Table |
| --- |
| Subject | Lector | Location | Participants | Time | Manual | Materials | Budget |
|  |  |  |  |  |  |  | Trainers | Equipment | Transport | Materials | Refreshments | Manuals |
| Introduction in the mushroom breeding. Concept for the Champignon and Pleurotus. Role, technology in mushroom breeding and cultivation | Dimce Todorovski | Vratnica | 15-17 | 18.12.2002 | 27.11.2002 | TV: VSR; Flip Chart | 150 | 70 | 0 | 100 | 100 | 725.81 |
| Technical-Technological engineering and mushroom breeding phase till before the beginning of the harvest | Dimce Todorovski | Vratnica | 15-17 | 19.12.2002 | 27.11.2002 | TV: VSR; Flip Chart | 150 | 70 | 0 | 100 | 100 | 725.81 |
| Harvest of mushrooms (on farm). Mushroom processing .Visit of the kompost production factory | Dimce Todorovski | Kompostara, Karbinci | 15-17 | 20.12.2002 | 27.11.2002 | Bus for transport | 150 | 0 | 200 | 50 | 100 | - |
| Farm accounting and investment options | Dragi Dimitrievski | Vratnica/ Tearce | 15-17 | 24.12.2002 | 06.12.2002 | LCD Projector; Flip Chart | 150 | 70 | 0 | 100 | 100 | 725.81 |
| Farm accounting and investment options | Dejan Gjorsovski | Vratnica/ Tearce | 15-17 | 25.12.2002 | 06.12.2002 | LCD Projector; Flip Chart | 0 | 70 | 0 | 100 | 100 | - |
| Farm accounting and investment options | Dejan Gjorsovski | Vratnica/ Tearce | 15-17 | 26.12.2002 | 06.12.2002 | LCD Projector; Flip Chart | 0 | 70 | 0 | 100 | 100 | - |
| Introduction in poultry breeding (Gross margin ). Broiler production | Dragoslav Kocevski | Vratnica/ Tearce | 15-17 | 22.01.2003 | 10.01.2003 | LCD Projector; TV, VSR, Flip Chart | 150 | 70 | 0 | 100 | 100 | 725.81 |
| Hens, breeding and feeding technology | Dragoslav Kocevski | Vratnica/ Tearce | 15-17 | 23.01.2003 | 10.01.2003 | LCD Projector; TV, VSR, Flip Chart | 150 | 70 | 0 | 100 | 100 | - |
| Practical part - farm training | Dragoslav Kocevski | Poultry farm,Ohrid | 15-17 | 24.01.2003 | 10.01.2003 | Bus for transport | 150 | 0 | 200 | 100 | 100 | - |
| Sheep production | Vladimir Djabirski | Agricultural faculty | 15-17 | 04.02.2003 | 18.01.2003 | Bus for transport | 250 | 0 | 100 | 100 | 70 | 725.00 |
| Sheep selection | Vladimir Djabirski Sreten Andonov | Agricultural faculty | 15-17 | 05.02.2003 | 18.01.2003 | Bus for transport | 250 | 0 | 100 | 100 | 70 | - |
| Practical part - farm training | Vladimir Djabirski | Farm in Kozle, Petrovec | 15-17 | 06.02.2003 | 18.01.2003 | Bus for transport | 250 | 0 | 100 | 50 | 100 | - |
| Cheese production | Sonja Srbinovska | Agricultural faculty | 15-17 | 07.02.2003 | 18.01.2004 | Bus for transport | 250 | 0 | 100 | 100 | 70 |  |
| Introduction in the greenhouse production; Soil illness and parasites | Gordana Popsimonova | Vratnica/ Tearce | 15-17 | 19.02.2003 | 01.02.2003 | LCD Projector; TV, VSR, Flip Chart | 150 | 70 | 0 | 100 | 100 | 725.00 |
| Finalization of the production, storing, packing and analysis of the expenses and the incomes | Gordana Popsimonova | Vratnica/Tearce | 15-17 | 20.02.2003 | 01.02.2003 | LCD Projector; TV, VSR, Flip Chart | 150 | 70 | 0 | 100 | 100 | - |
| Practical training in greenhouses | Gordana Popsimonova | Borievo, Strumica | 15-17 | 21.02.2003 | 01.02.2003 | Bus for transport | 150 | 0 | 200 | 50 | 100 | - |
|  |  |  |  |  |  | Total | 2,500.00 | 630.00 | 1,000.00 | 1,450.00 | 1,510.00 | 4,353.23 |
|  |  | 250 expected participants |  | Grand Total |  |  |  |  | 11,443.23 | 3,556.77 |

## Manuals

One of the tasks that are requested from the lecturers is preparation of manual with contents related to the topics that are elaborated on the workshop. It is planned that five manuals for each field of training program should be published:

- Manual for mushroom production (the manual will include part for Champignons and the other part for Pleurotus production)

- Manual for Farm accounting with funding possibilities

- Manual for Poultry breeding

- Manual for Sheep breeding and

- Manual for Greenhouse production.

All manuals will have CIP number and will be catalogued in National and University Library  “St. Kliment Ohridski” in Skopje.

## Location	Part of the lecturing training programs will be performed in the municipality building in village Slationo. Workshops that are related to the sheep breeding will be conducted at the Agricultural Faculty in Skopje in the special equipped workshop. On-farm trainings will be organized and performed on several best farms in Macedonia.

## Schedule for training programs

The schedule for the training programs is as follows:

- Mushroom production

# Lecturer	Lecturer for the training programs for mushroom production will be Dimce Todorovski, expert in mushroom production, owner of one of the biggest compost factories in Macedonia.

# Time frame 	Training programs will be performed on December 18, December 19 and December 20. 2002.

# Topics 		Following topics will be elaborated during these three different workshops:

  - Introduction in mushroom production. Concept for the Champignon and Pleurotus. Role, production and cultivation technology

  - Technical engineering and phase of mushroom production

  - Mushroom harvest (on farm). Mushroom processing. Visit of compost production factory

- Farm accounting and funding possibilities

# Lecturer 	Lecturer for the training program in Farm accounting will be Ph.D. Dragi Dimitrievski, professor in Faculty of Agriculture in Skopje at Department of Agricultural Economy.  He has e relevant experience in Farm accounting in several projects.  For the second part of the training program – funding possibilities, lecturers from Macedonian Business Research Center will be engaged. They have updated information about all sources for financing in Republic of Macedonia and regularly publish a bulletin with all data in this topic.

# Time frame	Training programs will be performed on December 24, December 25 and December 26, 2002.

# Topics 	The same topic will be elaborated in different three workshops in duration of one day per workshop.

- Farm accounting and funding possibilities

- Poultry breeding

# Lecturer	Lecturer on the training programs for poultry breeding will be Master of Science Dragoljub Kocevski, expert in poultry breeding. He is an Assistant in Faculty of Agriculture in Skopje at Department of Livestock breeding.  He has e relevant experience in poultry breeding in number of projects

# Time frame	Training programs will be performed on January 22, January 23 and January 24, 2003.

# Topics	Following topics will be elaborated during these three different workshops:

  - Introduction in poultry breeding. Gross margin in poultry breeding. Broiler production.

  - Hens, breeding technology and feeding

  - On-farm training. Visit one of the biggest poultry farms in Ohrid.

- Sheep breeding

# Lecturer	Lecturers on the training programs for sheep breeding will be several professors from Agricultural Faculty in Skopje: PhD Vladimir Dzabirski, PhD Sreten Andonov and PhD Sonja Srbinovska. They are experts in sheep breeding and cheese production.

# Time frame	Training programs will be performed on February 11, February 12, February 13 and February 14, 2003.

# Topics		Following topics will be elaborated during these four different workshops:

  - Introduction in sheep breeding.

  - Selection of quality sheep

  - On-farm training. Visit of one of the biggest farm in region of Skopje in village Kozle.

  - Cheese production (practical training)

- Greenhouse production

# Lecturer	Lecturer on the training programs for greenhouse production will be PhD Gordana Popsimonova, scientific collaborator at the Institute of Agriculture in Skopje and project manager of GEF project for implementation of the Stockholm convention on Persistent Organic Pollutants in Republic of Macedonia. She is also National coordinator for greenhouse production in FAO.

# Time frame	Training programs will be performed on February 19, February 20 and February 21, 2003.

# Topics 	Following topics will be elaborated during these three different workshops:

  - Introduction in greenhouse production. Soil diseases and pests.

  - Finalization of greenhouse production, storing, packaging and cost and income analysis.

  - Practical on-farm training in one of the best greenhouses in Strumica.

| HSL Project – Plan of Operation – Timeframe and Responsibilities Mid-term Review |
| --- |
| Activity No. 2 Agriculture Assistance Kit | Operation | August 2002 to April 2003 | Responsibility | Estimated |
|  | Household |  | Name | Cost |
|  | 50 |  |  |  |  |  |  |  |  |  |  |  |
| 2.1. | Beneficiaries (for AAK) |  | A | S | O | N | D | J | F | M | A | CDO, PM | 8000US$ |
| a) | Meeting with other NGOs, INGOs and local authorities; |  | X | X |  |  |  |  |  |  |  |  | 4,000$ spent |
| b) | Lists of beneficiaries in selected region targeted by other donor organizations; |  | X | X |  |  |  |  |  |  |  |  | to date |
| c) | Lists of social cases from Local Government Social Protection Biro; |  | X | X |  |  |  |  |  |  |  |  |  |
| d) | Lists of IDPs and Returnees in the selected region; |  | X | X |  |  |  |  |  |  |  |  |  |
| e) | Finalization of the survey questioner; |  | X | X |  |  |  |  |  |  |  |  |  |
| f) | Organization and implementation of the survey; |  | X | X | X |  |  |  |  |  |  |  |  |
| g) | Creation of the selection committees; |  | X | X | X |  |  |  |  |  |  |  |  |
| h) | Finalization of the Baseline study based of the small survey; |  | X | X |  |  |  |  |  |  |  |  |  |
| 2.2. | Definition of AA Kits |  | A | S | O | N | D | J | F | M | A | CDO, AO, PM | 6,000US$ |
| a) | Investigate possibilities (Baseline Study) |  |  | X |  |  |  |  |  |  |  |  | 2,000$ spent |
| b) | Contact suppliers and define prices and distribution process; |  |  | X |  |  |  |  |  |  |  |  | to date |
| c) | Draft business plan |  |  | X |  |  |  |  |  |  |  |  |  |
| 2.3. | Procurement |  | A | S | O | N | D | J | F | M | A | CDO, PM | 80,000US$ |
| a) | Issue requests for quotation |  |  |  |  |  | X |  |  |  |  |  | 0$ spent |
| b) | Receive proposals |  |  |  |  |  | X | X |  |  |  |  |  |
| c) | Signed contracts with suppliers |  |  |  |  |  | X | X |  |  |  |  |  |
| 2.4. | Distribution |  |  |  |  |  |  |  | X | X |  | CDO, AO, PM | 2,000US$ |
| 2.5. | Counseling and field visits |  |  |  |  |  |  |  |  | X | X |  | 0$ spent |
| 2.6. | Beneficiaries feedback |  | A | S | O | N | D | J | F | M | A | AO, PM | 2,000US$ |
| a) | Select randomly 10 beneficiaries to be surveyed / interviewed; |  |  |  | X |  |  |  |  |  |  |  | 0$ spent |
| b) | Perform outcome impact interview; |  |  |  |  |  |  |  |  |  | X |  |  |
| c) | Reporting. |  |  |  |  |  |  |  |  |  | X |  |  |

The Activity 2: Agricultural Assistance Kit, now renamed as Income Generation Kit, is under implementation. Beneficiaries are all selected. All beneficiaries of this Income Generation Kit will have to follow the training sessions linked with the type of income kit they will receive. The preparation has been done in the state of the art as per all other project operations.

| HSL Project – Plan of Operation – Timeframe and Responsibilities Mid-term Review |
| --- |
| Activity No. 3 Emergency Response kits | Operation | August 2001 to December 2002 | Responsibility | Estimated |
|  | Household |  | Name | Cost |
|  | 80 |  |  |  |  |  |  |  |
| 3.1 | Beneficiaries |  | A | S | O | N | D | CDO, PM | 8000US$ |
| a) | Meeting with NGO, INGO and local authorities; |  | X | X |  |  |  |  | 4,000$ spent |
| b) | Lists of beneficiaries in selected region targeted by other donor organizations; |  | X | X |  |  |  |  |  |
| c) | Lists of social cases from Local Government Social Protection Bureau; |  | X | X |  |  |  |  |  |
| d) | Lists of IDPs and Returnees in the selected region; |  | X | X |  |  |  |  |  |
| e) | Finalization of the survey questioner; |  | X | X |  |  |  |  |  |
| f) | Organization and implementation of the survey; |  | X | X | X |  |  |  |  |
| g) | Creation of the selection committees; |  | X | X | X |  |  |  |  |
| h) | Finalization of the Baseline study based of the small survey; |  | X | X |  |  |  |  |  |
| 3.2. | Definition of ER Kits |  | A | S | O | N | D | CDO, AO, PM | 6,000US$ |
| a) | Investigate possibilities (Baseline Study) |  |  | X |  |  |  |  | 2,000$ spent |
| b) | Contact suppliers and define prices and distribution process; |  |  | X | X |  |  |  |  |
| 3.3. | Procurement of ER Kits |  | A | S | O | N | D | CDO, PM | 80,000US$ |
| a) | Issue requests for quotation |  |  | X | X |  |  |  | 38,420$ spent |
| b) | Receive proposals |  |  |  | X |  |  |  |  |
| c) | Signed contracts with suppliers |  |  |  | X |  |  |  |  |
| 3.4. | Distribution |  |  |  | X | X |  | CDO, AO, PM | 2,000US$ 900$ spent |
| 3.5. | Beneficiaries feedback |  | A | S | O | N | D | AO, PM | 2,000US$ |
| a) | Select randomly 10 beneficiaries to be surveyed / interviewed; |  |  |  | X |  |  |  | 0$ spent to date |
| b) | Perform outcome impact interview; |  |  |  |  |  | X |  |  |
| c) | Reporting. |  |  |  |  |  | X |  |  |

The Activity number 3: Emergency Response Kits delivery was successfully completed on time. Beneficiaries and local authorities interviewed were satisfied with the activity. The project was able to reduce procurement cost while increasing quality of the goods and material disbursed: fertilizers, small tools and fuel coupons. All respondents to the interviews conducted during the Mid-term Evaluation were commenting about the high quality of the material and also about the reasonable size of the grant, stating that it large enough to be fully useful. The distribution of fuel coupons was extremely handy for the crop harvests and came on time, which mean before hand. This element of the kit was a cost-efficient procurement tool for the project. Also the fuel coupons were helpful in reducing cash flow pressures to all households since they did not have to do this expense.

All beneficiaries interviewed recognized that they really needed the kit to complete their harvesting operations on time before the winter, but they also stated: “it is preferable to teach somebody how to fish than to give them fishes” following the Chinese saying common used in former Yugoslavia. In this regard, they did prefer this type of emergency kit they received from the HLS Project than the food parcels they received earlier. Otherwise, they would like to also receive the Income Generation Kit but they do understand that other people are in need too. They said they would be present to the training sessions.

Local authorities all said to the Mid-term Evaluator that the distribution and selection system of the HLS Project was orderly and it did not create jalousie among citizens since the process was totally transparent. They also commented that unfortunately it is not all organizations in their areas that do process with high quality standard and with a concern to not create more tensions. They thank the Canadian Government in this regard to have set up such a good project even if the number of beneficiaries was too small according to the needs their community have.

4.6 Visibility

The HLS Project has built its high profile in media with significant news coverage and interviews on press in the Tetovo Areas and Skopje publicizing CIDA’s financial contribution. Media coverage has resulted in 2 local media stories/interviews, as presented below. The project has clearly identified each parcel distributed with a CIDA Logo. Staff involved in the distribution process where dressed with CARE stamped shirts and caps.

Published in the newspaper “Global” on 18.11.2002, in Macedonian and Albanian language.

Canadian help for household support in Tetovo

40.000 $ from “CIDA” for agricultural development

215 families are in the second phase of the Project, from Raotince, Gjermo, Kopance, Leshok, Slatino, Prshovce, Nerashte, Dobroshte, Neproshteno, Tearce, Dolno Orashje, Belovishte, Staro Slo, Rogachevo and Jazince

215 families from the following municipalities Tetovo: Djepciste, Tearce, Jegunovce and Vratnica, have received help in total amount of 40.000 $ from the Canadian organization for development “CIDA”, in the frames of the second phase of the Project for household support in the rural area. The help, composed from cement, fertilizer, fuel and tools set, has been distributed to the families with the help of the humanitarian organization CARE International, in the villages Raotince, Gjermo, Kopance, Leshok, Slatino, Prshovce, Nerashte, Dobroshte, Neproshteno, Tearce, Dolno Orashje, Belovishte, Staro Selo, Rogachevo and Jazince.

According to Ljubomir Dimovski from CARE International mission, the families, beneficiaries of the help are selected in consultancy with the representatives from the local communities, and according to the previous monitoring that was carried out from the field workers of the humanitarian organization, the help will be used by the families that weren’t in project program of other humanitarian organizations.

- In cooperation with other humanitarian organizations that work on the field, as after previous discussions with the presidents and lidersheap of the local communities, first we made evaluation of the size and type of the necessary materials, than me made the selection of the families that fulfill the conditions for using such help, Dimovski said. He explained that CARE International has vide understanding that the help is necessary for every family, without exception, in the regions hit by the last years military crisis. However, in this phase the help will be given to the families, according to the previous made assessments, that have the most urgent need from the help.

Leshok, Neproshteno and Tearce are the villages that received a large amount of help in the first phase, because these villages, according to the evaluations are mostly hit by the war conflict.

Ali Ramadani, field worker from CARE, said that the distribution of the help is proceeding very good, thanks to the local inhabitants in the villages, where the help was given, also with the good cooperation with the presidents of the local communities in these villages.

- We didn’t have the chance to give help to everybody that needed help, because our sources are limited, Dimovski said, adding that in the second phase, which is in process, the humanitarian help will be given to the other inhabitants of the same villages that didn’t receive help in the first phase.

According to Gabriela Micevska, senior officer in CARE for agricultural development, in the same villages a training for the people will be organized, which will be consisted of theoretical and practical part.

- Professors from the Agricultural faculty are engaged for carrying out the training, also experts form other institutes that are in this field of work, said Micevska.

Micevska informed us that the second phase of the project is expected to organize 16 workshops with several subjects from the field of mushroom breeding, sheep breeding, greenhouse production (early vegetable), poultry breeding, cheese production and courses for farm accounting of the small farmers and agriculturalists. The last-mentioned point, says Micevska, will help the small farmers a lot, to have a view in any time, on how much they have spend and earned, during the year from their work.

The training will begin in the end of November and it will last till the end of February, and the workshops will be open for everybody that is interested.

- Beside the theoretical part, the lectures on each subject will include practical part also, Micevska said, with notification that for realization of the second phase of the project, 15.000 $ are provided, financed by the Canadian Government. She said that negotiations are in process, about providing additional materials to help the people in this region, and it is more than obvious that this kind of help is necessary.

Published in the newspaper “Global” on 15.10.2002, in Macedonian and Albanian language.

HUMANITARIAN HELP FROM THE CANADIAN “CIDA”

Four municipalities from the region of Tetovo that were involved in the war crisis last year, are included in the Household Livelihood Support Project of the Canadian Humanitarian Organization “CIDA”, that realizes financial and other kind of support for development of the livestock breeding. The help is provided for fifteen villages from the municipalities Djepshiste, Vratnica, Tearce and Jegunovci that were involved directly or indirectly in the conflict last year. We have information from “CIDA” that the project is implementing in the villages Gjermo, Raotinci, Kopance, Leshok, Slatino, Prshovce, Nerashte, Dobroshte, Neproshteno, Tearce, Dolno Orashje, Belovishte, Staro Selo, Rogacevo and Jazince.

The project started in July this year and it will last till April next year. The purpose of this project is to help the small-scale farmers and small-scale farming in the region of Tetovo, said Ljubomir Dimovski, mission representative from CARE International in Macedonia.

Dimovski informed us that the project is executing in three phases, and each phase has its own meaning.

The first phase, as Dimovski said, provides distribution of supplies for the small-stock farmers for continuous agricultural work. The help is consisted of distribution of cement, fertilizer and tools for work and fuel for carrying out the autumn sowing.

The second phase provides trainings with directions and advises for the small-stock farmers for having their own accounting and manuals that point the places where the farmers can apply for credits.

- Our farmers and the people that are involved in agriculture for long time don’t pay attention or they don’t have own accounting for the costs and for their profit. In the developed countries in the world, the small-stock farmers have own accounting. This phase of the project has a purpose to explain our farmers about the benefit of having own accounting and having evidence for all expenses and the profit from their work, said Dimovski. In addition, Dimovski said, training with manuals is expected for raising specific agricultural products, for ex: mushroom production. Dimovski said that he believes that with this training, the profitable crop, which was not enough present in this part of the country. He explained that the third phase of the project referees to the selection of the households that will organize beekeeping and mushroom production.

The distribution of the help will start at the end of this or at the beginning of the next month, Dimovski said. Dimovski informed us that the Demining started in the region of Tetovo. The project, which is financed by the European Agency for Reconstruction, involves all regions that are supposed to contain unexploded mines from the conflict that happened last year.

The process is very slow, but the efficiency is big. The deminig process in Popova Sapka is active, said Ljubomir Dimovski, mission representative of CARE International in Macedonia.

This humanitarian organization exists in Macedonia from 1999. CARE took active place in overcoming the crisis in Kosovo, with providing humanitarian help for the refugees from the war in Kosovo.

4.7 Conditionality, Risks & Assumptions

There was no conditionality attached to the contract. Risks and assumptions were outlined in the Plan of Operation, covering the political and economic environment for the assistance and the willing participation of the various stakeholders in the project.

The political environment in which the project has evolved in the last quarter was not an easy one; the electoral process gave difficulty to travel in the Tetovo areas. Also the project needed to be careful to not give the impression to support any political leaders in the areas while discussing beneficiary selection.

The mixed team of two staff active in the daily field activities (one Macedonian women and one Albanian men) in this regard enable the project representation to be considered fair and inclusive of both majority ethnical groups. Also the project has included both Serb and Turk minorities. A special emphasis was made to meet with women in the targeted beneficiary households.

Risks associated with the ability to quickly gain co-operation of the various stakeholders (especially local authorities and NGOs) and delays in commencing activities with them due to the initial slow pace of start-up of the assistance have not manifest any loss of opportunity of synergies between different project activities.

One of the success factors of the HLS Project delivery to date is linked to the high ability of the team to prepare well and to develop coherent methodologies before handing over field activities. It is clear from the fieldwork, that a range of political and ‘ethnically-related’ difficulties do impact on the assistance and constrain implementation of the work plans but we want to congratulate the team for maintaining quality delivery in this current situation.

The team manages well security issues and follow CARE code in this regard. Un-necessary risks are avoided. The security constraints do not disable the team to be fully active at the field level. It was interesting to observe the way field staff and beneficiaries knew each other. Dialogues were straightforward and a good atmosphere was present in the communication we had with the interviewees.

We would like to underline in this section that the security environment is still extremely hostile; tensions are still present: people to not travel after dawn, people are still afraid, security forces do not provide services people may need to enforce their human and property rights. It is unfortunate that nearly all donors are reducing their contribution when sources of income have not been re-established. This reduced donor funding input may lead to further tensions and we recommend the Canadian Government/CIDA to look at this situation with more emphasis by supporting economic initiatives that might prevent a worsening of the current situation.

5. Project Effectiveness & Efficiency

This section will evaluate the project within its effectiveness and level of efficiency. At first the management capacities will be commented to then review budget and expenditures to date, and to finally take a brief look at the internal control mechanisms in place.

5.1 Management

Five different management functions were observed during this Mid-term Evaluation. The data were collected from informal interviews with project staff and the project manager. The assessment evaluated specific areas to the project operational management, such as: Using Team, Project Quality Management and Project Management System. The next table reports the findings.

| HLS Project Mid-term Evaluation - Management Findings |
| --- |
| Management Function | Finding |
| 1. Project’s ability to Use its Team (Organization & Direction) | The actual project’s organizational culture observed in this Mid-term evaluation was about team consensus and the will to create a common vision that involves everyone. The team members use a team process for enabling the project decision-making process. The manager guides the team to set up deadlines and does stimulate creativity to emerge. The working environment is pleasant (people smile and are happy to be doing their job); work is done professionally. |
| 2. Project Quality Management (Quality service and Beneficiary satisfaction) | The project monitors adequately its internal and external quality delivery. Staff are satisfied and committed to their project and hope to find funding for increasing beneficiary outreach. Local authorities are positive in the way the project reaches their population and with the level of professionalism and transparency the selection process is done. Interviewed beneficiaries did all comment about the relevance and usefulness of the services and kits they received. The positive areas are high quality communication and positive organic control. |
| 3. Project Management System (Direction in its Human Resources attribute) | The management system used by the HLS Project is highly organic. This organic management enables the project to avoid steering in a wrong direction. Relevant results were achieved in harmony within the project staffing, while including a large feedback mechanism with local authorities and local NGOS. Information systems are flexible and well conceived which avoid confusion and a need for a large staffing. |
| 4. Understanding Control (Control) | Tremendous facility to understand the links between delegation, self-monitoring and risk management among staff. The decision-making team process largely contributes to this situation. The use of external resources and surveyors have enabled economies of scale and increased supervision quality over the data sets collected. All Staffs are completing all tasks required on time. All staffs consider that they are not stress by their workload because deadlines are realistic ones and open to changes if constraints are found on the way. Weekly team meetings are a driving force to inspire guidance, vision and commitment. Considering the country managerial archetypes of the centrally planned economy, we want to underline the quality management control of the HLS Project. |
| 5. Result-based Management Logic (Planning and Design) | Clear understanding of the HLS Project logical application of Results-based management. CARE Canada has largely contributed to this fact by training all staff to the project logic and by proceeding in the project redesign with the project manager in July 2002. |

5.2 Internal Control

We may identify three important levels of internal control that are relevant to the HLS Project. The first one is linked to the transparency level of the services provided to the beneficiaries. The second one is in relation to the validity of the information collected and the accuracy of the technical assistance provided. The third one is in regard to the financial control.

Transparency

The selection process selected by the HLS Project is truly transparent. Local authorities were commenting positively about this fact and were wishing that other projects may be operating in the same way.

Validity of the Information Collected

The information collected by the Selection Process enables the project to avoid duplication of aid and achieve best targeting of the neediest. The quantitative methodology and beneficiary scoring system for the full use of the Access Software home made application was fully insuring that no favouritism disturbed the selection process.

We may underline that all data of the project are filled on a shared network but also a backup is regularly done every two weeks to prevent any loss of data.

Accuracy of the Technical Assistance Provided

The quality recruitment of the Agricultural Officer enables the project to prepare a high profile quality-training program for its beneficiaries. Local experts, lecturers and practitioners were selected and consulted to develop relevant training session. The Mid-term Evaluator is confident that these training sessions will bring useful information and skills to the HLS Project’s beneficiaries.

Financial Control

CARE Kosovo gives daily feedback and strong software support to any request of the CARE Macedonia HLS Project Financial Officer. The system uses two peaces of software: Cash Imprest Manager and Scala.

Cash Imprest Manager enables systematic and accurate petty cash management. The Project Manager audits the petty cash every two weeks.

CARE Macedonia reconciles its bank accounts accurately.

All financial reports and vouchers are process within the scala system and posted on a daily basis and transferred electronically every week to Prishtina. Voucher verifications are done in Skopje by CARE Kosovo every two weeks or at least once a month depending of the volume of financial transactions to verify. All originals are kept in Skopje.

The monthly-book reconciliation between CARE Kosovo and CARE Macedonia is processed within 5 to 15 days, which is excellent. We cannot fortunately say the same thing with the involvement of CARE Canada, which has a current data input void of more than three months for the coverage of the international technical advisor to the project: air ticket, insurance and salary.

The only problem we have noticed is linked to the management of the Transit Account if mis-matched data are entered in the Scala system.

Currency exchange is managed weekly within the system, which is excellent in order to avoid bad surprises.

The banking services received by the project are considered satisfactory.

Costs have been controlled in order to be kept low up to date, while insuring quality delivery. The team is extremely cost-aware; they want to service the largest number of beneficiaries at the better price.

5.3 Budget and Financial Projections

The summary of expenses to date next page shows that the project attempts to reach greater level of efficiency than originally planned. Communication expenses are going low and were reduced to a minimum.

Cost-effectiveness has been reached in supply higher quality supplies to the project beneficiaries at a lower cost, which enabled the project to deliver 215 kits instead of 80 kits as originally planned. Savings from one budget line to the other will enable the HLS project to deliver 50 Income Generation Kits instead of 30 as originally planned. We may although argue that the pricing of each type of kits have been over pessimistic.

We strongly suggest CARE Canada to provide the financial data required for the adjustment of the budget line 1: Personel / International Staff, as explained in the sub-section above.

We suggest CARE Kosovo to produce the following adjustment to the budget line 6: Direct Administrative Cost, through the following procedures:

- Provide adjustment to the sub-line: Program Officer, before the project closure, in order to void the severance cost of this position that was absorb wrongly by this project;

- Provide adjustment to the sub-line: Communication/utilities/Bank fee, before the project closure, in order to void the over-costing of the communications that was absorbing wrongly the late start of the CARE De-mining Project; and

- Provide adjustment to the sub-line: Prishtina Office, before the project closure, in order to void the over transfer to this account that was wrongly inputted in the financial system.

| HLS Project Budget and Expenses to date |
| --- |
|  | Line Item | Budget | Budget | EXP | Exp | Subtotal | Exp | Exp | Exp | Exp | Addit. Exp | Exp | Available | Percent |
|  |  | CAN$ | US$ | Apr-May 02 | Jul-02 | Jul-02 | Aug-02 | Sep-02 | Oct-02 | Nov-02 | Nov-02 | to date | Budget | Spent |
| 1.0 | Personel | 91,040 | 56,521 | 771 | 428 | 1,199 | 4,520 | 3,058 | 4,884 | 996 | 3,301 | 17,957 | 38,564 | 31.8% |
|  | International Staff | 45,440 | 10,329 | 579 | 87 | 666 | 2,912.82 | - |  |  |  | 3,578.76 | 6,750 | 34.6% |
|  | National Staff | 45,600 | 46,192 | 192 | 341 | 533 | 1,607.44 | 3,058.43 | 4,883.55 | 995.57 | 3,300.60 | 14,378.33 | 31,814 | 31.1% |
| 2.0 | Project Supplies | 230,000 | 151,085 | - | - | - | - | - | 451 | 21,181 | 17,204 | 38,836 | 112,249 | 0.0% |
|  | Emergency Response Kits |  | 72,375 | - | - | - | - | - | 451 | 21,181 | 17,204 | 38,835.88 | 33,539 | 53.7% |
|  | Economic Dev Kits |  | 78,710 | - | - | - | - | - |  |  |  | - | 78,710 | 0.0% |
| 3.0 | Operating Inputs | 39,356 | 19,499 | 173 | - | 173 | - | - | - | - | - | 173 | 19,326 | 0.9% |
|  | Expert Input |  | 10,000 | - | - | - | - | - |  |  |  | - | 10,000 | 0.0% |
|  | Workshop/Training Costs |  | 8,000 | - | - | - | - | - |  |  |  | - | 8,000 | 0.0% |
|  | Visibility |  | 1,499 | 173 | - | 173 | - | - |  |  |  | 172.71 | 1,326 | 11.5% |
| 4.0 | Transport | 40,000 | 24,158 | 3,637 | 1,443 | 5,080 | 1,372 | 795 | 570 | 571 | - | 8,388 | 15,770 | 34.7% |
|  | Vehicles |  | 12,000 | - | 800 | 800 | 533 | 570 | 570 | 570 |  | 3,043.00 | 8,957 | 25.4% |
|  | Fuel/Maintenance |  | 3,837 | 837 | 577 | 1,414 | 826 | 140 |  |  |  | 2,379.65 | 1,457 | 62.0% |
|  | Travel Costs |  | 8,321 | 2,800 | 66 | 2,867 | 13 | 85 |  | 1 |  | 2,965.49 | 5,356 | 35.6% |
| 5.0 | Monitoring & Evaluation | 3,600 | 2,250 | - | - | - | - | - | - | - | - | - | 2,250 | 0.0% |
|  | M&E Costs |  | 2,250 | - | - | - | - | - |  |  |  | - | 2,250 | 0.0% |
| 6.0 | Direct Adininstrative Cost | 61,120 | 37,185 | 12,533 | 9,244 | 21,777 | 6,836 | 5,167 | 1,235 | (195) | 36 | 34,857 | 2,328 | 93.7% |
|  | Office Rent | 4,800 | 4,000 | 1,100 | 550 | 1,650 | 550 | 550 | 550 | (238) |  | 3,061.67 | 938 | 76.5% |
|  | Office Equipment | 1,600 | 799 | 123 | 197 | 321 | - | - | 29 | - |  | 350.34 | 449 | 43.8% |
|  | Office Supplies | 3,360 | 1,832 | 631 | 355 | 986 | 185 | 60 | - | - |  | 1,231.46 | 601 | 67.2% |
|  | Comms/Util/Bank |  | 5,108 | 3,078 | 1,537 | 4,615 | 731 | 401 | 394 | 44 | 36 | 6,221.34 | (1,113) | 121.8% |
|  | Contry Representative | 7,200 | 4,776 | 748 | 1,050 | 1,797 | 1,122 | 1,304 |  |  |  | 4,222.94 | 553 | 88.4% |
|  | Finance/Procurement Officer | 6,160 | 3,930 | 748 | 423 | 1,171 | 433 | 458 | 261 |  |  | 2,322.87 | 1,607 | 59.1% |
|  | Programe Officer | 6,000 | 2,417 | 975 | 1,520 | 2,495 | - | (1,147) | - | - |  | 1,348.04 | 1,069 | 55.8% |
|  | Prishtina Office | 32,000 | 14,323 | 5,130 | 3,612 | 8,742 | 3,815 | 3,541 |  |  |  | 16,098.28 | (1,775) | 112.4% |
|  | Subtotal Project Direct Costs | 465,116 | 290,698 | 17,113 | 11,115 | 28,229 | 12,728 | 9,021 | 7,139 | 22,553 | 20,541 | 100,211 | 190,487 | 65.5% |
|  | CARE Canada ICR @ 7.5% | 34,884 | 21,802 | 1,284 | 834 | 2,117 | 955 | 677 | 535.41 | 1,691.48 | 1,540.55 | 6,401 | 15,401 | 29.4% |
|  | Total | 500,000 | 312,500 | 18,397 | 11,949 | 30,346 | 13,683 | 9,698 | 7,674 | 24,245 | 22,081 | 106,612 | 205,888 | 34.1% |

6. Lessons Learned

The HLS Project, even with a relatively small grant funding according to Eastern European standard, offers tremendous numbers of lessons. This section wants to underline the most important ones in regards to monitoring and evaluation, synergy, equity and diversity, partnership and community participation, capacity building and sustainability.

Monitoring and Evaluation

- By reducing the budget line allocated to international staff, the project has been able to hire a highly qualified and committed team, which in turn developed high quality standard monitoring and selection systems.

- Even if the project has limited resources it has been able to prioritize a limited allocation of funds to develop a software application for the selection of its beneficiaries by a scoring system, which in turn reduced the need for additional staffing and have saved a tremendous amount of time to the team.

Synergy

- The establishment of a selection board committee involving local authorities and local NGOs have facilitated the acceptation of the project among its beneficiary communities, which in turn has enabled a revision of the selection and avoided favouritism.

- The training program has been built in consultation with the National Agronomic Faculty, which increases interest in providing services in the Tetovo areas. Also, this involvement has reduced the cost burden of hiring few technical experts for a longer period than needed.

Equity and Diversity

- The team represents a role model in showing that both Albanians and Macedonians can work together.

- Gender issues are well managed within the HLS Project and the CARE Macedonia Office by the recruitment of mixed teams. Respect and hierarchical tasks are shared among the team and the environment is organic.

- The HLS Project gives also opportunities to youth to be part of the project activities.

Partnerships and Community Participation

- The project succeeded in developing strong partnerships with the communities involved in its activities.

- There is a strong will from the stakeholders to participate in the Agricultural Training sessions, services that are not available currently.

- Time is although limited for the HLS Project to built upon its findings and network in order to start-up new initiatives and support economic rehabilitation of the Tetovo areas.

Capacity Building

- The HLS Project even if funded from the CIDA - International Humanitarian Assistance Program has a strong strategy and will to develop a quick response to humanitarian needs in the Tetovo areas that can develop further economic opportunities to its beneficiaries, enabling its activities to focus on income generation potentials.

Sustainability

- In the context of humanitarian assistance it may be hard to argue about project sustainability. Although, the HLS Project shows creativity in developing a quick response to constraints limiting economic generation by providing good governance and transparent methods, enabling communities to establish dialogues and common goals within the training activities.

- The selection of training promoting high value cash commodities and farming accounting is cutting hedge and aligned with the up-coming agricultural policies in favour of the commercialization of the Macedonian agriculture.

7. Conclusion and Recommendations

The previous sections reported the fact-findings and observations of the Mid-term Evaluation of the HLS Project implementation, a project managed by CARE International Mission in Macedonia and finance through the CIDA – International Humanitarian Assistance (IHA) Program.

The purpose of this report is to review the implementation of the HLS Project and to provide feedback wherever needed in order to guide its coherent implementation. Here are the main conclusions of this document:

- The HLS Project is well managed and coherent to the project logic and established expected results;

- The team uses a dynamic and organic way of communication that enables professional delivery of the project;

- The beneficiaries were highly satisfied with the quality of the material they have received from the HLS Project, and have commented the aid being useful;

- The deliveries happened in a useful timing for the farmers with no material losses to date;

- Both local authorities and NGOS did appreciate the selection process used by the project;

- The team is extremely cost aware, which enabled the project to service to date 215 beneficiary households instead to 80 as originally planned. The project has increased its target to 265 households instead of 130.

- The HLS Project financial data are impeccably kept;

- Files and financial records have up-dated backups;

- The beneficiaries were highly satisfied with the quality of the material they have received from the HLS Project, and have commented the aid being useful;

- The deliveries happened in a useful timing for the farmers with no material losses to date;

- Both local authorities and NGOS did appreciate the selection process used by the project;

- The training program offers concrete opportunities for income generation for the project beneficiaries;

- Gender and diversity issues as well as security are matters well integrated in the daily operations.

Thereby and following the previous sections, we recommend that:

- The HLS Team keeps its high managerial profile and its already shown commitment for servicing its beneficiaries;

- The HLS Project should be extended for a one-year period through a cost extension, considering its small cost and the quality of its management the argument makes sense;

- The Canadian Government to investigate the risk of tension escalation in the Tetovo areas;

- Fixed cost valuations be analyzed in regard to the financial viability of agriculture commodities that will be incorporated in the HLS Project Agriculture Training Program;

- Training tests and evaluation forms be completed before the training delivery in order to assess knowledge gains and training relevance;

- CARE Kosovo and CARE Canada proceed in the four minor financial adjustments outlined in section 5; and that

- CARE International Regional Management Unit document a case study on the corporate advantages of nationalizing management positions within country offices since the mission in Macedonia builds a strong cost-effective argument in this direction.

# Annexes   				Annex I:  HLS Project - Plan of Operation

# Footnotes

The opinions expressed in this report are those of the authors and do not necessarily reflect the opinions of CARE International or any other organization mentioned in the report. No attempt has been made to verify the consistency between recommendations contained in this report and CIDA rules and procedures. As a result, this should be verified before implementation of any of the recommendations contained herein.

This situation made the evaluation more difficult for the evaluator and a pleasure to the team that was open to show how they operated, present their innovative approaches in solving problems and insuring transparency at all levels. This is not a common situation, which the evaluator has been used to be involved in.

# Text boxes

CARE International Macedonia

Maksim Gorki 20/3

1000 Skopje

Macedonia

Tel:  389 (2) 222-229

Fax: 389 (2) 214-635

e-mail: care@unet.com.mk